## Form D.06
DETAILS OF FINAL ESTIMATE
GRAND SUMMARY
Summary of Final Progress Quantities
Region:
Contract No.:
Contractor:
Primary Project:
Project Limits:
Primary WAC/Job:
Other Projects:
|  | Work Started: |  | Shut Down: |  | Dates: ________________________
|  | Work Resumed: |  | Completed: |  | Dates: ________________________
Item No. | Item Description |  | Quantities |  |  | Remarks
|  |  | Units | Tender | Actual
- NOTE: This form represents the total quantity by bid item for all work under the contract.
- Details regarding bid item and quantities by locations is detailed in the final progress payment
| PREPARED BY: |  |  |  | APPROVED BY:
| Consultant's Signature |  | Date: |  | Project Sponsor
CERTIFIED CORRECT BY:
Date:
| Consultant's Seal/Stamp |  | Date:

## D.06 Sample
DETAILS OF FINAL ESTIMATE
GRAND SUMMARY
Summary of Final Progress Quantities
Region:
Contract No.:
Contractor:
Primary Project: |  | Hwy XXX:XX or Bridge File XXXX-0X (Hwy XX.X at km x.xx)
Project Limits: |  | Hwy X to Hwy XXX (km x.xx to x.xx)
Primary WAC/Job:
Other Projects: |  | Hwy XX:XX, Hwy XX:XX
Hwy XX:XX, Hwy XX:XX
|  | Work Started: | 2013-01-01 | Shut Down: |  | Dates: ________________________
|  | Work Resumed: |  | Completed: |  | Dates: ________________________
Item No. | Item Description |  | Quantities |  |  | Remarks
|  |  | Units | Tender | Actual
1 | Mobilization |  | lump sum | 200000 | 200000
2 | Site Occupancy |  | days | 12 | 19 | 7 days over
3 | Supply of Aggregate w/Option |  | tonne | 54460 | 54599.22
4 | Cold Milling Asphalt Pavement |  | m2 | 375100 | 369684.33
| EWO #1 |  | lump sum | n/a | 3500 | Replace culvert
| EWO #2 |  | lump sum | n/a | 2300 | Replace damaged sign
| Diesel Fuel Cost Adjustment |  | lump sum | n/a | 1500 | EPS price adjustment
| Traffic Accommodation Strategy |  | lump sum | n/a | 2000 | EPS price adjustment
| Smoothness |  | lump sum | n/a | 510 | EPS price adjustment
- items listed above are for
example purposes only
- NOTE: This form represents the total quantity by bid item for all work under the contract.
- Details regarding bid item and quantities by locations is detailed in the final progress payment
| PREPARED BY: |  |  |  | APPROVED BY:
| Consultant's Signature |  | Date: |  | Project Sponsor
CERTIFIED CORRECT BY:
Date:
|  | Consultant's Seal/Stamp | Date: