## Utility Conflict Matrix
UTILITY CONFLICT MATRIX
Project Information | [18 empty] | Color Legend
Project Number | [10 empty] | Consultant | [8 empty] | Conflict Resolved
Project Description | [10 empty] | Completed By | [8 empty] | Confirmed Conflict
AT Sponsor | [10 empty] | Updated | [8 empty] | Review Required
AT PM | [10 empty] | Edited
Instructions: use filtering so UO's only see their info. Save and send as PDF to appropriate Utility Owner.
Utility Conflicts
Conflict # | Reference Drawing | Owner | Utility Type | Utility Orientation | Lanes Affected | Road | Start Control Section | Start Offset | End Control Section | End Offset | Location Description | Assessment of Effects | Conflict Identified | Letter Sent - Signed and Dated | Utility Letter # | Utility Adjustment Required | Plan for Resolving Utility Adjustment Exists | Agreement | Agreement Status | Conflict Resolved? | Notes
1 | Drawing Set Name, Sheet, Figure | AltaLink | Overhead Power | Parallel | None | 2 |  |  |  |  | W. of CN Crossing | No Conflict, outside of project limits. IFC drawings and schedule to be forwarded | N | 2012-01-23 | 4 | N | N | Not required | Not required | Y | Utility Contact
2 | Drawing Set Name, Sheet, Figure | ATCO Gas | Low Pressure Pipeline | Crossing | None | 2 |  |  |  |  | E. of pedestrian overpass | The utility is crossing HWY 2. Cross sections suggest there is no vertical conflict in this area. | N | 2012-01-24 | 4 | N | N | Crossing (Adj) | Review by Utility Owner | N
3 | Drawing Set Name, Sheet, Figure | Bell | Burried Telecom | Parallel | East | 2 |  |  |  |  | E. of Hwy 2, Legal Land Description | The utility is running along xx drive on the east side of the road. Cross sections not yet available. Check any potential conflicts with the utility. Relocate or protect utility as required. The line is impacted with the location and construction of the bridge foundation piles and within the retaining wall influence zone. Additionally a proposed stormwater pond is located in the northeast quadrant of Highway 2 and xx Drive with 2 m grade cuts along the fibre line. Therefore, relocation is required for this line. Alternatives north of the bridge structures have been identified as possible relocation options. | Y | 2012-01-24 | 4 | Y | N | Crossing (Adj) | N | N
4 | Drawing Set Name, Sheet, Figure | Bell | Telecom Conduit | Bridge | East | 2 |  |  |  |  | BF012345 | Utility located on BF012345 on east side of bridge running along x girder | Y | 2012-01-24 | 4 | Y | N | Crossing (Adj) | N | N