## General Info
Intent
There are two separate 'Bridge Cost Data' spreadsheets, 'Projects' and 'Bid Items', which contain the same cost data organized in different ways.
This spreadsheet, 'Projects', groups the data by project and bridge file in order to provide an archive of project cost data to find similar projects to use as comparables when preparing cost estimates for Department projects.
Use
The 'Index' tab contains a list of projects, with corresponding sortable fields which can be used to identify projects with the desired characteristics for comparison. In order to sort, click the arrow in the top cell of each field and select the desired sort values.
The first column, 'Link', contains links to the cost data for each project within this spreadsheet (note that it will always correctly select the right destination cell, but sometimes you need to scroll up or down on the mouse slightly to get the screen to correctly move to the right location).
In order to organize the data and make it easier to navigate, each project's cost data is 'grouped' in excel. All groups are collapsed by default. To show the data for each group, click on the 'plus' icon to the left. To collapse it again, click on the 'minus' icon.
Multiple projects can be shown at once, which can help with comparing the data from similar projects.
In order to show all projects on a sheet, click the '2' at the top left. Click the '1' to collapse all projects.
This spreadsheet is provided unprotected, to permit the extraction, sorting and processing of cost data as desired by the user.
Details
The cost data is separated for each bridge file for projects that either have multiple bridge files or other major components of work (such as significant roadway work beyond bridge approach or tie-ins). Typically other major component work is determined to be significant enough to separate its data from the bridge file work when it has a separate WAC number. If there are multiple bridge files for a project, their data will still be separated even if they share a WAC number. Only the cost data related to bridge files is presented in this spreadsheet.
An exception to the above is when there are a large number of bridge files with cost data that is either difficult to separate or the work is minor in nature, in which case it is presented together with the bridge file column marked as 'Multiple'.
The cost data provided is an average of the lowest three bids, in order to preserve bid confidentiality.
The coefficient of variation (the standard deviation divided by the average, expressed as a percentage) is provided in order to provide a sense of how variable the three bids were. The smaller the coefficient of variation is, the less variation there is between the lowest three bids.
Site occupancy and lane closure data relating to the noted bridge structure is provided in a separate table below the cost data table.
For larger roadway projects that do not have separate site occupancy or lane closure bid items for the bridge structure work, the site occupancy and lane closure fields are omitted.
A bid item noted as being 'PRORATED' in its description indicates that it is a single bid item, such as mobilization or traffic accommodation, for which only a portion applies to the noted bridge structure (due to it being a shared bid item between roadway and bridge structure scopes, and/or between two or more bridge structures). The prorating is equivalent to the percentage of the cost of the noted bridge structure in relation to the total project cost (minus the prorated bid items).
Data Fields
Some additional details/context for a few of the data fields in this spreadsheet:
Tender Opening Date: This is the date when the Department opened the Tenders and is the primary date associated with the cost data as it is when it is most accurate (since it is closest to the date when the bids were submitted). Not to be confused with the Contract Award date which can be much later.
Tender Fiscal Year: The Department's Fiscal year is from April 1 to March 31 of each year.
Project Type: This provides info on the size and complexity of the overall project that the cost data is from, which can have a significant impact on the applicability of the data to a project as a comparable. Single - A project with a single bridge file scope of work, and no significant highway scope of work. A single bridge file related WAC. Multiple - A project with multiple bridge file scopes of work, and no significant highway scope of work. Either multiple bridge file related WACs or a single WAC with multiple associated bridge files. Highway - A project a significant highway scope of work, but only a minor bridge file scope of work that does not have a separate bridge file related WAC. Combined - A project with a significant highway scope of work and a significant bridge file scope of work, typically with separate WACs. Complex - A project with a significant highway scope of work and multiple bridge file scopes of work, typically with separate WACs.
Bridge/Culvert Total Length: This is either the total length of a bridge (the sum of all the span lengths) or the total length of all culvert barrels (the sum of all the barrel lengths if there are multiple barrels).
Bridge Width or Culvert Diameter: This is either the total out to out width of a bridge (measured square) or the diameter of a culvert barrel. In the case of a bridge deck with tapering width or culverts with varying barrel diameters, it is the average width along the length.
Bridge/Culvert Total Length and Bridge Width or Culvert Diameter can be multiplied together to get an effective area for the bridge or culvert, in order to generate per m2 bridge file cost data, if desired.
Scope of Work: This is the scope of work copied from the Tender of each contract. Note that, typically, it has not been edited or verified. It can be used along with the spreadsheet search to identify projects with desired work scopes for comparison.
Limitations
This spreadsheet only contains cost data from design-bid-build (DBB) delivery model projects as other project delivery models, such as design build (DB) and private public partnerships (P3), have incompatible bid and payment structures.
For projects that only have a single bidder, cost data is omitted in order to preserve bid confidentiality.
For projects that only have two bidders, the coefficient of variation is omitted in order to preserve bid confidentiality, as it could permit back calculation of the two bids.
Questions
Questions or comments on this spreadsheet can be directed to:
Michael Kostyra Bridge Construction Engineer Technical Standards Branch – Bridge Engineering Transportation and Economic Corridors michael.kostyra@gov.ab.ca

## Project Index
Link | Tender Number | Bridge File Number | Str | Tender Opening Date | Number of Bidders | Tender Fiscal Year | Region | Project Type | Work Type | Work Description | Structure Type | Span/Culvert Material | Span/Culvert Type | Span/Culvert Details | Bridge Span Lengths or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter | SSBC Version | Specified Contract Completion | Hwy | Sec | Crossing | Location | Scope of Work
Go To | 23525 | Multiple | - | 2023-04-13 | 3 | 2023-2024 | Southern | Highway | New Sign Structures | Construct Sign Structures | Sign Structure | - | - | - | - | - | - | 2020 | 2024-07-31 | - | - | - | Deerfoot Trail | Scope of Work: Overhead sign structures including install new sign panels and related works
Go To | 23533 | 78151 | 1 | 2023-04-18 | 1 | 2023-2024 | North Central | Single | Bridge Repair | Bridge High Load Damage Repair | Bridge | Concrete | FM | 16 x 1170 FM | 28 ¦ 26 | 54 | 27 | 2020 | 2023-10-15 | Local | Road | Highway 63 | At Ft McMurray | Scope of Work: Traffic Accommodation Removal and salvage of existing bridgerail Removal and disposal of damaged precast concrete girder (S2G1) and sidewalk Removal and disposal of affected lateral post-tensioning and hardware Removal and disposal of affected bridge bearings Supply new precast concrete girder, S2G1 Delivery and erection of the replacement precast concrete girder Supply and Install bridge bearings Place grout pads for new bearings Lateral Connection restoration between new and existing girders Supply and placement of Type SCC (Type FP Concrete) concrete diaphragm at lateral girder connections c/w all formwork required Lateral post tensioning installation including supply of new high strength bolts, nuts, washers etc. and miscellaneous associated materials Casting new concrete sidewalk using Class HPC concrete Reinstall existing bridge rail at S2G1 Concrete girder repairs (S2G16) Install new bridge rail anchor bolt assemblies at S2G1 Reinstall existing bridge rail at S2G1 Supply and installation of deck joint assemblies Supply and placement of Class HPC concrete at deck joints Supply and placement of Class HPC concrete with steel fibres concrete deck overlay
Go To | 18129 | 78321 | 1 | 2023-04-20 | 3 | 2023-2024 | Peace | Highway | Remove Bridge | Remove Timber Bridge | Bridge | Timber | Treated Timber Beam | Treated Timber Beam | 6 ¦ 9 ¦ 6 | 21 | 7.9 | 2020 | 2024-07-28 | 686 | 12 | Tributary to Trout River | 80 km East of Red Earth Creek | Scope of Work: Demolition and removal of existing timber bridge structure and guardrail as determined by the Consultant
Go To | 22729 | 9125 | 1 | 2023-05-10 | 4 | 2023-2024 | Central | Single | Ferry Rehabilitation | Ferry Rehabilitation | Ferry | - | - | - | - | - | - | 2020 | 2024-04-19 | 838 | 2 | Red Deer River | 10 km West of Munson | Scope of Work: Scarifying, levelling, and compacting an existing gravel turnaround to provide a firm and level surface to stage the ferry rehabilitation work Moving and lifting a barge-style cable ferry from a dry-dock position to a raised construction staging position Implementing and maintaining environmental controls Erecting, maintaining, and removing a temporary hoarding enclosure around the Vessel, including all heating and lighting, to complete structural steel welding, recoating, and additional ferry rehabilitation scopes of work Carrying out complete coating removal and replacement for most ferry components Executing like-for-like structural steel replacement of isolated hull components Supply and installation of miscellaneous moisture control materials
Go To | 22125 | 2298 | 2 | 2023-05-11 | 1 | 2023-2024 | Southern | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 8 x 510 SLC | 14 | 14 | 9.9 | 2020 | 2023-10-31 | 507 | 4 | Kettles Creek | 2 km Southeast of Pincher Creek | Scope of Work: Traffic accommodation Water management Demolition and disposal of existing bridge structure Excavation Backfill Steel piling Reinforcing steel Construction of abutments Supply and erection of 14m span precast concrete girders Construction of concrete deck and approach slabs Waterproofing and paving Bridgerail and approach transition rail Guardrail Class 1 heavy rock riprap Seeding Erosion and sediment control Roadway work
Go To | 21916 | 6893 | 2 | 2023-06-07 | 3 | 2023-2024 | Central | Single | Replace Bridge with Bridge | Construct SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 8 x 510 SLW | 8 ¦14 ¦ 8 | 30 | 9.9 | 2020 | 2023-10-31 | 587 | 4 | Threehills Creek | 22 km Northeast of Torrington | Scope of Work: Traffic accommodation Site isolation and water accommodation (Care of Water) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structure, including guardrail Excavation Supply, set-up and drive steel H-piling Abutment construction Pier construction Heavy rock riprap erosion protection including geotextile filter fabric Supply, delivery, and erection of concrete girders Approach slab construction Deck waterproofing and asphalt concrete pavement including material testing Miscellaneous iron Roadway work Supply and installation of bridgerail and guardrail Permanent environmental protection devices
Go To | 23534 | Multiple | - | 2023-06-15 | 4 | 2023-2024 | Southern | Highway | New Sign Structures | Construct Sign Structures | Sign Structure | - | - | - | - | - | - | 2020 | 2024-10-01 | - | - | - | Deerfoot Trail | Scope of Work: Overhead sign structures including removal and disposal, supply and install, modifications, and related works
Go To | 22567 | 1404 | 2 | 2023-06-27 | 1 | 2023-2024 | Central | Single | Replace Bridge with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 2200 CSP | 35 | 35 | 2.2 | 2020 | 2023-11-01 | 604 | 2 | Tributary to Whelp Brook | 14 km West of Morningside | Scope of Work: Traffic Accommodation Clearing, Timber Salvage and Mulching Temporary and Permanent Fencing Removal and Disposal of Existing Bridge Structure Access Management Common Excavation Contractor Supplied Borrow Grading Gravel Surfacing Topsoil Placement Seeding Building Demolition Asbestos Abatement Bridge Culvert Construction (BF 01404) Total Suspended Solids (TSS) Testing Structural Excavation Supply, Assembly and Installation of CSP Culvert Material Supply and Install De-icing Line Structural Backfill Class 1 Heavy Rock Riprap Erosion Control Barrier (Straw Rolls) Erosion Control Soil Covering (Type C) Fish Capture and Release
Go To | 20234 | 74978 | 1 | 2023-06-29 | 2 | 2023-2024 | North Central | Multiple | Remove Bridge | Remove Precast Concrete Girder Bridge | Bridge | Concrete | Concrete Stringer | 7 x 1120 Concrete Stringer | 16 ¦ 16 ¦ 21 ¦ 19 | 72 | 15.2 | 2020 | 2023-10-15 | 16 | 12 | Mine Haul Road | North Boundary of Wabamun | Scope of Work: Traffic Accommodation Grading Granular Base Course (GBC) Asphalt Concrete Pavement (ACP) Bridge Demolition and Removal
Go To | 20234 | 74978 | 2 | 2023-06-29 | 2 | 2023-2024 | North Central | Multiple | Remove Bridge | Remove Precast Concrete Girder Bridge | Bridge | Concrete | VF | 8 x 1320 VF | 32 ¦ 21 ¦ 20 | 73 | 13.7 | 2020 | 2023-10-15 | 16 | 12 | Mine Haul Road | North Boundary of Wabamun | Scope of Work: Traffic Accommodation Grading Granular Base Course (GBC) Asphalt Concrete Pavement (ACP) Bridge Demolition and Removal
Go To | 22927 | 75425 | 1 | 2023-07-06 | 5 | 2023-2024 | North Central | Single | Bridge Repair | Bridge Flood Damage Repair | Bridge | Steel | Bailey Truss | Bailey Truss | 21 | 21 | 3.7 | 2020 | 2023-12-15 | Local | Road | Lily Creek | Near Slave Lake | Scope of Work: Major Channel Realignment Embankments Repair Debris Removal Bailey Truss Member Repair Excavation – Channel Backfill – Des 2 Class 25 Backfill – Native Soil Rip Rap Class 2 – Supply and Install Rip Rap Class 1 – Supply and Install Timber Backwall – Supply and Install Gabion Baskets Wingwalls – Supply and Install Bioengineering Fish Capture, Salvage and Release Total Suspended Solids (TSS) Testing Site clean-up and Restoration
Go To | 23062 | 85370 | 1 | 2023-07-27 | 4 | 2023-2024 | North Central | Multiple | New Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 1600 CSP | 25 | 25 | 1.6 | 2020 | 2023-12-15 | 40 | 28 | Tributary to Luscar Creek | 4 km North of Cadomin | Scope of Work: Traffic accommodation for bridge construction Site isolation and water accommodation Total Suspended Solid (TSS) Fish capture, salvage, and release Structural excavation Removal and disposal of existing Corrugated Steel Pipe (CSP) culvert Supply, assemble, and installation of Corrugated Steel Pipe (CSP) culvert Granular backfill and non-granular backfill (clay seal) including supply and placement of geotextile filter fabric Roadway work Heavy rock riprap (Class 1) including supply and placement of geotextile filter fabric Heavy rock riprap (Class 1M) substrate supply and placement Permanent environmental enhancement, and erosion and sediment control devices
Go To | 23062 | 85371 | 1 | 2023-07-27 | 4 | 2023-2024 | North Central | Multiple | New Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 2200 CSP | 42 | 42 | 2.2 | 2020 | 2023-12-15 | 40 | 28 | Tributary to Teepee Creek | 22 km Southeast of Hinton | Scope of Work: Traffic accommodation for bridge construction Site isolation and water accommodation Total Suspended Solid (TSS) Fish capture, salvage, and release Structural excavation Removal and disposal of existing Corrugated Steel Pipe (CSP) culvert Supply, assemble, and installation of Corrugated Steel Pipe (CSP) culvert Granular backfill and non-granular backfill (clay seal) including supply and placement of geotextile filter fabric Roadway work Heavy rock riprap (Class 1) including supply and placement of geotextile filter fabric Heavy rock riprap (Class 1M) substrate supply and placement Permanent environmental enhancement, and erosion and sediment control devices
Go To | 20343 | 9851 | 2 | 2023-08-17 | 1 | 2023-2024 | Central | Single | Replace Culvert with Culvert | Construct WSP Culvert | Culvert | Steel | WSP | 1 x 2740 WSP | 72 | 72 | 2.7 | 2020 | 2024-06-30 | 16 | 22 | Norris Creek | 29 km East of Ardrossan | Scope of Work: Traffic Accommodation for Bridge Construction Secure Laydown area within Elk Island National Park. Install fencing around Laydown, as required Remove and Dispose Existing Fence (Class F) Topsoil Stripping and Stockpiling Structural Excavation Remove and Dispose CSP Bevel Ends Supply and Trenchless Installation of WSP (2743 mm dia.) Supply and Install Steel Median Drain Grout Abandoned Culvert Supply and Install new Fence (Class F) Supply and Install Woven (as required) and Non-Woven Geotextiles Supply and Install Heavy Rock Riprap (Class 1) Supply and Install Erosion Fence Barriers (Straw Rolls) Supply and Install Erosion Control Soil Covering (Type B) Roadway Embankment Re-grading and Site Restoration
Go To | 23872 | 73810 | 1 | 2023-08-30 | 3 | 2023-2024 | North Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | VF | 8 x 1270 VF | 24 ¦ 38 ¦ 38 ¦ 31 ¦ 31 ¦ 24 | 186 | 13.7 | 2020 | 2024-10-15 | 43 | 14 | Athabasca River | 5 km Northwest of Whitecourt | Scope of Work: Care of Birds Traffic Accommodation Surface Removal Removal and Disposal of Bridge Components Partial Depth Concrete Repairs Full Depth Concrete Repairs Concrete Crack Repairs Shear Key Repairs Galvanic Corrosion Protection Installation Deck Drain Repairs Girder Ends and End Diaphragms Modification Abutment Backwall Modifications New Approach Slabs New HPC Deck Overlay with Steel Fibres New Abutment Deck Joints – Cover Plated 178 V-Seal New Pier Deck Joints – Type 1 Strip Seal Bridgerail Repairs Bridgerail Grout Pad Replacements Traffic Accommodation Bearing Replacement Bearing Cleaning and Metalizing Repair/Replacement of Girders Expansion Links Existing Lateral Post-Tensioning Repairs New Steel Underslung Diaphragms Concrete Cleaning and Sealing Approach Transition Paving Painted Roadway Markings Seeding and Harrowing
Go To | 22393 | 75695 | 2 | 2023-09-19 | 6 | 2023-2024 | Peace | Complex | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 9 x 700 SLC | 20 ¦ 20 ¦ 20 | 60 | 11.1 | 2020 | 2025-10-15 | 58 | 10 | Caribou River | 36 km Northeast of Ft Vermilion | Scope of Work: Traffic Accommodation Demolition, Disposal, and Salvage Existing Structure Environmental Protection Works Care of Water Excavation - Structural Backfill – Crushed Granular Drilled concrete piles with installation of H – piles at abutments Drilled steel pipe piles filled with concrete at piers Construction of concrete pier caps and abutment seats Supply, fabrication, delivery and erection of SLC girders Supply, delivery and installation of elastomeric bearings Construction of concrete deck and curbs Construction of concrete approach slabs and wingwalls Asphalt concrete pavement and waterproofing membrane Supply and installation of bridgerail and approach rail transition Construction of drain troughs Supply and installation of silt fence barriers Supply and Installation of erosion control matting (Type C) Detour Road and Detour Bridge over Caribou River
Go To | 22393 | 75716 | 2 | 2023-09-19 | 6 | 2023-2024 | Peace | Complex | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 2700 CSP | 32 | 32 | 2.7 | 2020 | 2025-10-15 | 58 | 10 | Tributary to Caribou River | 31 km North of Ft Vermilion | Scope of Work: Traffic Accommodation Demolition, Disposal, and Salvage Existing Structure Excavation – Structural Environmental Protection Works Care of Water Total Suspended Solids (TSS) Testing Supply and Installation of a CSP culvert and a small bridge plaque Bedding and Backfill (includes woven geotextile filter fabric, crushed aggregate material Des 2 Class 40, crushed aggregate material Designation 2 Class 25, and clay seals) Heavy Rock Riprap Class 1 (includes non-woven geotextile filter fabric) Supply and installation of silt fence barriers Supply and Installation of erosion control matting (Type C)
Go To | 23922 | 73218 | 1 | 2023-10-11 | 2 | 2023-2024 | North Central | Single | Bridge Rehabilitation | Replace Superstructure SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 8 x 510 SLW | 10 ¦ 10 ¦ 10 | 30 | 10 | 2020 | 2023-12-15 | 661 | 6 | Shoal Creek | 11 km West of Dapp | Scope of Work: Traffic accommodation for bridge construction Remove and dispose of existing guardrail Excavation - Structural Demolition and disposal of existing bridge girders and pier caps Construct new cast-in-place pier caps Partial depth repair (Wingwall & Abutment Seat) Erection of new bridge girders and precast approach slabs Backfill Waterproofing Asphalt Concrete Pavement – Type H2 Bridgerail and guardrail – Supply and installation Impact Attenuator – Supply and installation Roadway work
Go To | 23137 | 76054 | 3 | 2023-10-18 | 4 | 2023-2024 | North Central | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 12 x 510 SLC | 11 ¦ 16 ¦ 11 | 38 | 14.8 | 2020 | 2024-10-15 | 2 | 36 | CNR Railway | At Morinville | Scope of Work: Coordination with CN Rail Environmental management including care of birds Traffic accommodation Removal and disposal of bridge components ACP surface removal New abutment construction (on existing and new piles) Driven steel H-piles (abutment wingwalls) Driven steel pipe piles (piers) New pier construction New precast concrete girders (SLC-510) New reinforced concrete deck New approach slabs and sleeper slabs New deck waterproofing and asphalt wearing surface Approach transition paving New bridgerail (including thrie-beam approach guardrail transitions) Salvage w-beam guardrail and guardrail modifications Concrete cleaning and sealing (abutments, piers, girders, etc.) New drain troughs Painted roadway markings Removal of existing crossovers Seeding and harrowing
Go To | 15989 | 74227 | 1 | 2023-11-02 | 2 | 2023-2024 | Peace | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Welded Box Girder | 2 x 3580 Welded Box Girder | 90 ¦ 111 ¦ 111 ¦ 111 ¦ 90 | 513 | 10.7 | 2020 | 2025-10-15 | 88 | 18 | Peace River | 8 km Northwest of Ft Vermilion | Scope of Work: Traffic Accommodation Surface Removal – Deck and Roof Slab ACP Surface Removal – Approach Slab & Approaches Roadway Demolition and Disposal of Bridge Structures Partial Depth Concrete Repairs of Deck and Roof Slab, Deck Overhang, Deck Soffit (Between Box Girders and Within a Box Girder), Curbs, and Abutments. Full Depth Concrete Repairs of Deck and Roof Slab, Deck within Box Girder, Curbs, and Abutments Concrete crack repair - curb and abutments Retrofit deck drains Steel Girder Modifications including, girder strengthening, steel support brackets, and steel girder end modifications. Deck End Modification Abutment End Modification Galvanic corrosion protection - supply and installation Abrasive blasting – deck surface Deck overlay concrete – supply and place Deck surface preparation for waterproofing Deck surface testing and inspection Deck waterproofing system Supply, fabrication, delivery, and installation of Mageba LR4 modular deck joint assemblies Asphalt concrete pavement and approach transition paving Approach grade widening Painted roadway markings Replacement of the abutment bearing grout pads including bridge jacking Replacement of drain troughs Concrete cleaning and sealing Supply and place fillcrete at the abutments Headslope improvement Miscellaneous Iron including supply, fabrication, and installation of four survey benchmark tablets, and galvanizing repair of salvage abutment drainage chutes. Approach rail transition upgrade, including wingwall and approach slab modifications Supply and install new bridge hazard markers Supply and installation of guardrail and impact attenuators Catwalk door repairs Supply and install slope inclinometer and vibrating wire piezometers Shorten and repair existing geotechnical instruments Supply and install permeant erosion control devices
Go To | 22614 | 76749 | 2 | 2023-11-28 | 6 | 2023-2024 | Peace | Single | Culvert Repair | Repair SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 2430 SPCSP | 115 | 115 | 2.4 | 2020 | 2024-03-15 | 40 | 34 | Tributary to Susa Creek | 15 km Northeast of Grande Cache | Scope of Work: Traffic Accommodation for Bridge Construction Care of Water Structural Excavation Supply and Installation of CSP Liner Supply and Placement of Concrete (Class S Modified) Supply and Installation of Class 3 Heavy Rock Riprap Roadway Work
Go To | 22336 | 13541 | 2 | 2023-11-29 | 2 | 2023-2024 | Peace | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 9 x 700 SLC | 20 | 20 | 11.1 | 2020 | 2024-10-15 | 671 | 2 | Beavertail Creek | 2 km West of Goodfare | Scope of Work: Traffic Accommodation Demolition and Disposal of Bridge Structure Headslope Preparation and Backfill Supply, Set-Up and Drive Steel H-Piling Supply and Placement of Reinforcing Steel (Plain, Corrosion Resistant and Stainless) Supply and Placement of Class C Concrete Supply, Delivery and Erection of Prestressed SLC-700 Interior and Exterior Curbs (20 m long) Supply and Placement of Reinforced Class HPC Concrete Bridge Deck and Approach Slabs Deck Waterproofing Roadway Work Supply and Placement of Class 1 Heavy Rock Riprap Bridgerail and Guardrail Installation Supply and Installation of Erosion Control Barrier (Silt Fence) Supply and Installation of Erosion Control Barrier (Straw Fibre Roll) Supply and Installation of Erosion Control Matting (Type C) Fish Capture and Release Turbidity Monitoring
Go To | 22346 | 71933 | 2 | 2023-12-07 | 2 | 2023-2024 | Peace | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 9 x 700 SLC | 20 | 20 | 11.1 | 2020 | 2024-10-15 | 670 | 2 | Tributary to Wapiti River | 10 km Southwest of Bezanson | Scope of Work: Traffic accommodation Site isolation and water management (Care of Water) Total suspended solids (TSS) testing Demolition and disposal of existing bridge structure Excavation Backfill Supply, set-up and drive steel H-piling Supply and placement of reinforcing steel for substructure and superstructure Supply and placement of concrete for substructure and superstructure Supply, delivery and erection of Type "SLC 700" concrete girders Deck waterproofing and asphalt concrete pavement Miscellaneous iron Supply and placement of heavy rock riprap including geotextile filter fabric Supply and installation of bridgerail and guardrail Roadway work Erosion and sediment control
Go To | 22610 | 74229 | 2 | 2023-12-19 | 5 | 2023-2024 | North Central | Single | Reconstruct Guide Bank | Reconstruct Guide Bank | Guide Bank | - | - | - | - | - | - | 2020 | 2024-06-30 | - | - | - | 4 km North of Blue Ridge | Scope of Work: Site access and preparation of laydown area(s) Environmental protection works Clearing Concrete slope protection removal Channel excavation Common excavation Embankment fill – Des 2 Class 40 aggregate Spur fill – Des 2 Class 40 aggregate Channel backfill – 100mm to 200mm clean coarse granular aggregate Topsoil excavation and placement Non-woven Geotextile Filter Fabric Modified Class 3 Heavy Rock Riprap Permanent sediment and erosion control
Go To | 20631 | 9684 | 2 | 2024-01-23 | 13 | 2023-2024 | Central | Single | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 1800 CSP | 52 | 52 | 1.8 | 2020 | 2024-10-15 | 593 | 2 | 2nd Order Tributary to Gough Lake | 47 km Southeast of Gadsby | Scope of Work: Traffic accommodation Site isolation and water accommodation (Care of Water) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge culvert structure Excavation including supply & placement of geotextile filter fabric Supply and assembly of culvert materials Backfill including backfill material testing Heavy rock riprap erosion protection including geotextile filter fabric Roadway work Permanent environmental protection devices
Go To | 12507 | 78651 | 2 | 2024-01-24 | 5 | 2023-2024 | Central | Single | Replace Culvert with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 3360 SPCSP | 49 | 49 | 3.4 | 2020 | 2024-10-31 | 816 | 2 | Tributary to Ghostpine Creek | 1 km South of Pine Lake | Scope of Work: Traffic accommodation Site isolation and water accommodation (Care of Water) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge culvert structure Excavation including supply & placement of geotextile filter fabric Supply and assembly of culvert materials Backfill including backfill material testing Concrete end treatment including concrete testing and small bridge plaque Heavy rock riprap erosion protection including geotextile filter fabric Roadway work Permanent environmental protection devices
Go To | 23812 | 1642 | 1 | 2024-01-25 | 2 | 2023-2024 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | VS | 9 x 510 VS | 9 ¦ 11 ¦ 9 | 29 | 11.1 | 2020 | 2024-10-25 | 53 | 10 | Meeting Creek | 2 km East of Donalda | Scope of Work: Clearing cliff swallow nests outside of nesting period and providing deterrent to further nesting activities Traffic accommodation for bridge construction Remove the existing concrete overlay Partial depth repairs to piers and girder curbs Remove curbs over the pier sections Supply and install girder filler plates between spans, install grout in between gaps and voids at the pier ends Construct new HPC concrete deck and curbs with corrosion resistant reinforcement, including new girder-deck shear reinforcement installed with adhesive Surface preparation, environmental protection for painting the pier pile columns down to the water level Construct new drain troughs at all four corners of the bridge Repair erosion gulley on the west headslope Construct settlement mitigation wall Place new topsoil to account for raise in roadway profile Replace bridgerail transitions Remove and dispose of existing guardrail with turn-down ends Install new guardrail with crash-worthy end treatments Replace damaged bridgerail tube on southwest corner of the bridge Apply a Class 2 – Rubbed Surface Finish to the pier caps Apply sealer to curbs and exterior girder fascia Install river identification signs
Go To | 21981 | 1031 | 1 | 2024-01-30 | 6 | 2023-2024 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | SM (Modified) | 12 x 510 SM (Modified) | 11 ¦ 11 ¦ 11 ¦ 11 | 44 | 14.8 | 2020 | 2024-09-30 | 36 | 20 | Vermilion River | At South Boundary of Two Hills | Scope of Work: Traffic accommodation Demolition and disposal of bridge structure – Approach Rail Transition Surface removal Cold milling of existing ACP on the bridge deck and the approach roads Partial depth repair – various elements Concrete crack repair of the deck and approach slabs – gravity fed epoxy Concrete crack repair on various bridge elements – pressure injected epoxy Supply and placement of deck waterproofing and asphalt concrete pavement including material testing Supply and install new approach rail transitions Supply and application of type 3 pigmented concrete sealer Supply and application of type 1C concrete sealer Supply and install new concrete troughs at all corners Headslope erosion repair Miscellaneous repair
Go To | 21893 | 13693 | 2 | 2024-01-31 | 3 | 2023-2024 | Central | Single | Replace Bridge with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 2 x 3360 SPCSP | 38 - 38 | 76 | 3.4 | 2020 | 2024-10-31 | 781 | 2 | Tindastoll Creek | 17 km West of Penhold | Scope of Work: Traffic accommodation Site isolation and water accommodation (Water Management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structure, including guardrail Excavation including supply & placement of geotextile filter fabric Supply and assembly of culvert materials Backfill including backfill material testing Concrete end treatment including concrete testing and small bridge plaque Heavy rock riprap erosion protection including geotextile filter fabric Roadway work Permanent environmental protection devices
Go To | 22039 | 72819 | 1 | 2024-02-01 | 1 | 2023-2024 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | RD | 14 x 610 RD | 15 ¦ 15 ¦ 15 | 45 | 17.1 | 2020 | 2024-09-30 | 11 | 10 | CNR Railway | At Rocky Mountain House | Scope of Work: Traffic accommodation Surface removal and abrasive blasting – bridge deck Cold milling of existing ACP on the approach slabs and approach roads Demolition and disposal of bridge structure – various elements Supply and placement of reinforcing steel and HPC concrete for new deck overlay, curbs, and barriers including material testing Partial depth repair – various elements Supply and install new deck link slabs with all associated materials Supply and install new TL-4 single slope concrete barriers between roadway and multi-use-trail Upgrade west existing bridgerail to TL-4 Double Tube bridgerail Supply and install pressure injected epoxy for crack repair Supply and install new approach slabs at both abutment ends Supply and placement of asphalt concrete pavement including material testing Salvage and re-install approach rail transition c/w posts Salvage and re-install pedestrian handrail and with new rub rail Supply and application of type 3 pigmented and type 1C concrete sealer Supply and install Galvanized Steel Grating and Type ‘C’ Catch Basin Concrete slope protection repair Deck drain extension at pier caps Supply and install bridge plaque Miscellaneous repairs Extra work – various repairs (total force account)
Go To | 22040 | 1569 | 1 | 2024-02-01 | 5 | 2023-2024 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | SC | 11 x 510 SC | 10 ¦ 12 ¦ 10 | 32 | 13.4 | 2020 | 2024-10-15 | 54 | 6 | North Raven River | 14 km West of Spruce View | Scope of Work: Traffic accommodation Surface removal of existing ACP wearing surface and waterproofing membrane Partial depth repairs of curbs and wingwall Supply and install Asphalt concrete pavement and waterproofing membrane Supply and apply Type 3 pigmented sealer on exterior surface of curbs and girders Supply and apply Type 1c sealer on curbs Deck drain removal Supply and install approach rail transition Grouting void under approach slab and cap Erosion repairs Drain trough Miscellaneous repair
Go To | 19213 | 79509 | 2 | 2024-02-07 | 4 | 2023-2024 | Peace | Single | Replace Culvert with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 6470 SPCSP | 76 | 76 | 6.5 | 2020 | 2024-09-30 | 40 | 38 | Ratson Creek | 83 km South of Grande Prairie | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Water Management Removal and Disposal of Existing Culvert Structure Excavation Supply, Assembly and Installation of SPCSP Culvert Material Supply and Install Subdrains Backfill Concrete End Treatments Environmental Compensation Work Class 2 Heavy Rock Riprap Roadway Work Class 1M Rock Ditch Drains Erosion Control Barrier (Straw Rolls) Fish Capture and Release
Go To | 19645 | 6615 | 1 | 2024-02-08 | 3 | 2023-2024 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Rolled Beam | 7 x 910 RB | 27 ¦ 34 ¦ 34 ¦ 34 ¦ 27 | 156 | 14.9 | 2020 | 2025-09-30 | 9 | 6 | Red Deer River | At Drumheller | Scope of Work: Traffic accommodation for bridge and roadway construction Partial and full depth concrete repairs Reconstruction of east bridge combination barrier and deck overhang Reconstruction of west traffic separation barrier Supply and installation of new bridgerail Remove and dispose of ACP on roof slabs Partial demolition of roof slabs Installation of roof slab support system Replace roof slab Filling gullies at abutment head slopes and regrading Remove nominal 40 mm of deck concrete overlay Remove delaminated overlay after micro-milling Full and partial depth concrete repairs on deck, roof slab, sidewalk and abutments Crack sealing on deck Supply and place new HPC concrete overlay on deck and roof slabs Supply and place new polymer overlay on sidewalk Replace deck joints with cover plated v-seal joints Replace barrier cover plates Salvage and reinstall bridge plaques and identification plaques Reconstruction of deck end beams Remove and dispose of existing east deck drains, including localized full depth repairs Construct new bridge street light corbels Place type 1c silane sealer Install new bearing anchor bolt nuts and washers Modify west pedestrian railing Remove gas pipeline from underside of bridge structure Preparation of grading and subgrade Supply and placement of granular base course Cold milling (Micro-milling) Supply and placement of asphalt concrete pavement on roadways Supply and placement of roadway concrete barrier, curb and gutter, swale, and sidewalk Reconstruction of asphalt pathway Remove and reinstall highway / Bridge Lighting Supply and place line painting and permanent highway signing Supply and placement of topsoil and seeding
Go To | 22430 | 77563 | 1 | 2024-02-13 | 3 | 2023-2024 | Southern | Multiple | Remove Bridge | Remove Precast Concrete Girder Bridge | Bridge | Concrete | RD | 11 x 610 RD | 11 ¦ 12 ¦ 11 | 34 | 13.6 | 2020 | 2024-10-15 | 1 | 12 | CPR Railway | 11 km East of Chestermere | Scope of Work: Designing, constructing, operating, maintaining, and removing temporary traffic crossovers between eastbound and westbound traffic on Hwy 1 on either side of the project site Implementing and maintaining environmental controls Cold milling the existing approach roadway surface proximate to the existing bridge structures Removing and salvaging the existing bridge rails from BF77563E-1 and BF77563W-2 Demolishing and disposing of all other components for two (2) existing bridge structures, including but not limited to the wearing surface, girders, abutments, approach slabs, slope protection, pier caps, pier columns and piles Carrying out lead abatement during the removal of the existing painted pier columns Sampling and testing existing soils within the former Canadian Pacific Railway (CPR) right-of-way and potentially removing and disposing of contaminated soils Removing and disposing of sections of the existing guardrail systems, including all median guardrails and portions of the exterior guardrails proximate to the existing bridge structures Grading and backfilling the former CPR right-of-way to construct embankments to match the existing roadway embankments, including supply of borrow material Supplying, installing, and compacting granular base course and asphalt concrete pavement over the former bridge locations Reconnecting the existing outside shoulder w-beam and high-tension cable barriers (HTCB) through the project site with new guardrail materials Supplying and placing topsoil and broadcast seeding the new embankment slopes Supplying and installing permanent erosion control devices (silt fences and soil coverings) on the new embankment slopes
Go To | 22430 | 77563 | 2 | 2024-02-13 | 3 | 2023-2024 | Southern | Multiple | Remove Bridge | Remove Precast Concrete Girder Bridge | Bridge | Concrete | RD | 11 x 610 RD | 11 ¦ 12 ¦ 11 | 34 | 13.6 | 2020 | 2024-10-15 | 1 | 12 | CPR Railway | 11 km East of Chestermere | Scope of Work: Designing, constructing, operating, maintaining, and removing temporary traffic crossovers between eastbound and westbound traffic on Hwy 1 on either side of the project site Implementing and maintaining environmental controls Cold milling the existing approach roadway surface proximate to the existing bridge structures Removing and salvaging the existing bridge rails from BF77563E-1 and BF77563W-2 Demolishing and disposing of all other components for two (2) existing bridge structures, including but not limited to the wearing surface, girders, abutments, approach slabs, slope protection, pier caps, pier columns and piles Carrying out lead abatement during the removal of the existing painted pier columns Sampling and testing existing soils within the former Canadian Pacific Railway (CPR) right-of-way and potentially removing and disposing of contaminated soils Removing and disposing of sections of the existing guardrail systems, including all median guardrails and portions of the exterior guardrails proximate to the existing bridge structures Grading and backfilling the former CPR right-of-way to construct embankments to match the existing roadway embankments, including supply of borrow material Supplying, installing, and compacting granular base course and asphalt concrete pavement over the former bridge locations Reconnecting the existing outside shoulder w-beam and high-tension cable barriers (HTCB) through the project site with new guardrail materials Supplying and placing topsoil and broadcast seeding the new embankment slopes Supplying and installing permanent erosion control devices (silt fences and soil coverings) on the new embankment slopes
Go To | 23535 | Multiple | - | 2024-02-13 | 4 | 2023-2024 | Southern | Highway | New Sign Structures | Construct Sign Structures | Sign Structure | - | - | - | - | - | - | 2020 | 2025-10-01 | - | - | - | Deerfoot Trail | Scope of Work: Overhead sign structures including removal and disposal, supply and install, modifications, and related works
Go To | 19214 | 9276 | 2 | 2024-02-14 | 7 | 2023-2024 | Peace | Single | Replace Culvert with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 3990 SPCSP | 41 | 41 | 4 | 2020 | 2024-09-30 | 674 | 2 | Tributary to Kleskun Creek | 24 km East of Teepee Creek | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Removal and Disposal of Existing Culvert Structure Excavation Supply, Assembly and Installation of SPCSP Culvert Material Backfill Concrete End Treatment Class 1 Heavy Rock Riprap Roadway Work Class 1M Rock Ditch Drains Erosion Control Barrier (Straw Rolls) Erosion Control Soil Covering (Type C) Fish Capture and Release
Go To | 22727 | 75369 | 2 | 2024-02-27 | 4 | 2023-2024 | Central | Single | Replace Culvert with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 2 x 4300 SPCSP | 94 - 94 | 188 | 4.3 | 2020 | 2024-10-15 | 2 | 30 | Pipestone Creek | Near Millet | Scope of Work: Traffic accommodation Site isolation and water accommodation (Water Management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structure Excavation including supply & placement of geotextile filter fabric Supply and assembly of culvert materials Backfill including backfill material testing Concrete end treatment including concrete testing and small bridge plaque Heavy rock riprap erosion protection including geotextile filter fabric Roadway work Removal, disposal, and reinstallation of high tension cable barriers Permanent environmental protection devices
Go To | 21582 | 84165 | 1 | 2024-02-28 | 3 | 2023-2024 | Southern | Combined | New Wildlife Bridge | Construct SLC Precast Concrete Girder Bridge | Wildlife Bridge | Concrete | SLC | 12 x 510 SLC | 16 | 16 | 14.8 | 2020 | 2024-10-31 | 3 | 4 | Wildlife Trail | 5 km West of Lundbreck | Scope of Work: Traffic accommodation Construction, maintenance and removal of a temporary detour Construction of single-span SLC precast concrete girder bridge on cast-in-place concrete abutments, supported by driven steel H-piles Installation of bridgerail Removal of existing guardrail and installation of new guardrail system Construction of wildlife mitigation fencing and associated features such as guards (“Texas gates”) and jump-outs Installation of asphalt concrete pavement Topsoil placement and hydroseeding of wildlife underpass and fencing areas Supply and installation of specified trees
Go To | 21915 | 7765 | 2 | 2024-03-05 | 5 | 2023-2024 | Central | Single | Replace Bridge with Bridge | Construct SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 9 x 510 SLW | 10 ¦ 14 ¦10 | 34 | 11.1 | 2020 | 2024-10-31 | 570 | 2 | Berry Creek | 65 km Southeast of Hanna | Scope of Work: Traffic accommodation for bridge construction Site isolation and water accommodation (Water Management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structure, including guardrail Excavation Supply, set-up and drilled steel H-piling Abutment construction Pier construction Heavy rock riprap erosion protection including geotextile filter fabric Supply, delivery, and erection of concrete girders Approach slab construction Deck waterproofing and asphalt concrete pavement including material testing Miscellaneous iron Roadway work Supply and installation of bridgerail and guardrail Permanent environmental protection devices
Go To | 20595 | 1710 | 2 | 2024-03-07 | 5 | 2023-2024 | Central | Single | Replace Culvert with Culvert | Construct SWSP Culvert | Culvert | Steel | SWSP | 1 x 1200 SWSP | 41 | 41 | 1.2 | 2020 | 2024-10-15 | 42 | 8 | Tributary to Threehills Creek | 15 km East of Penhold | Scope of Work: Traffic Accommodation for Bridge Construction Monitoring and deterring swallow nests prior to construction Total Suspended Solids (TSS) Testing Fish capture and release Care of all Utilities and related infrastructure Care of water and environmental management Excavation (Structural & Channel) Demolition and removal of existing culvert bevel ends Backfill (Clay Seals) Grouting of the existing culverts Supply & Installation of New, 1.2 m diameter x 41.3 m long, Smooth Wall Steel Pipe (SWSP) via tunneled installation Heavy Rock Riprap – Class 1 Erosion and sediment control measures (temporary and permanent) Removal of existing fence Installation and maintenance of temporary, Class A, fencing Installation of new Class C fence Sideslope Improvements Clearing, Topsoiling, and Seeding
Go To | 21875 | 9173 | 1 | 2024-03-08 | 6 | 2023-2024 | Central | Single | Bridge Rehabilitation | Replace Superstructure SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW (Modified) | 8 x 510 SLW (Modified) | 8 ¦ 10 ¦ 8 | 26 | 10 | 2020 | 2024-10-15 | 562 | 2 | Empress Creek | 2 km North of Empress | Scope of Work: Traffic accommodation Demolition and disposal of bridge girders Deck and approach slabs waterproofing and asphalt concrete pavement installation including painting of roadway markings Approach road asphalt concrete pavement installation including painting of roadway markings Supply and place approach slab concrete (Class C) Supply and place corrosion resistant reinforcing steel on approach slabs Supply, delivery, and erection of modified type SLW 510 precast concrete girders Supply and apply Type 1c sealer to bridge abutments and pier caps Supply and Fabrication, Delivery and Installation bridgerail including approach rail transitions Supply and install guardrail including end treatments Partial depth repairs of pier caps and abutments Surface preparation and painting on pier pipes & braces Erosion damage repairs Supply and install miscellaneous irons Rock drain trough installation
Go To | 42 | 8098 | 2 | 2024-03-14 | 5 | 2023-2024 | Central | Single | Replace Culvert with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 2700 SPCSP | 44 | 44 | 2.7 | 2020 | 2024-10-15 | 752 | 4 | Tributary to North Saskatchewan River | Near Rocky Mountain House | Scope of Work: Traffic accommodation for culvert construction (including a local road detour), local closure of Hwy 752 Clearing swallow nests, monitoring and deterring swallow nests and further nesting activities Site Isolation and water accommodation Total suspended solids (TSS) testing Fish capture and release Excavation (structural and channel) Demolition and disposal of existing culvert structure Water main and associated work Sanitary sewer and associated work Care of all utilities and related infrastructure Backfill (grade separation contour) Construction of new single 2.7 m diameter, 44.0 m long SPCSP, and associated work Heavy rock riprap – Class 1 and Class 1M Care of water and environmental management Installation of wood permanent fence Erosion and sediment control Roadway and pathway work
Go To | 22984 | 77759 | 2 | 2024-03-14 | 5 | 2023-2024 | Peace | Highway | Replace Culvert with Culvert | Construct WSP Culvert | Culvert | Steel | WSP | 1 x 1830 WSP | 32 | 32 | 1.8 | 2020 | 2024-10-15 | 733 | 4 | Pinto Creek | Near Wanham | Scope of Work: Care of Water Turbidity Monitoring and Testing Grouting and Abandonment of the existing culvert Structural excavation Supply and installation of a WSP culvert Granular and clay backfill Roadway work Supply and installation of rock riprap Permanent erosion control devices
Go To | 22842 | 733 | 2 | 2024-03-19 | 3 | 2023-2024 | North Central | Single | Replace Culvert with Culvert | Construct WSP Culvert | Culvert | Steel | WSP | 1 x 3050 WSP | 45 | 45 | 3 | 2020 | 2025-02-28 | 28A | 1 | Tributary to North Saskatchewan River | 12 km West of Fort Saskatchewan | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Silt, Debris and Ice Removal Excavation – Structural Grouting and Abandonment of the Existing Culvert Supply and Install WSP Culvert using Trenchless Methods Backfill Roadway Work Supply and Install Class 1 Heavy Rock Riprap Supply and Install Class 1M Heavy Rock Riprap Ditch Drains Supply and Install Erosion Control Barriers Supply and Install Erosion Control Soil Coverings
Go To | 23921 | 70277 | 1 | 2024-03-22 | 4 | 2023-2024 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | FC | 6 x 1140 FC | 32 ¦ 32 ¦ 32 ¦ 14 | 110 | 10.4 | 2020 | 2024-10-15 | 22 | 22 | Clearwater River | 16 km Southeast of Rocky Mountain House | Scope of Work: Traffic accommodation Demolition and disposal of bridge structure – W-Beam transition rail, concrete drain troughs, and existing deck joints Surface removal – approach slabs Cold milling of existing ACP on the approach roads Grout void under approach slabs Supply, fabrication, delivery and installation of deck joint assemblies – Type 1 strip seal Partial depth repair – various elements Supply and install pressure injected epoxy for crack repair Supply and placement of chip seal on concrete deck Supply and placement of asphalt concrete pavement including material testing Supply and install approach rail transition Supply and install concrete drain trough collectors Erosion repairs at abutments and nearby culvert Supply and install Class 1M riprap erosion protection Supply and application of type 3 pigmented concrete sealer Supply and application of type 1C concrete sealer Drift removal Miscellaneous repairs
Go To | 18144 | 78643 | 2 | 2024-03-26 | 2 | 2023-2024 | Peace | Single | New and Lined Culverts | Construct SWSP Culvert - Spray Line SPCSP Culvert | Culvert | Steel | SWSP - Spray Line SPCSP | 1 x 3000 SWSP - 1 x 1800 Spray Lined SPCSP | 93 - 90 | 183 | 2.4 | 2020 | 2024-11-15 | 33 | 14 | Jerry Creek | Near Kinuso | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Monitoring/Testing Fish Capture and Release Site Isolation/Water Management Clearing and Mulching Excavation Structural & Channel Excavation Supply & Installation of Welded Steel Pipe culvert Backfill (Non-Granular) Heavy Rock Riprap (Class 1, Substrate) Heavy Rock Riprap (Class 2) Supply and Installation of Steel Substrate Holders Supply and Installation of Boulders (Class 3 Heavy Rock Riprap) Culvert Lining (Geopolymer) Supply and Installation of Strong Post W-Beam Guardrail Roadway Work Erosion Control Barrier (Silt Fence) Erosion Control Soil Covering Willow Staking Brush Layering Tree Planting
Go To | 20345 | 76533 | 2 | 2024-04-24 | 3 | 2024-2025 | Central | Single | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 1600 CSP | 31 | 31 | 1.6 | 2020 | 2024-10-15 | 857 | 4 | Tributary to Vermilion River | 2 km North of Vegreville | Scope of Work: Traffic Accommodation for Bridge Construction Pre-disturbance Wildlife Sweeps Topsoil Stripping and Stockpiling Remove and Dispose Asphalt Surfacing Removal and Disposal Concrete Curb and Gutter Common Excavation Remove and Dispose of Existing CSP Culvert Structural Excavation Supply and Install 1600 mm diameter CSP Culvert Granular Backfill (Des 2 Class 25) Non-Granular Backfill Roadway Work including Line Painting Supply and Installation of Woven and Non-woven Geotextiles Supply and Installation of Heavy Rock Riprap (Class 1) Supply and Installation of Erosion Fence Barriers (Straw Rolls) Supply and Installation of Erosion Control Soil Covering (Type B) Roadway Embankment Re-grading Site Restoration Turbidity Monitoring, if required Fish Capture and Release, if required
Go To | 22587 | 76848 | 2 | 2024-05-01 | 2 | 2024-2025 | Southern | Single | Bridge Repair | Bridge High Load Damage Repair | Bridge | Steel | Welded Girder | 5 x 1900 WG | 46 ¦ 50 | 96 | 15.1 | 2020 | 2024-12-01 | 567 | 5 | Highway 2 | At North Boundary of Airdrie | Scope of Work: Traffic accommodation Non-destructive testing Heat straightening of damaged girder Removal of damaged intermediate diaphragms Provision of new intermediate diaphragms Modification and reinforcement of damaged girder near point of impact Specialized engineering services
Go To | 22081 | 77520 | 2 | 2024-05-02 | 4 | 2024-2025 | Southern | Single | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 2100 CSP | 30 | 30 | 2.1 | 2020 | 2024-10-31 | 515 | 2 | 2nd Order Tributary to Mackay Creek | 43 km Southeast of Irvine | Scope of Work: Temporary detour construction and removal, including a temporary creek crossing Fish capture and release (as required) Total Suspended Solids (TSS) Testing (as required) Demolition and disposal of existing 1.12 x 1.83 m pipe arch Culvert structure Structural and channel excavation Backfill Construction of new 30 m long 2.1 m diameter CSP culvert on a new creek alignment Installation of heavy rock riprap (class 1) Care of wetlands and environmental management Roadway work Temporary and permanent fencing
Go To | 21534 | 721 | 2 | 2024-05-28 | 2 | 2024-2025 | Central | Single | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 2 x 2100 CSP | 46 - 46 | 92 | 2.1 | 2020 | 2024-10-15 | 581 | 2 | Sheep Coulee | 4 km East of Carstairs | Scope of Work: Traffic accommodation for bridge construction Site isolation and water accommodation Total Suspended Solid (TSS) testing Fish capture, salvage, and release Structural excavation Removal and disposal of existing Corrugated Steel Pipe (CSP) culvert Supply, assembly, and installation of a Corrugated Steel Pipe (CSP) culvert Granular backfill and non-granular backfill including supply and placement of geotextile filter fabric Heavy rock riprap including supply and placement of geotextile filter fabric Roadway Work Supply and installation of erosion and sediment control devices
Go To | 21917 | 7892 | 2 | 2024-05-30 | 6 | 2024-2025 | Central | Single | Replace Bridge with Bridge | Construct SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 9 x 510 SLW | 10 ¦ 10 ¦ 10 | 30 | 11.1 | 2020 | 2024-10-31 | 886 | 8 | Monitor Creek | 15 km South of Consort | Scope of Work: Traffic accommodation for bridge construction Site isolation and water accommodation (Water Management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structure, including guardrail Removal and disposal of water gauge station Excavation Supply, set-up and drive steel H-piling Supply and placement of reinforcing steel Abutment Construction Pier Construction Heavy rock riprap erosion protection including geotextile filter fabric Supply, delivery, and erection of concrete girders Approach Slab Construction Roadway work Deck waterproofing and asphalt concrete pavement including material testing Miscellaneous iron Supply and installation of bridgerail and guardrail Permanent environmental protection devices
Go To | 20709 | 248 | 2 | 2024-06-06 | 4 | 2024-2025 | Southern | Single | Replace Bridge with Culvert | Construct DCSP Arch Culvert | Culvert | Steel | DCSP Arch | 1 x 7000 DCSP Arch | 28 | 28 | 7 | 2020 | 2024-10-31 | 22 | 6 | Wildcat Creek | 18 km North of Lundbreck | Scope of Work: Traffic accommodation Construction, maintenance and removal of a temporary detour Site isolation/water accommodation Care of water Removal and disposal of existing bridge structure Removal and disposal of existing wearing surface Removal and disposal of existing guardrail Structure excavation Channel excavation Supply and H-pile installation Cast-in-place concrete footings (including mudslab) supported on driven steel H-piles Supply, installation of Deep Corrugated Steel Plate (DCSP) open bottom culvert, galvanized steel head walls and wing walls Structural backfill Granular backfill Installation of new riprap (Class 2) (including substrate material and geotextile filter fabric) Installation of new asphalt concrete pavement Water and environmental management, monitoring, and testing Roadway work (including pavement line marking)
Go To | 24340 | 81157 | 1 | 2024-06-14 | 5 | 2024-2025 | North Central | Single | Bridge Repair | Bridge High Load Damage Repair | Bridge | Concrete | Bulb-T (Modified) | 9 x 1700 Bulb-T (Modified) | 29 ¦ 37 ¦ 37 ¦ 29 | 132 | 17.6 | 2020 | 2025-02-28 | 628 | 4 | Highway 216 | At East Boundary of Edmonton | Scope of Work: Initial Construction Setup Stage 1 Repairs – Deck and Top Flange, Girder Webs, and Prestressing Stage 2 Repairs – Preloading and Crack Repair Stage 3 Repairs – Girder Bottom Flanges, Web Jackets, and Post Tensioning Miscellaneous Activities
Go To | 20098 | 74661 | 1 | 2024-06-18 | 4 | 2024-2025 | Southern | Single | Culvert Extension | Extend Cast-in-Place Concrete Box Culvert | Culvert | Concrete | CIP Box | 1 x 6100 CIP Box | 61 | 61 | 6.1 | 2020 | 2025-10-31 | 1 | 2 | Tributary to Bow River | 2 km South of Exshaw | Scope of Work: Traffic accommodation Care of water Fish capture and release Turbidity Monitoring Excavation and backfill Demolition and disposal of existing culvert elements and bridge girders Steel H-pile installation including PDA testing Pile cap construction and existing wingwall modifications Partial depth repairs to concrete culvert walls and roof Supply and fabrication, delivery and erection of precast girders Heavy Rock Riprap (Class 2) Permanent Erosion Control Devices (Silt Fence & Soil Covering) Roadway Work
Go To | 21132 | 76415 | 2 | 2024-06-20 | 2 | 2024-2025 | Peace | Single | Replace Bridge with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 2900 CSP | 42 | 42 | 2.9 | 2020 | 2024-10-31 | 2 | 52 | Mud Creek | 2 km East of Enilda | Scope of Work: Traffic Accommodation Demolition and Disposal of Bridge Structure Structural Excavation Supply of CSP Culvert with Couplers Backfill Concrete End Treatment Roadway Work Supply and Placement of Class 1 Heavy Rock Riprap Supply and Installation of Erosion Control Barrier (Silt Fence) Supply and Installation of Erosion Control Barrier (Straw Fibre Roll) Supply and Installation of Erosion Control Matting (Type C) Fish Capture and Release Turbidity Monitoring
Go To | 22184 | 74031 | 1 | 2024-06-26 | 5 | 2024-2025 | Southern | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Welded Girder | 7 x 1200 WG | 32 ¦ 38 ¦ 38 ¦ 32 | 140 | 14 | 2020 | 2025-10-31 | 2 | 12 | Sheep River | 7 km North of Aldersyde | Scope of Work: Traffic accommodation Care of birds Surface removal Partial depth concrete repairs Abutment bearing stainless steel replacements Galvanic corrosion protection Deck joint replacements Deck waterproofing and paving Removal and disposal of existing guardrail New guardrail installation (including end treatments) New approach guardrail transitions Girder end painting (surface preparation and painting and protection of the environment) Concrete cleaning and sealing Concrete drain trough collector replacements CSE Ground Connections Transition approach paving Roadside ditch modifications Painted roadway markings
Go To | 23067 | 9179 | 1 | 2024-07-09 | 4 | 2024-2025 | Central | Multiple | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Through Truss | Through Truss | 61 ¦ 76 ¦ 61 | 198 | 7.3 | 2020 | 2025-10-15 | 884 | 4 | Red Deer River | 10 km North of Jenner | Scope of Work: Traffic Accommodation Approach Rail Repairs Bridge Rail Repairs Timber Strip Deck Repairs Heat Straighten Steel Truss Members Replacement of Steel Truss Members Miscellaneous Repairs
Go To | 23067 | 13170 | 1 | 2024-07-09 | 4 | 2024-2025 | Central | Multiple | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Through Truss | Through Truss | 9 ¦ 61 ¦ 61 ¦ 61 ¦ 61 ¦ 9 | 262 | 5.8 | 2020 | 2025-10-15 | 886 | 2 | Red Deer River | 5 km North of Buffalo | Scope of Work: Traffic Accommodation Approach Rail Repairs Bridge Rail Repairs Timber Strip Deck Repairs Replacement of Steel Truss Members Floor Beam Strengthening Bearings – Supply and Fabrication, Delivery and Installation Concrete Crack Repairs Partial Depth Concrete Repairs Miscellaneous Repairs
Go To | 21891 | 75962 | 2 | 2024-07-11 | 6 | 2024-2025 | Central | Single | Replace Culvert with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 12 x 510 SLC | 12 ¦ 14 ¦ 12 | 38 | 14.8 | 2020 | 2025-10-15 | 11 | 4 | Tributary to North Saskatchewan River | 39 km Southwest of Nordegg | Scope of Work: Traffic accommodation for bridge construction Site isolation and water accommodation (Water Management) Total suspended solids (TSS) testing Demolition and disposal of existing bridge structure, including guardrail Excavation including haul of excess material Supply, set-up, and drilled steel H-piling Supply, set-up, and drive steel H-piling Supply and install pier pile bracing Supply and placement of reinforcing steel for substructure and superstructure Supply and placement of concrete for substructure and superstructure including material testing Heavy rock riprap erosion protection including geotextile filter fabric Supply, delivery, and erection of concrete girders Deck waterproofing and asphalt concrete pavement including material testing Miscellaneous iron Roadway work Supply and installation of bridgerail and guardrail Permanent environmental protection devices
Go To | 23808 | 75540 | 2 | 2024-07-19 | 3 | 2024-2025 | Central | Single | Replace Bridge with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 3 x 1800 CSP | 32 - 32 - 32 | 96 | 1.8 | 2020 | 2024-10-31 | 41 | 10 | Kennedy Coulee | 1 km Southwest of Acadia Valley | Scope of Work: Traffic accommodation Site isolation and water accommodation (Water Management) Demolition and disposal of existing bridge structure, including guardrail Excavation including supply & placement of geotextile filter fabric Supply and assembly of culvert materials including bridge identification tag Backfill including clay seals and backfill material testing Heavy rock riprap erosion protection including geotextile filter fabric Roadway work Removal and haul of detour bridge Removal of detour road and site restoration Permanent environmental protection devices
Go To | 22126 | 76979 | 2 | 2024-08-28 | 4 | 2024-2025 | Southern | Single | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 2 x 1400 CSP | 27 - 27 | 54 | 1.4 | 2020 | 2024-10-31 | 514 | 2 | Gros Ventre Creek | 42 km South of Irvine | Scope of Work: Traffic Accommodation Water management Demolition and disposal of existing bridge culvert structure Excavation Backfill Installation of new culvert structure Class 1 heavy rock riprap Erosion and sediment control Topsoil and seeding Roadway work
Go To | 22021 | 1980 | 1 | 2024-09-05 | 2 | 2024-2025 | Central | Highway | Bridge Maintenance | Replace Bridge Approach Slabs | Bridge | Concrete | Type-O | 7 x 1550 Type-O | 31 ¦ 31 ¦ 31 ¦ 31 | 124 | 12.2 | 2020 | 2025-11-01 | 27 | 6 | Red Deer River | At Sundre | Scope of Work: Traffic accommodation Temporary detour construction and site reclamation Obliteration of existing roadways Grading Storm sewer, manholes, catch basins and related work Valve and manhole adjustments Subgrade preparation Granular base course Cold milling Asphalt concrete pavement Concrete curbs, swales, sidewalks, aprons, gutters, and islands Handrail, guardrail, energy attenuator systems and guideposts Permanent erosion control measures Line painting and permanent highway signing Highway street lighting Traffic signals Bridge approach slab reconstruction Topsoil placement and seeding Structure demolition Tree clearing
Go To | 23103 | 70872 | 2 | 2024-09-05 | 2 | 2024-2025 | North Central | Single | New and Lined Culverts | Construct WSP Culvert - Install WSP Culvert Liner | Culvert | Steel | WSP - WSP Liner | 1 x 2430 WSP - 1 x 1220 WSP Liner | 143 - 136 | 279 | 1.8 | 2020 | 2025-10-15 | 16 | 4 | Rooster Creek | 31 km Northeast of Hinton | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Fish Capture and Release Water Management Silt, Debris and Ice Removal Excavation – Structural Shoring and Boring Pit Preparation Supply and Installation of a Welded Steel Pipe (WSP) Liner Class S Modified Concrete Supply and Installation of Welded Steel Pipe (WSP) Culvert using Trenchless Methods Supply and Install Pipe Substrate and Substrate Holders Backfill Roadway Work Supply and Install Class 1 Heavy Rock Riprap Supply and Install Class 1M Heavy Rock Riprap Ditch Drains Supply and Install Erosion Control Barriers Supply and Install Erosion Control Soil Coverings Supply and Install Environmental Compensation
Go To | 22337 | 76641 | 2 | 2024-09-19 | 4 | 2024-2025 | Peace | Single | Replace Bridge with Culvert | Construct SWSP Culvert | Culvert | Steel | SWSP | 1 x 2130 SWSP | 146 | 146 | 2.1 | 2020 | 2025-03-14 | 33 | 14 | Tributary to Swan River | 43 km Northeast of Swan Hills | Scope of Work: Traffic accommodation Total suspended solids (TSS) testing Site isolation and water accommodation (Care of Water) Fish capture and release Grouting and abandonment of existing culvert Supply and installation of Smooth Wall Steel Pipe (SWSP) by trenchless method Supply and installation of substrate holders and Class 1M heavy rock substrate Channel excavation Backfill including backfill material testing Channel restoration Culvert embankment and berm construction Supply and placement of Class 1 heavy rock riprap including geotextile filter fabric Willow plantings Remove and dispose of existing guardrail Supply and installation of strong post W-Beam guardrail with crashworthy end terminals Clearing, topsoil and seeding Erosion and sediment control
Go To | 22124 | 6780 | 3 | 2024-09-24 | 5 | 2024-2025 | Southern | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 11 x 510 SLC | 12 ¦ 14 ¦ 12 | 38 | 13.5 | 2020 | 2025-06-30 | 3 | 10 | SMRID Canal | Near Coaldale | Scope of Work: Traffic Accommodation Demolition and disposal of existing bridge structure Excavation Backfill Steel piling Reinforcing steel Construction of abutments and piers Supply and erection of 12m and 14m span precast concrete girders Construction of deck and approach slabs Waterproofing and paving Bridgerail and approach transition rail Guardrail Class 1 heavy rock riprap Seeding Erosion and sediment control Roadway work
Go To | 19889 | 75195 | 1 | 2024-10-16 | 2 | 2024-2025 | North Central | Multiple | Bridge Rehabilitation | Replace Superstructure Welded Steel Girder Bridge | Bridge | Steel | Welded Girder | 8 x 600 WG | 14 ¦ 24 ¦ 17 | 55 | 13.4 | 2020 | 2026-08-31 | 16 | 12 | Highway 43 | 2 km North of Carvel | Scope of Work: Environmental management and care of birds Traffic accommodation Surveying Temporary median crossover detours Supply, install and maintain crash worthy barriers Removal and disposal of bridge components New concrete abutments on existing abutment piles Existing piers strengthening/modifications New Type WG steel girders New reinforced concrete decks New approach slabs and sleeper slabs New high performance waterproofing system (bridge decks and approach slabs) Hwy 16 profile modifications (ACP milling and repaving) Hwy 43 ACP re-profiling (ACP milling and re-paving) New TL-4 bridgerail (including TL-4 approach guardrail transitions) Existing Hwy 16 guardrails removal, modification and reinstallation Existing Hwy 43 guardrails removal, modification and reinstallation New guardrails Ditch Re-grading, Slope Improvements and Erosion Repair New concrete drain troughs and take-offs New concrete head slope protection Concrete cleaning and sealing (abutments, piers, curbs, etc.) CSP culverts supply and installation (open cut) SWSP culverts supply and installation (boring) Culverts fill and cap Painted roadway markings Median crossover removal Erosion Control Topsoil, seeding and harrowing
Go To | 19889 | 75195 | 2 | 2024-10-16 | 2 | 2024-2025 | North Central | Multiple | Bridge Rehabilitation | Replace Superstructure Welded Steel Girder Bridge | Bridge | Steel | Welded Girder | 8 x 600 WG | 14 ¦ 24 ¦ 17 | 55 | 13.4 | 2020 | 2026-08-31 | 16 | 12 | Highway 43 | 2 km North of Carvel | Scope of Work: Environmental management and care of birds Traffic accommodation Surveying Temporary median crossover detours Supply, install and maintain crash worthy barriers Removal and disposal of bridge components New concrete abutments on existing abutment piles Existing piers strengthening/modifications New Type WG steel girders New reinforced concrete decks New approach slabs and sleeper slabs New high performance waterproofing system (bridge decks and approach slabs) Hwy 16 profile modifications (ACP milling and repaving) Hwy 43 ACP re-profiling (ACP milling and re-paving) New TL-4 bridgerail (including TL-4 approach guardrail transitions) Existing Hwy 16 guardrails removal, modification and reinstallation Existing Hwy 43 guardrails removal, modification and reinstallation New guardrails Ditch Re-grading, Slope Improvements and Erosion Repair New concrete drain troughs and take-offs New concrete head slope protection Concrete cleaning and sealing (abutments, piers, curbs, etc.) CSP culverts supply and installation (open cut) SWSP culverts supply and installation (boring) Culverts fill and cap Painted roadway markings Median crossover removal Erosion Control Topsoil, seeding and harrowing
Go To | 22843 | 73852 | 2 | 2024-11-28 | 8 | 2024-2025 | North Central | Single | Replace Culvert with Culvert | Construct WSP Culvert | Culvert | Steel | WSP | 1 x 2130 WSP | 78 | 78 | 2.1 | 2020 | 2025-10-01 | 43 | 22 | Tributary to Kilini Creek | 8 km Southwest of Onoway | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Silt, Debris and Ice Removal Excavation – Structural Grouting and Abandonment of the Existing Culvert Supply and Install WSP Culvert using Trenchless Methods Backfill Roadway Work Supply and Install Class 1 Heavy Rock Riprap Supply and Install Class 1M Heavy Rock Riprap Ditch Drains Supply and Install Erosion Control Barriers Supply and Install Erosion Control Soil Coverings
Go To | 24780 | 8519 | 2 | 2024-12-06 | 5 | 2024-2025 | Peace | Single | New and Lined Culverts | Construct SWSP Culvert - Install SWSP Culvert Liner | Culvert | Steel | SWSP - SWSP Liner | 1 x 3050 SWSP - 1 x 2440 SWSP Liner | 47 - 43 | 90 | 2.8 | 2020 | 2025-06-30 | 59 | 2 | Niobe Creek | Near Sexsmith | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Monitoring/Testing Fish Capture and Release Site Isolation/Water Management Clearing and Mulching Excavation Supply & Installation of Welded Steel Pipe Culvert Backfill Heavy Rock Riprap (Class 1) Culvert Lining and Grouting Roadway Work Class “B” Fence Supply and Installation of Strong Post W-Beam Guardrail Erosion Control Barrier (Straw Rolls and Silt Fence) Erosion Control Soil Covering (Type “C”)
Go To | 24012 | 72633 | 2 | 2025-01-16 | 9 | 2024-2025 | Central | Combined | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | SCC | 11 x 510 SCC | 14 | 14 | 13.4 | 2020 | 2025-10-15 | 2A | 16 | Waskasoo Creek | 7 km North of Penhold | Scope of Work: Pre-disturbance wildlife sweeps Asphalt milling and paving Concrete repairs Approach guardrail modifications Fill voids below abutments Place additional riprap
Go To | 23517 | 76089 | 2 | 2025-01-29 | 5 | 2024-2025 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | SCC | 12 x 510 SCC | 12 | 12 | 14.8 | 2020 | 2025-10-01 | 11 | 2 | Tributary to North Saskatchewan River | 82 km Southwest of Nordegg | Scope of Work: Traffic accommodation Concrete surface removal – deck and approach slabs Cold milling asphalt pavement – roadway approaches Removal, storage and reinstallation of bridgerail Removal, storage and reinstallation of approach rail transitions Removal, salvage or disposal, and reinstallation of approach guardrails Supply and install new impact attenuators Concrete demolition and disposal, including exterior girders and parts of the deck slab, end diaphragms, corbels and approach slabs Supply, fabrication, delivery and erection of new SLC510 precast concrete curb girders HPC concrete Jacking of approach slabs Waterproofing Asphalt concrete pavement Roadway markings New signage
Go To | 21131 | 74853 | 2 | 2025-02-04 | 6 | 2024-2025 | Peace | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 9 x 510 SLC | 16 | 16 | 11.1 | 2020 | 2025-10-31 | 697 | 4 | Teepee Creek | Near La Crete | Scope of Work: Traffic Accommodation Demolition and Disposal of Bridge Structure Headslope Preparation and Backfill Supply, Set-Up and Drive Steel H-Piling Supply and Placement of Reinforcing Steel (Plain, Corrosion Resistant and Stainless) Supply and Placement of Class C Concrete Supply, Delivery and Erection of Prestressed SLC-510 Interior and Exterior Curbs (16 m long) Supply and Placement of Reinforced Class HPC Concrete Bridge Deck and Approach Slabs Deck Waterproofing Roadway Work Supply and Placement of Class 1 Heavy Rock Riprap Bridgerail and Guardrail Installation Supply and Installation of Erosion Control Barrier (Silt Fence) Supply and Installation of Erosion Control Barrier (Straw Fibre Roll) Supply and Installation of Erosion Control Matting (Type C) Fish Capture and Release
Go To | 22685 | 2401 | 1 | 2025-02-21 | 7 | 2024-2025 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | Type-O | 4 x 1520 Type-O | 24 ¦ 24 | 48 | 9.5 | 2020 | 2025-10-15 | 893 | 4 | Vermilion River | 6 km North of Islay | Scope of Work: Clearing cliff swallow nests outside of the nesting period and providing deterrent to further nesting activities Traffic accommodation for bridge construction Install temporary access for under bridge work at pier Partial depth repairs on pier faces Install new Pier Modifications Clean and apply class 2 surface finish to pier faces and pier modifications Replace pier bearings and refurbish existing girder shoe plates Remove existing deck joints at pier and abutments Supply and install new type 1 strip seal joints at pier and abutments Partial depth repair of delaminations on deck and overlay Partial depth repairs on abutment backwalls, curtainwalls and seats Refurbish all abutment bearings Remove deck drains and full depth repair removal areas Partial depth repairs on deck soffit and deck undersides Repair erosion gullies Construct new heavy rock riprap drain troughs (4 total)
Go To | 21768 | 75700 | 2 | 2025-02-25 | 7 | 2024-2025 | Peace | Single | New and Lined Culverts | Construct WSP/CSP Culvert - Install SPCSP Culvert Liner | Culvert | Steel | WSP ¦ CSP - SPCSP Liner | 1 x 2430 WSP ¦ 2700 CSP - 1 x 3360 SPCSP Liner - 1 x 3050 SPCSP Liner | 90 ¦ 51 - 83 - 82 | 306 | 2.9 | 2020 | 2026-10-15 | 733 | 4 | Bad Heart River | 23 km South of Wanham | Scope of Work: Traffic Accommodation Turbidity Monitoring Water Management Silt, Concrete Floor, Debris and Ice Removal Excavation Channel Excavation Shoring and Boring Pit Preparation Supply and Installation of Welded Steel Pipe (WSP) Culvert using Trenchless Methods Supply and Install 2700 mm CSP Extensions Supply and Install 3050 mm SPCSP Culvert Liner Supply and Install 3360 mm SPCSP Culvert Liner Concrete – Class S Modified Concrete – Class S Concrete End Treatment Backfill Roadway Work Supply and Install Class 3 Heavy Rock Riprap Supply and Install Class 2 Heavy Rock Riprap Supply and Install Class 1M Heavy Rock Riprap Ditch Drains Supply and Install Erosion Control Barriers Drift Removal Drift Catcher – Berm Construction Drift Catcher Repairs – Weld Repairs
Go To | 22809 | 70063 | 1 | 2025-02-27 | 6 | 2024-2025 | North Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | CIP Frame | 1 x 1220 CIP Frame | 22 | 22 | 18.6 | 2020 | 2025-10-01 | 2 | 32 | Blackmud Creek | 5 km North of Nisku | Scope of Work: Traffic accommodation Demolition and disposal of bridge structure – bridge curbs, bridgerail, wingwalls, and guardrail Surface removal of ACP wearing surface on top of the bridge – average thickness 250 mm Cold milling of existing ACP on the approach roads to achieve a minimum 40 mm transition paving at the required grade transition of 200:1 Surface removal of the existing concrete deck to achieve newly designed bridge centreline (crown) – minimum removal of 50 mm thickness of concrete deck (thickness varies) Partial depth repair of the concrete deck Abrasive blasting of the concrete deck surface Supply and install dowels to the existing bridge deck for the anchoring of the new TL-5 barriers Supply and placement of reinforcing steel and Class HPC fibre-reinforced concrete for the new deck overlay and TL-5 barriers, including material testing Construction of new approach slabs at both bridge abutments Supply and install TL-5 barrier double tube railing Supply and install deck waterproofing, including on top of the new approach slabs Supply and placement of asphalt concrete pavement including material testing Supply and install approach rail transition c/w posts Supply and install strong post thriebeam c/w posts Construction of new reinforced concrete wingwalls (at all four corners) with H-pile footings Construction of new concrete drain toughs at all four corners of the bridge Supply and application of Type 3 pigmented and Type 1C concrete sealers Supply and install heavy rock riprap (class 1)
Go To | 23181 | Multiple | - | 2025-02-27 | 4 | 2024-2025 | Southern | Highway | Bridge Maintenance | Mill and Pave Bridges | Bridge | - | - | - | - | - | - | 2020 | 2025-10-15 | - | - | - | Hwy 2 North of Calgary | Scope of Work: Cold Milling Asphalt Concrete Pavement – Superpave Bridge Tie-in Saw Cutting & Sealant
Go To | 23855 | Multiple | - | 2025-02-28 | 4 | 2024-2025 | Southern | Highway | Bridge Maintenance | Mill and Pave Bridges | Bridge | - | - | - | - | - | - | 2020 | 2025-10-15 | - | - | - | Stoney Trail | Scope of Work: Cold Milling Asphalt Concrete Pavement (ACP) – Superpave Bridge Tie-in Saw Cutting & Sealant
Go To | 22642 | 7855 | 2 | 2025-03-04 | 3 | 2024-2025 | North Central | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 9 x 700 SLC | 20 | 20 | 11.1 | 2020 | 2025-10-15 | 830 | 4 | Astotin Creek | 5 km Northwest of Bruderheim | Scope of Work: Traffic Accommodation for Bridge Construction Site Isolation and Water Accommodation Construct On-site Paved Detour with Temporary Bridge Demolition and Disposal of the Existing Bridge Structure Excavation - Structural Backfill Supply, Setup, and Drive Steel H-Piles Construct Cast-in-Place Abutment Seats and Wingwalls Fabricate, Supply, and Erect 20 m Long SLC-700 Girders Construct Cast-in-Place Concrete Deck and Approach Slabs Deck Waterproofing Asphalt Concrete Pavement – Mix Type M1 Bridgerail and Guardrail – Supply and Install Impact Attenuator – Supply and Install Roadway Work Site Reclamation and Environmental Protection Devices
Go To | 21867 | 73534 | 2 | 2025-03-05 | 7 | 2024-2025 | Peace | Single | Replace Bridge with Bridge | Construct SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 9 x 510 SLW | 14 | 14 | 11 | 2020 | 2025-09-30 | Local | Road | Winagami / Girouxville Canal | 1 km North of Falher | Scope of Work: Traffic Accommodation Removal of Bridge Structure Headslope Preparation and Backfill Supply, Set-up and Drive Steel H-piling Abutment and Wingwall Construction Supply, Delivery, and Erection of Pre-stressed Bridge Girders Supply and Install Bridgerail Supply and Install Approach Rail Construction of Approach Slabs Supply and Installation of Bridge Deck Waterproofing Membrane Roadway Work ACP Supply and Install Heavy Rock Riprap (Class 1) Supply and Installation of Erosion Control Soil Covering (Type C) Supply and Install Erosion Control Barrier (Silt Fence) Supply and Install Erosion Control Barrier (Straw Roll) Turbidity Monitoring
Go To | 23732 | 77415 | 1 | 2025-03-07 | 9 | 2024-2025 | Central | Highway | Remove Culvert | Remove CSP Culvert | Culvert | Steel | CSP | 1 x 1800 CSP | 29 | 29 | 1.8 | 2020 | 2025-10-31 | 56 | 16 | Cattlepass | Near Meeting Creek | Scope of Work: Bridge File Culvert Demolition
Go To | 22362 | 75059 | 1 | 2025-03-20 | 4 | 2024-2025 | Southern | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Rolled Beam | 5 x 910 RB | 21 ¦ 29 ¦ 22 ¦ 12 | 84 | 9 | 2020 | 2026-07-31 | 507 | 2 | Mill Creek | 6 km East of Beaver Mines | Scope of Work: Designing, constructing, operating, maintaining, and removing temporary traffic accommodation activities. Implementing and maintaining environmental controls. Removing and disposing of the existing wearing surface on the bridge deck and approach slabs. Removing and disposing of existing deck joints and supplying and installing new Type 1 strip seal joints at both abutments and at one pier. Performing concrete repairs including partial depth repairs, full depth repairs, and crack repairs. Supplying and installing galvanized steel deck drain extensions. Implementing protection of the environment and conducting selected coating repairs to steel girders and bearings. Modifications to existing approach slabs and wingwall-supported flared concrete parapets to accommodate new approach guardrail thrie-beam connections. Supplying and installing a hot-applied deck waterproofing system with nominal 80 mm two- course hot-mix ACP wearing surface on the bridge deck and approach slabs. Removing and disposing of existing concrete drain trough collectors. Supplying and installing new concrete drain trough collectors. Renewing concrete sealer with Type 1c penetrating sealer at selected locations. Removing and disposing of the existing approach guardrail systems. Supplying and installing new approach guardrail systems. Cold milling and paving approach roadways to tie-in to the existing roadway for a smooth transition.
Go To | 24815 | 75726 | 1 | 2025-04-01 | 5 | 2025-2026 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Rigid Frame | 5 x 910 FR | 30 ¦ 9 ¦ 30 | 69 | 10.7 | 2020 | 2025-10-25 | Local | Road | Highway 2 | 10 km Northwest of Ponoka | Scope of Work: Traffic Accommodation Deck Joint Replacement Wearing Surface Crack Sealing Partial Depth Repair – Various Bridge Elements Supply and Application of Type 3 Pigmented and Type 1C Concrete Sealer Recasting Pier Grout Pads Bridgerail Repair Supply and Installation of New Approach Rail Transitions Drain Troughs Concrete Slope Protection Repairs Miscellaneous Repairs
Go To | 24779 | 72485 | 2 | 2025-04-03 | 5 | 2025-2026 | Peace | Multiple | Replace Bridge with Bridge | Construct SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 8 x 510 SLW | 6 ¦ 12 ¦ 6 | 24 | 9.9 | 2020 | 2025-10-15 | 690 | 2 | Tributary to Rousseau Creek | 30 km Southeast of Manning | Scope of Work: Traffic accommodation for bridge construction Site isolation and water accommodation Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structure Excavation Backfill Supply, set-up, and drive steel H-piling Supply, set-up, and install steel abutment seats and pier caps Fabricate, supply, and erect SLC510 prestress concrete girders Construct Cast-in-Place approach slabs Deck waterproofing and ACP – Mix Type M1 Roadway work, including removal and reinstall guardrails Miscellaneous iron Bridgerail and guardrail - supply and install Impact Attenuator – supply and install Site reclamation and environmental protection devices
Go To | 24779 | 72488 | 2 | 2025-04-03 | 5 | 2025-2026 | Peace | Multiple | Replace Bridge with Bridge | Construct SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 8 x 510 SLW | 14 | 14 | 9.9 | 2020 | 2025-10-15 | 690 | 2 | Rousseau Creek | 33 km Southeast of Manning | Scope of Work: Traffic accommodation for bridge construction Site isolation and water accommodation Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structure Excavation Backfill Supply, set-up, and drive steel H-piling Supply, set-up, and install steel abutment seats and pier caps Fabricate, supply, and erect SLC510 prestress concrete girders Construct Cast-in-Place approach slabs Deck waterproofing and ACP – Mix Type M1 Roadway work, including removal and reinstall guardrails Miscellaneous iron Bridgerail and guardrail - supply and install Impact Attenuator – supply and install Site reclamation and environmental protection devices
Go To | 22891 | 80940 | 2 | 2025-04-29 | 5 | 2025-2026 | Peace | Single | Replace Bridge with Bridge | Construct SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 9 x 510 SLW | 8 ¦ 14 ¦ 8 | 30 | 11.1 | 2020 | 2025-10-31 | 750 | 6 | Utikuma River | 82 km Northeast of Enilda | Scope of Work: Traffic accommodation Demolition and disposal of bridge structure Headslope preparation and backfill Supply, set-up and drive steel H-piling Abutment, pier and wingwall construction Supply, delivery, and erection of pre-stressed concrete bridge girders Construction of approach slabs Supply and installation of bridge deck waterproofing membrane Roadway Work ACP supply and install Supply and install bridgerail Supply and install of approach rail Heavy rock riprap (Class 1) Supply and installation of erosion control soil covering (type C) Supply and install erosion control barrier (silt fence) Supply and install erosion control barrier (straw roll) Turbidity Monitoring Fish salvage (if required)
Go To | 20364 | 109 | 2 | 2025-05-01 | 5 | 2025-2026 | Central | Complex | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 2 x 2200 CSP | 37 - 37 | 74 | 2.2 | 2020 | 2026-09-30 | 834 | 4 | Hastings Creek | Near Tofield | Scope of Work: Traffic accommodation Site isolation and water accommodation (Water Management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structures, including guardrail Excavation including supply & placement of geotextile filter fabric Supply and assembly of culvert materials Backfill including clay seals and backfill material testing Concrete end treatment including concrete testing and small bridge plaque (Bridge File 237, Bridge File 416 and Bridge File 708 only) Supply and Installation of bridge identification tag (Bridge File 109 only) Heavy rock riprap erosion protection including geotextile filter fabric Permanent environmental protection devices
Go To | 20364 | 237 | 2 | 2025-05-01 | 5 | 2025-2026 | Central | Complex | Replace Bridge with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 3360 SPCSP | 39 | 39 | 3.4 | 2020 | 2026-09-30 | 834 | 4 | Norris Creek | Near Chipman | Scope of Work: Traffic accommodation Site isolation and water accommodation (Water Management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structures, including guardrail Excavation including supply & placement of geotextile filter fabric Supply and assembly of culvert materials Backfill including clay seals and backfill material testing Concrete end treatment including concrete testing and small bridge plaque (Bridge File 237, Bridge File 416 and Bridge File 708 only) Supply and Installation of bridge identification tag (Bridge File 109 only) Heavy rock riprap erosion protection including geotextile filter fabric Permanent environmental protection devices
Go To | 20364 | 416 | 2 | 2025-05-01 | 5 | 2025-2026 | Central | Complex | Replace Culvert with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 3670 SPCSP | 50 | 50 | 3.7 | 2020 | 2026-09-30 | 834 | 4 | Katchemut Creek | Near Tofield | Scope of Work: Traffic accommodation Site isolation and water accommodation (Water Management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structures, including guardrail Excavation including supply & placement of geotextile filter fabric Supply and assembly of culvert materials Backfill including clay seals and backfill material testing Concrete end treatment including concrete testing and small bridge plaque (Bridge File 237, Bridge File 416 and Bridge File 708 only) Supply and Installation of bridge identification tag (Bridge File 109 only) Heavy rock riprap erosion protection including geotextile filter fabric Permanent environmental protection devices
Go To | 20364 | 708 | 2 | 2025-05-01 | 5 | 2025-2026 | Central | Complex | Replace Culvert with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 3360 SPCSP | 43 | 43 | 3.4 | 2020 | 2026-09-30 | 834 | 4 | Wakinagan Creek | Near Tofield | Scope of Work: Traffic accommodation Site isolation and water accommodation (Water Management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structures, including guardrail Excavation including supply & placement of geotextile filter fabric Supply and assembly of culvert materials Backfill including clay seals and backfill material testing Concrete end treatment including concrete testing and small bridge plaque (Bridge File 237, Bridge File 416 and Bridge File 708 only) Supply and Installation of bridge identification tag (Bridge File 109 only) Heavy rock riprap erosion protection including geotextile filter fabric Permanent environmental protection devices
Go To | 22515 | 2143 | 4 | 2025-05-02 | 4 | 2025-2026 | Southern | Complex | Replace Bridge with Bridge | Construct Precast Box Concrete Girder Bridge | Bridge | Concrete | Precast Box | 11 x 900 PB | 27 ¦ 30 ¦ 27 | 84 | 14.4 | 2020 | 2026-10-31 | 8 | 6 | Elbow River | 19 km West of Calgary | Scope of Work: Elbow River temporary access berm design, installation, maintenance and removal Demolition and disposal of the existing eastbound Highway 8 bridge over the Elbow River (BF 02143E) and related work Construction of the new precast prestressed concrete girder bridge (BF 02143E) carrying Highway 8 eastbound over the Elbow River and related work
Go To | 22515 | Multiple | - | 2025-05-02 | 4 | 2025-2026 | Southern | Complex | New Sign Structures | Construct Sign Structures | Sign Structure | - | - | - | - | - | - | 2020 | 2026-10-31 | - | - | - | Hwy 8 West of Calgary | Scope of Work: Relocation of existing overhead sign panels, installation of the Department’s supplied overhead sign panels, and supply and installation of new overhead sign panels
Go To | 23931 | 76392 | 1 | 2025-05-06 | 4 | 2025-2026 | Southern | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | VF | 10 x 1320 VF | 38 ¦ 38 | 76 | 16.9 | 2020 | 2026-10-31 | 2A | 6 | Highway 2 | At Dewinton | Scope of Work: Designing, constructing, operating, maintaining, and removing temporary traffic accommodation activities including detour Implementing and maintaining environmental controls Removing and salvaging the existing median delineators. Reinstalling the salvaged delineators upon completion of construction Removing and disposing of top 25 mm of the existing wearing surface on the bridge deck and roof slabs Removing and disposing of existing deck joints supplying and installing new Type 1 strip seal joints at both abutments and pier Performing concrete repairs including partial depth and full depth repairs, and crack repairs Supplying and placing 50 mm HPC concrete deck overlay with steel fibres on the bridge deck and roof slabs Performing high load damage repairs on girders Conducting paint repairs of anchor chuck of lateral post-tensioning system strands Conducting grout pad repairs and coating repairs at selected bridgerail post locations and bearings Renewing concrete sealer with Type 1c penetrating sealer and Type 3 pigmented sealer at selected locations Roof slab inspection access Grouting void under approach slab at Abutment 1 Removing parging and sack rubbing on Abutment 2 Replacing bridge plaque at Abutment 2 Replacing curb control joint sealing with flexible joint sealant between roof slab curb and approach slab curb Cold milling and paving approach roadways to tie-in to the existing roadway for a smooth transition
Go To | 12477 | 1704 | 2 | 2025-05-08 | 5 | 2025-2026 | Central | Single | Replace Bridge with Bridge | Construct SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 8 x 510 SLW | 14 | 14 | 9.9 | 2020 | 2025-10-31 | 585 | 2 | Ghostpine Creek | 4 km East of Trochu | Scope of Work: Traffic accommodation for bridge construction Site isolation and water accommodation (Water management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structure, including guardrail Excavation Supply, set-up, and driving of steel H-piling Abutment construction Heavy rock riprap erosion protection including geotextile filter fabric Supply, delivery and erection of concrete girders Approach slab construction Deck waterproofing and asphalt concrete pavement including material testing Miscellaneous iron Roadway work Supply and installation of bridgerail and guardrail Permanent environmental protection devices
Go To | 23213 | 78802 | 1 | 2025-06-03 | 3 | 2025-2026 | North Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Welded Girder | 3 x 1530 WG | 28 ¦ 34 ¦ 34 | 96 | 9.2 | 2020 | 2026-06-30 | 60 | 4 | Highway 16 | 3 km West of Edmonton | Scope of Work: Traffic accommodation Demolition and disposal of bridge structure (existing deck joint assemblies at both abutments; existing approach rail transitions, guardrail, and end treatments; north concrete slope protection (partial)) Surface removal of 40 mm ACP wearing surface on top of the bridge deck and approach slabs Cold milling of 50 mm existing ACP on the approach roads with a grade transition of 200:1 Partial depth repair of the concrete curbs, abutments, pier caps, and wingwalls Supply, fabrication, delivery, and installation of new deck joint assemblies at both abutments Concrete crack repair of the wingwalls, curbs, pier columns, and pier caps Repair of the existing steel girders from previous high load impact – removal of nicks Repair of deficient deck waterproofing areas, if any, as determined on site by the Consultant Supply and placement of asphalt concrete pavement (ACP) including material testing Supply and install approach rail transitions c/w posts Supply and install new strong-post w-beam guardrail c/w posts, including TL-3 energy absorbing end treatments Construction of a new concrete drain trough at the northeast corner of the bridge Cleaning of the existing concrete surfaces on the abutments, wingwalls, curbs, pier columns, and pier caps Supply and application of Type 2 a/b concrete sealers on the interior and top facings of bridge curbs Supply and application of Type 3 pigmented concrete sealers on the exterior concrete facings of the abutment, pier columns, pier caps, and exterior curb facings Repair and construction of the existing concrete slope protection on abutment 2 (north) Extra work to be identified by the Consultant during construction (total force account)
Go To | 21653 | 73436 | 1 | 2025-06-10 | 4 | 2025-2026 | Peace | Highway | Bridge/Culvert Rehabilitation | Bridge/Culvert Rehabilitation | Bridge/Culvert | Concrete/Steel | HC (Bridge) / SPCSP (Culvert) | 14 x 510 HC / 1 x 7060 Elliptical SPCSP | 9 / 16 | 16 | 7.1 | 2020 | 2025-10-15 | 35 | 12 | Boyer River | 8 km South of Paddle Prairie | Scope of Work: Bridge Curb and Bridgerail Replacement
Go To | 23214 | 76646 | 2 | 2025-06-11 | 6 | 2025-2026 | North Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | Type-M / Type-M (Modified) | 19 x 610 Type-M / 4 x 610 Type-M (Modified) | 11 ¦ 17 ¦ 11 | 39 | 18.6 | 2020 | 2026-06-30 | 16 | 18 | Clover Bar Road | 5 km East of Edmonton | Scope of Work: Traffic accommodation Demolition, disposal, and salvage of existing bridge structure (demolition and disposal of the existing bridge curbs (both sides); demolition and disposal of the existing bridgerail (both sides); demolition and disposal of the existing approach rail transitions (all corners; salvage of the existing strong-post w-beam guardrail (all bridge corners); salvage of the pedestrian rail on Range Road Road 231 at the east abutment) Surface removal 50 mm of the existing concrete deck Abrasive blasting of concrete surfaces Partial depth repair – various elements Concrete crack repair of various bridge elements – gravity-fed epoxy Concrete crack repair of various bridge elements – pressure-injected epoxy Investigation and grouting of voids under approach slabs Supply and placement of Class HPC fibre-reinforced concrete for the new deck overlay, including material testing Construction of new concrete curbs Supply and install new TL-4 double tube bridgerail Supply and install new approach rail transitions Reinstallation of the salvaged strong-post w-beam guardrail, including the supply and installation of new hardware. Reinstallation of the salvaged pedestrian railing on Range Road 231 Concrete slope protection repair Supply and placement of asphalt concrete pavement, including material testing Supply and install new drain troughs Supply and apply type 3 pigmented concrete sealer Extra work to be identified by the Consultant during construction (total force account)
Go To | 19440 | 75337 | 3 | 2025-06-12 | 5 | 2025-2026 | Central | Complex | Replace Bridge with Bridge | Construct NU Precast Concrete Girder Bridge | Bridge | Concrete | NU | 7 x 1600 NU | 34 | 34 | 21.8 | 2020 | 2026-10-15 | 2 | 26 | CNR Railway | 13 km Northwest of Red Deer | Scope of Work: Demolition and disposal of existing bridge structure, including guardrail Excavation structural Supply, pile tip reinforcement, set-up, and driving of steel H-Piles including Pile Driving Analysis (PDA) testing Supply and placement of reinforcing steel for substructure and superstructure Supply and placement of concrete for substructure and superstructure including material testing Supply, fabrication, delivery, and erection of concrete girders and steel diaphragms- Deck waterproofing and asphalt concrete pavement including material testing Miscellaneous iron Supply and installation of drain troughs Supply and installation of mechanically stabilized earth (MSE) walls Supply and fabrication, delivery, and installation of bridgerail and guardrail
Go To | 19440 | 75337 | 4 | 2025-06-12 | 5 | 2025-2026 | Central | Complex | Replace Bridge with Bridge | Construct NU Precast Concrete Girder Bridge | Bridge | Concrete | NU | 7 x 1600 NU | 34 | 34 | 21.8 | 2020 | 2026-10-15 | 2 | 26 | CNR Railway | 13 km Northwest of Red Deer | Scope of Work: Demolition and disposal of existing bridge structure, including guardrail Excavation structural Supply, pile tip reinforcement, set-up, and driving of steel H-Piles including Pile Driving Analysis (PDA) testing Supply and placement of reinforcing steel for substructure and superstructure Supply and placement of concrete for substructure and superstructure including material testing Supply, fabrication, delivery, and erection of concrete girders and steel diaphragms- Deck waterproofing and asphalt concrete pavement including material testing Miscellaneous iron Supply and installation of drain troughs Supply and installation of mechanically stabilized earth (MSE) walls Supply and fabrication, delivery, and installation of bridgerail and guardrail
Go To | 19440 | 83091 | 2 | 2025-06-12 | 5 | 2025-2026 | Central | Complex | New DMS Structure | Construct DMS Structure | DMS Structure | - | - | - | - | - | - | 2020 | 2026-10-15 | 2 | 26 | - | 13 km Northwest of Red Deer | Scope of Work: Dynamic Message Sign (DMS) including removal and disposal, supply and install, modifications, and related works. Road Weather Information System (RWIS) including removal, salvage and disposal, supply and install, and related works.
Go To | 23207 | 76001 | 2 | 2025-06-25 | 2 | 2025-2026 | North Central | Multiple | Culvert Maintenance | Install Erosion and Sediment Control Measures | Culvert | Steel | SWSP | 1 x 2100 SWSP | 118 | 118 | 2.1 | 2020 | 2026-03-31 | 63 | 11 | Prairie Creek | 9 km South of Ft McMurray | Scope of Work: Traffic Accommodation Common Excavation Topsoil Placement Class 1M, Class 1, and Class 2 heavy rock riprap (including geotextile filter fabric) Sideslope improvements Permanent environmental protection devices Site cleanup
Go To | 23207 | 76002 | 3 | 2025-06-25 | 2 | 2025-2026 | North Central | Multiple | Replace Culvert with Culvert | Construct SWSP Culvert | Culvert | Steel | SWSP | 1 x 3350 SWSP | 80 | 80 | 3.4 | 2020 | 2026-03-31 | 63 | 10 | Halfway Creek | 15 km South of Ft McMurray | Scope of Work: Traffic Accommodation Demolition, Disposal, and Salvage Existing Structure Excavation – Structural Environmental Protection Works Care of Water Total Suspended Solids (TSS) Testing Supply and Install Smooth Wall Steel Pipe Culvert (SWSP) (3353 mm dia.) by trenchless methods. Extents of culvert to be placed through trenchless method is as identified in the contract drawings and a bridge plaque Abandon the existing culvert with grout Concrete end treatment at upstream end only Bedding and Backfill (includes woven geotextile filter fabric, crushed aggregate material Des 2 Class 40, crushed aggregate material Designation 2 Class 25, and clay seals) Heavy Rock Riprap Class 1 (includes non-woven geotextile filter fabric) Supply and installation of silt fence barriers
Go To | 22880 | 72029 | 2 | 2025-07-09 | 12 | 2025-2026 | Southern | Single | Replace Bridge with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 3600 CSP | 62 | 62 | 3.6 | 2020 | 2026-06-15 | 875 | 4 | EID - Irrigation Canal | 25 km Southwest of Tilley | Scope of Work: Site Occupancy and Lane Closure for Bridge Construction Traffic Accommodation for Bridge Construction (Staged Construction) Care of Water Total Suspended Solids (TSS) Testing Fish Capture & Release Demolition and Disposal of Bridge Structures Structural Excavation Supply and Assembly of (1) 3600 mm diameter x 62 m Polymer Coated CSP Concrete End Treatment Granular and Non-Granular Backfill Supply and Placement of Class 1 and Class 1M Heavy Rock Rip Rap Removal and Disposal of Approach Culvert Removal, Salvage and Reinstallation of Approach Culvert Supply and Installation of New Approach Culverts Roadway Work Asphalt Concrete Pavement – Type M1 (PG 52-34) Erosion Control Barrier – Silt Fence Other Work
Go To | 12463 | 7816 | 2 | 2025-07-15 | 8 | 2025-2026 | Central | Single | Replace Bridge with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 2 x 2700 CSP | 27 - 27 | 54 | 2.7 | 2020 | 2025-10-15 | 834 | 2 | Amisk Creek | 7 km North of Round Hill | Scope of Work: Traffic Accommodation Demolition, Disposal, and Salvage Existing Structure Excavation – Structural Environmental Protection Works Water management (Care of Wate) Fish capture and release Total Suspended Solids (TSS) Testing Supply, assembly, and Install Corrugated Steel Pipe (CSP) (2 - 2700 mm dia.) by open cut methods Bedding and Backfill (includes woven geotextile filter fabric, crushed aggregate material Des 2 Class 40, crushed aggregate material Designation 2 Class 25, and clay seals) Heavy Rock Riprap Class 1 (includes non-woven geotextile filter fabric) Roadway work High Tension Cable Barrier (HTCB) – Supply and Installation Permanent environmental protection devices include supply and installation of erosion control barriers (straw rolls) and supply and installation of erosion control matting (Type B) Removal of temporary detour bridge Restore detour road footprint (Topsoil, positive drainage)
Go To | 21869 | 8320 | 2 | 2025-07-22 | 5 | 2025-2026 | Peace | Single | Replace Bridge with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 3670 SPCSP | 41 | 41 | 3.7 | 2020 | 2025-11-15 | 49 | 10 | Tributary to Peavine Creek | Near Falher | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Fish Capture and Release Removal and Disposal of Existing Bridge Structure Excavation Supply, Assembly and Installation of SPCSP Culvert Material Backfill Concrete End Treatment Class 1 Heavy Rock Riprap Roadway Work Class 1M Rock Ditch Drains Erosion Control Barrier (Straw Rolls) Erosion Control Soil Covering (Type C) Erosion Eontrol Barrier (silt fence)
Go To | 23792 | 73127 | 2 | 2025-07-22 | 5 | 2025-2026 | Central | Multiple | Replace Culvert with Culvert | Construct SWSP Culvert | Culvert | Steel | SWSP | 1 x 2100 SWSP | 65 | 65 | 2.1 | 2020 | 2026-06-30 | 585 | 2 | Tributary to Ghostpine Creek | Near Trochu | Scope of Work: Traffic accommodation Site isolation and water accommodation (water management) Total Suspended Solids (TSS) testing Fish capture and release Excavation Supply and bore SWSP culvert Backfill including material testing Heavy rock riprap erosion protection including geotextile filter fabric Grouting of existing culvert, including concrete testing Permanent environmental protection devices
Go To | 23792 | 73865 | 2 | 2025-07-22 | 5 | 2025-2026 | Central | Multiple | Replace Culvert with Culvert | Construct SWSP Culvert | Culvert | Steel | SWSP | 1 x 2440 SWSP | 38 | 38 | 2.4 | 2020 | 2026-06-30 | 45 | 8 | 2nd Order Tributary to Slawa Creek | Near Myrnam | Scope of Work: Traffic accommodation Site isolation and water accommodation (water management) Total Suspended Solids (TSS) testing Fish capture and release Excavation Supply and bore SWSP culvert Backfill including material testing Heavy rock riprap erosion protection including geotextile filter fabric Grouting of existing culvert, including concrete testing Permanent environmental protection devices
Go To | 22256 | 80927 | 2 | 2025-08-07 | 3 | 2025-2026 | Peace | Single | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 2400 CSP | 40 | 40 | 2.4 | 2020 | 2026-03-31 | 58 | 12 | 2nd Order Tributary to Lawrence River | Near John D'Or Prairie | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Water Management Removal and Disposal of Existing Culvert Structure Excavation Supply, Assembly and Installation of CSP Culvert Material Backfill Concrete End Treatment Roadway Work Class 2 Heavy Rock Riprap Rock Ditch Drains - Class 1M Erosion Control Barrier (Silt Fence) Erosion Control Barrier (Straw Rolls) Erosion Control Soil Covering (Type C) Fish Capture and Release (deletable)
Go To | 22726 | 72398 | 2 | 2025-08-20 | 2 | 2025-2026 | Central | Single | Replace Bridge with Bridge | Construct SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 9 x 510 SLW | 14 | 14 | 11.1 | 2020 | 2026-09-30 | 857 | 4 | 2nd Order Tributary to Vermilion River | 19 km North of Vegreville | Scope of Work: Traffic Accommodation for Bridge Construction Site Isolation and Water Accommodation (Water Management) Total Suspended Solids (TSS) Testing Fish Capture and Release Demolition and Disposal of Existing Bridge Structure, Including Guardrail Excavation Supply, Set-up and Drilled Steel H-Piling Abutment Construction Heavy Rock Riprap Erosion Protection, Including Geotextile Filter Fabric Supply, Delivery, and Erection of Concrete Girders Approach Slab Construction Deck Waterproofing and Asphalt Concrete Pavement, Including Material Testing Miscellaneous Iron Roadway Work Supply and Installation of Drain Troughs Supply and Installation of Bridgerail and Guardrail Permanent Environmental Protection Devices
Go To | 25141 | 75651 | 5 | 2025-08-26 | 3 | 2025-2026 | Central | Highway | Remove Sign Structure | Remove Sign Structure | Sign Structure | - | - | - | - | - | - | 2020 | 2026-07-31 | 2 | 28 | - | 5 km West of Ponoka | Scope of Work: Signage including removal and reinstall or removal and disposal of existing signs, and supply and reinstall new signs
Go To | 25520 | 76028 | 2 | 2025-09-18 | 3 | 2025-2026 | Peace | Multiple | New and Lined Culverts | Construct WSP Culvert - Install CSP Culvert Liner | Culvert | Steel | SWSP - CSP Liner | 2 x 2440 SWSP - 1 x 2400 CSP Liner | 115 - 115 - 107 | 337 | 2.4 | 2020 | 2026-07-31 | 33 | 12 | Tributary to Swan River | 24 km Northeast of Swan Hills | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Fish Capture and Release Care of Water Clearing & Mulching Excavation Supply and Installation of CSP Liner Grouting of CSP Liner Structural & Channel Excavation Supply & Installation of Welded Steel Pipe culvert Backfill (Non-Granular) Heavy Rock Riprap (Class 1) Supply and Installation of Substrate Holders and Substrate Material (Class 1M) Erosion Control Barrier (Silt Fence) Erosion Control Soil Covering Miscellaneous Environmental Work Roadway Work Hydro-mulching Tree Planting
Go To | 25520 | 76042 | 2 | 2025-09-18 | 3 | 2025-2026 | Peace | Multiple | New and Lined Culverts | Construct WSP Culvert - Install CSP Culvert Liner | Culvert | Steel | SWSP - CSP Liner | 1 x 2440 SWSP - 1 x 2000 CSP Liner | 95 - 83 | 178 | 2.2 | 2020 | 2026-07-31 | 33 | 14 | Tributary to Chalmers Creek | 33 km Northeast of Swan Hills | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Fish Capture and Release Care of Water Clearing & Mulching Excavation Supply and Installation of CSP Liner Grouting of CSP Liner Structural & Channel Excavation Supply & Installation of Welded Steel Pipe culvert Backfill (Non-Granular) Heavy Rock Riprap (Class 1) Supply and Installation of Substrate Holders and Substrate Material (Class 1M) Erosion Control Barrier (Silt Fence) Erosion Control Soil Covering Miscellaneous Environmental Work Roadway Work Hydro-mulching Tree Planting
Go To | 22993 | 75932 | 1 | 2025-09-23 | 4 | 2025-2026 | Southern | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Rolled Beam | 5 x 910 RB | 13 ¦ 27 ¦ 27 ¦ 13 | 80 | 12.5 | 2020 | 2026-10-31 | 22 | 14 | Highway 1 | 14 km South of Cochrane | Scope of Work: Traffic accommodation ACP Surface removal Partial depth concrete repairs (deck, curbs, abutments and piers) Full depth concrete repairs (deck) Concrete crack repairs (deck overlay) Deck joint replacements Galvanic corrosion protection Abutment and curb modifications Abutment bearing replacements Chip seal coat repairs Steel girder pressure washing Concrete cleaning and sealing Median traffic separator system repairs Transition approach paving Miscellaneous repairs Painted roadway markings
Go To | 22743 | 9223 | 1 | 2025-09-25 | 5 | 2025-2026 | North Central | Highway | Remove Culvert | Remove CSP Culvert | Culvert | Steel | CSP | 1 x 2250 CSP | 34 | 34 | 2.3 | 2020 | 2027-07-31 | 14 | 6 | Cattlepass | Near Cooking Lake | Scope of Work: Traffic accommodation Topsoil stripping and stockpiling Removal and dispose installation of fence Supply and installation of new fence Structural excavation and demolition of bridge culvert ends Prepare the reminder of the culvert for lining. Lining the bridge culvert with SWSP, grouting the liner, and backfilling the SWSP extension. Restoring the highway sideslopes and contouring the area to match the surroundings Placement of hand-laid rip-rap Removal and disposal of existing guardrail Topsoiling, harrowing and seeding
Go To | 22743 | 77126 | 1 | 2025-09-25 | 5 | 2025-2026 | North Central | Highway | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | FC | 14 x 1270 FC | 36 ¦ 36 | 72 | 23.5 | 2020 | 2027-07-31 | 21 | 26 | Highway 14 | 10 km East of Sherwood Park | Scope of Work: Bridge rail upgrade Approach rail Raised concrete median on bridge Deck joints Drain trough
Go To | 22743 | 85071 | 13 | 2025-09-25 | 5 | 2025-2026 | North Central | Highway | New Sign Structures | Construct Sign Structures | Sign Structure | - | - | - | - | - | - | 2020 | 2027-07-31 | 14 | 4 | - | 3 km East of Edmonton | Scope of Work: Overhead sign structure
Go To | 25083 | 76396 | 1 | 2025-10-09 | 6 | 2025-2026 | North Central | Single | Bridge Rehabilitation | Replace Superstructure SLW Precast Concrete Girder Bridge | Bridge | Concrete | SLW | 10 x 510 SLW | 10 ¦ 12 ¦ 10 | 32 | 12.3 | 2020 | 2026-05-16 | Local | Road | Lac La Biche | 8 km North of Lac La Biche | Scope of Work: Traffic accommodation for bridge construction Removal and disposal of existing guardrail Removal and salvage of existing pedestrian handrail Excavation - Channel Excavation - Structural Demolition and disposal of existing bridge girders, wingwalls and pier caps Supply, set-up, and drive pipe piles Supply, set-up, and install pier caps Abrasive blasting and painting pier piles/columns Abutment modification (Partial depth repair and widening) Erection of SLW-510 girders and precast approach slabs Backfill Deck waterproofing and ACP – Mix Type M1 Bridgerail and guardrail – Supply and installation Pedestrian handrail reinstallation Roadway work Site reclamation and environmental protection devices
Go To | 12478 | 1974 | 2 | 2025-10-28 | 8 | 2025-2026 | Central | Multiple | Replace Bridge with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 3670 SPCSP | 40 | 40 | 3.7 | 2020 | 2026-10-15 | 585 | 2 | Tributary to Ghostpine Creek | Near Trochu | Scope of Work: Traffic Accommodation Demolition, Disposal, and Salvage Existing Structure Excavation – Structural Environmental Protection Works Care of Water (Water Management) Fish capture and release Total Suspended Solids (TSS) Testing Supply, assembly, and Install Structural Plate Corrugated Steel Pipe (SPCSP) (3670 mm dia.) by open cut methods Concrete end treatment at upstream end only Bedding and Backfill (includes woven geotextile filter fabric, crushed aggregate material Des 2 Class 40, crushed aggregate material Designation 2 Class 25, and clay seals) Heavy Rock Riprap Class 1 (includes non-woven geotextile filter fabric) Roadway work Hydroseeding and topsoiling Supply and installation of New Fence – Class B Permanent environmental protection devices include supply and installation of straw rolls, and supply and installation of erosion control matting (Type B)
Go To | 12478 | 70562 | 2 | 2025-10-28 | 8 | 2025-2026 | Central | Multiple | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 2400 CSP | 63 | 63 | 2.4 | 2020 | 2026-10-15 | 576 | 2 | McConnell Coulee | 21 km South of Delia | Scope of Work: Traffic Accommodation Demolition, Disposal, and Salvage Existing Structure Excavation – Structural Environmental Protection Works Care of Water Fish capture and release Total Suspended Solids (TSS) Testing Supply, assembly, and Install Corrugated Steel Pipe (CSP) (2400 mm dia.) by open cut methods Bedding and Backfill (includes woven geotextile filter fabric, crushed aggregate material Des 2 Class 40, crushed aggregate material Designation 2 Class 25, and clay seals) Heavy Rock Riprap Class 1 and Class 1M (includes non-woven geotextile filter fabric) Roadway work Hydroseeding and topsoiling Supply and installation of New Fence – Class B Permanent environmental protection devices include supply and installation of straw rolls, and supply and installation of erosion control matting (Type B)
Go To | 12478 | 77652 | 2 | 2025-10-28 | 8 | 2025-2026 | Central | Multiple | Replace Culvert with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 3990 SPCSP | 51 | 51 | 4 | 2020 | 2026-10-15 | 13 | 4 | Modeste Creek | 5 km West of Winfield | Scope of Work: Traffic Accommodation Demolition, Disposal, and Salvage Existing Structure Excavation – Structural Environmental Protection Works Care of Water Fish capture and release Total Suspended Solids (TSS) Testing Supply, assembly, and Install Structural Plate Corrugated Steel Pipe (SPCSP) (3990 mm dia.) by open cut methods Concrete end treatment at upstream end only Bedding and Backfill (includes woven geotextile filter fabric, crushed aggregate material Des 2 Class 40, crushed aggregate material Designation 2 Class 25, and clay seals) Heavy Rock Riprap Class 1 (includes non-woven geotextile filter fabric) Roadway work Hydroseeding and topsoiling Supply and installation of New Fence – Class B Permanent environmental protection devices include supply and installation of straw rolls and supply and installation of erosion control matting (Type B)
Go To | 20171 | 77728 | 2 | 2025-10-28 | 7 | 2025-2026 | Central | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 16 x 700 SLC | 20 | 20 | 19.6 | 2020 | 2026-10-15 | 11 | 4 | Shunda Creek | Near Nordegg | Scope of Work: Traffic accommodation Site isolation and water accommodation (water management) Total suspended solids (TSS) testing Fish capture and release Demolition and disposal of existing bridge structure, including guardrail Structural and channel excavation Supply, set-up and drive steel H-piling Supply and placement of reinforcing steel for substructure and superstructure Supply and placement of concrete for substructure and superstructure including material testing Heavy rock riprap erosion protection including geotextile filter fabric Supply, delivery, and erection of concrete girders Miscellaneous iron Deck waterproofing and asphalt concrete pavement including material testing Roadway work Supply and installation of bridgerail and guardrail Drain troughs Environmental offsetting measures including rock boulders and willow shrub plantings Permanent environmental protection devices
Go To | 21391 | 77462 | 2 | 2025-11-25 | 7 | 2025-2026 | Central | Single | Replace Culvert with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 3050 SPCSP | 69 | 69 | 3.1 | 2020 | 2026-10-15 | 11 | 8 | Jackfish Creek | 39 km East of Nordegg | Scope of Work: Traffic accommodation for bridge construction (including an on-site detour) Environmental and Regulatory compliance Site isolation and water accommodation Total suspended solids (TSS) testing Fish capture and release Excavation (structural and channel) Backfill Construction of new single 3.05 m diameter, 69.0m long SPCSP, and associated work Construction of two (2) cast-in-place concrete headwalls and culvert collars Downstream channel realignment Construction of rock drainage swales Heavy rock riprap – Class 1 and Class 1M Erosion and sediment control Roadway work and sideslope improvements Site reclamation, landscaping, and hydroseeding
Go To | 23914 | 74600 | 3 | 2025-11-27 | 10 | 2025-2026 | Southern | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 15 x 510 SLC | 10 ¦ 16 ¦ 10 | 36 | 18.4 | 2020 | 2026-10-31 | 1 | 4 | Bear Hill Road | 37 km West of Cochrane | Scope of Work: Temporary detour construction and removal, including a temporary bridge structure Demolition and disposal of existing three-span bridge structure Removal of existing bridgerail and guardrail Structural excavation Removal and replacement of existing drainage culvert Backfill Installation of cast-in-place concrete slope protection along headslopes Construction of new 36 m long three-span (10 m – 16 m – 10 m) SLC-510 girder bridge with concrete substructure, steel and concrete piers, cast-in-place concrete deck, and associated work Supply, fabrication, delivery, and erection of precast concrete girders Bridge deck waterproofing membrane and asphalt concrete pavement overlay (H1 Mix Type (PG 58-28)) Supply and installation of guardrail and bridgerail Installation of concrete and riprap drain troughs Roadway work – grade widening and paving (H1 Mix Type (PG 58-28)) Environmental management including temporary and permanent erosion control measures
Go To | 12482 | 629 | 2 | 2025-12-11 | 10 | 2025-2026 | Central | Multiple | Replace Bridge with Culvert | Construct SPCSP Culvert | Culvert | Steel | SPCSP | 1 x 4300 SPCSP | 43 | 43 | 4.3 | 2020 | 2026-10-15 | 601 | 4 | Tributary to Red Willow Creek | 10 km East of Red Willow | Scope of Work: Traffic Accommodation Demolition, Disposal, and Salvage Existing Structure Excavation – Structural Environmental Protection Works Care of Water (Water Management) Fish Capture and Release Total Suspended Solids (TSS) Testing Supply, Assembly, and Install Structural Plate Corrugated Steel Pipe (SPCSP) (4300 mm dia.) by Open Cut Methods Concrete End Treatment at Upstream and Downstream Ends Bedding and Backfill (includes woven geotextile filter fabric, crushed aggregate material Des 2 Class 40, crushed aggregate material Designation 2 Class 25, and clay seals) Heavy Rock Riprap Class 2 (includes non-woven geotextile filter fabric) Roadway Work Hydroseeding and Topsoiling Supply and Installation of New Fence – Class B Permanent Environmental Protection Devices (includes supply and installation of straw rolls, and supply and installation of erosion control matting (Type B))
Go To | 12482 | 75521 | 2 | 2025-12-11 | 10 | 2025-2026 | Central | Multiple | Replace Culvert with Culvert | Construct CSP Culvert | Culvert | Steel | CSP | 1 x 2200 CSP | 32 | 32 | 2.2 | 2020 | 2026-10-15 | 855 | 6 | Slough Creek | 32 km Northeast of Gadsby | Scope of Work: Traffic Accommodation Demolition, Disposal, and Salvage Existing Structure Excavation – Structural Environmental Protection Works Care of Water Fish Capture and Release Total Suspended Solids (TSS) Testing Supply, Assembly, and Install Corrugated Steel Pipe (CSP) (2200 mm dia.) by Open Cut Methods Bedding and Backfill (includes woven geotextile filter fabric, crushed aggregate material Des 2 Class 40, crushed aggregate material Designation 2 Class 25, and clay seals) Heavy Rock Riprap Class 1 (includes non-woven geotextile filter fabric) Roadway Work Hydroseeding and Topsoiling Supply and Installation of New Fence – Class B Permanent Environmental Protection Devices (includes supply and installation of straw rolls and supply and installation of erosion control matting (Type B))
Go To | 18625 | 74295 | 2 | 2026-01-14 | 3 | 2025-2026 | Peace | Single | New and Lined Culverts | Construct WSP Culvert - Install WSP Culvert Liner | Culvert | Steel | WSP - WSP Liner | 1 x 1830 WSP - 1 x 1680 WSP Liner | 161 - 123 | 284 | 1.8 | 2020 | 2026-10-31 | 43 | 2 | Tributary to Beaverlodge River | 4 km Southeast of Beaverlodge | Scope of Work: Traffic Accommodation Total Suspended Solids (TSS) Testing Fish Capture and Release Care of Water Coordination with CN Rail for Works within Railway Right-of-way including Monitoring Clearing & Mulching Structural & Channel Excavation Supply and Installation of Welded Steel Pipe Culvert and Culvert Extensions Supply and Installation of Welded Steel Pipe Liner Grouting of Welded Steel Pipe Liner Supply and Installation of Drop Inlet Extension. Backfill (Non-Granular) Heavy Rock Riprap (Class 2 & 3) Erosion Control Barrier (Silt Fence) Erosion Control Soil Covering Hydro-Seeding Miscellaneous Environmental Work Roadway Work
Go To | 23958 | 2235 | 1 | 2026-01-15 | 6 | 2025-2026 | Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | Type-O | 4 x 1120 Type-O | 17 ¦ 18 ¦ 17 | 52 | 9 | 2020 | 2026-10-15 | 766 | 12 | Lasthill Creek | 1 km South of Eckville | Scope of Work: Traffic Accommodation Concrete Deck Overlay Replacement Approach Slab Replacement New ACP Wearing Surface on Approach Slab Deck Joints Replacement Partial Depth Repair on Various Elements (Girders, Deck, Curbs, Pier Shafts, Abutments, and Diaphragms) Bearings Replacement at Piers and Abutments Concrete Modifications on Top of Piers and Abutments (including new shear blocks and corbels) Concrete Crack Repair - Gravity-Fed Epoxy Concrete Crack Repair - Pressure Injected Epoxy Supply, Delivery, and Install Elastomeric Bearing Assemblies Supply and Apply Type 1c Sealer Supply and Apply Pigmented Sealer Upgrade Bridgerail Supply and Install New Approach Rail Transitions Supply and Install New Guardrail and End Treatments Construct New Drain troughs at South Abutment Headslope Protection Erosion Repairs Supply and Install Lasthill Creek Sign Miscellaneous Repairs Extra Work - Miscellaneous Repairs
Go To | 12498 | 72242 | 2 | 2026-01-21 | 5 | 2025-2026 | Central | Single | Replace Bridge with Bridge | Construct SLC Precast Concrete Girder Bridge | Bridge | Concrete | SLC | 12 x 510 SLC | 14 ¦ 14 ¦ 14 | 42 | 13.6 | 2020 | 2026-10-31 | 11 | 8 | Chambers Creek | 31 km Northwest of Rocky Mountain House | Scope of Work: Traffic accommodation Temporary access berms, cofferdams, dikes and channel diversions Total suspended solids testing and fish capture, salvage and release Demolition and disposal of existing bridge structure, including guardrail Excavation Supply, set-up and drive steel H-piling Supply, set-up, pre-drill and drive steel pipe piling Supply and install pier bracing Supply and placement of reinforcing steel for substructure and superstructure Supply and placement of concrete for substructure and superstructure including material testing Drain troughs Heavy rock riprap erosion protection including geotextile filter fabric Supply, delivery and erection of Type ‘SLC’ concrete girders Miscellaneous iron Deck waterproofing and asphalt concrete pavement (ACP) including material testing Roadway work, including hydroseeding Supply and installation of bridgerail and guardrail Permanent environmental protection devices
Go To | 25448 | 75722 | 1 | 2026-02-03 | 5 | 2025-2026 | Central | Single | Bridge Repair | Bridge High Load Damage Repair | Bridge | Concrete | FC | 6 x 1020 FC | 15 ¦ 26 ¦ 26 ¦ 15 | 82 | 10.7 | 2020 | 2026-09-15 | Local | Road | Highway 2 | 19 km Northwest of Wetaskiwin | Scope of Work: Traffic Accommodation Demolition and Disposal of Existing Bridge Components Concrete Restoration Stirrup Repairs Strand Repair, Splicing & Re-tensioning Prestressing Strand Repositioning Girder Preloading Epoxy Crack Injection Repairs Concrete Cleaning and Sealing Side Slope Restoration
Go To | 24294 | 85465 | 1 | 2026-02-10 | 2 | 2025-2026 | North Central | Complex | New Bridge | Construct Welded Steel Girder Bridge | Bridge | Steel | Welded Girder | 5 x 2470 WG | 55 | 55 | 13.5 | 2020 | 2028-07-31 | 63 | 12 | Haul Road | 35 km North of Fort McMurray | Scope of Work: Structural excavation and backfill Drill, installation, and construction of belled cast-in-place concrete piles Construction of semi-integral concrete abutments, diaphragm, and wingwalls Design and installation of a mechanically stabilized earth (MSE) wall consisting of vertical wire mesh facing panels Supply and installation of the instrumentation behind the MSE wall Supply and place plain reinforcing steel for substructure Supply and installation of structural steel I-Girders, cross bracings and associated materials Supply and installation of elastomeric bearings at the abutments Construction of cast-in-place concrete deck and curbs Supply and place corrosion resistant reinforcing steel for deck, curbs, approach slabs, top 300 mm of abutment backwalls Supply and place stainless steel bars in corbels and dowels connecting approach slabs to corbels Supply and installation of ducts, electrical conduits and under bridge lighting Miscellaneous iron Bridgerail including appropriate curb connections and approach rail transitions Bridge deck waterproofing ACP on deck, approach slabs, and roadway approach transitions Drain troughs Sealers Clearing and grubbing Stripping Removing existing roadway Grading Culvert installation Utility Sleeve installation Underpass area excavation Fill with construction staging at Mildred Lake Reservoir Dam (MLRD) Preloading fill at Mildred Lake Reservoir Dam Upgrading Mildred Lake Reservoir Dam Geotechnical Instrumentation and Dewatering Well Installations at MLRD Granular base course Granular wearing course Asphalt paving Asphalt milling and overlay Pavement line markings Signing
Go To | 24294 | 85467 | 2 | 2026-02-10 | 2 | 2025-2026 | North Central | Complex | New Bridge | Construct Welded Steel Girder Bridge | Bridge | Steel | Welded Girder | 5 x 2470 WG | 55 | 55 | 13.5 | 2020 | 2028-07-31 | 63 | 12 | Haul Road | 35 km North of Fort McMurray | Scope of Work: Structural excavation and backfill Drill, installation, and construction of belled cast-in-place concrete piles Construction of semi-integral concrete abutments, diaphragm, and wingwalls Design and installation of a mechanically stabilized earth (MSE) wall consisting of vertical wire mesh facing panels Supply and installation of the instrumentation behind the MSE wall Supply and place plain reinforcing steel for substructure Supply and installation of structural steel I-Girders, cross bracings and associated materials Supply and installation of elastomeric bearings at the abutments Construction of cast-in-place concrete deck and curbs Supply and place corrosion resistant reinforcing steel for deck, curbs, approach slabs, top 300 mm of abutment backwalls Supply and place stainless steel bars in corbels and dowels connecting approach slabs to corbels Supply and installation of ducts, electrical conduits and under bridge lighting Miscellaneous iron Bridgerail including appropriate curb connections and approach rail transitions Bridge deck waterproofing ACP on deck, approach slabs, and roadway approach transitions Drain troughs Sealers Clearing and grubbing Stripping Removing existing roadway Grading Culvert installation Utility Sleeve installation Underpass area excavation Fill with construction staging at Mildred Lake Reservoir Dam (MLRD) Preloading fill at Mildred Lake Reservoir Dam Upgrading Mildred Lake Reservoir Dam Geotechnical Instrumentation and Dewatering Well Installations at MLRD Granular base course Granular wearing course Asphalt paving Asphalt milling and overlay Pavement line markings Signing
Go To | 24468 | 75946 | 1 | 2026-02-12 | 2 | 2025-2026 | Peace | Complex | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Steel Arch | Steel Arch | 20 ¦ 29 ¦ 29 ¦ 124 ¦ 125 ¦ 125 ¦ 92 ¦ 29 | 573 | 11.3 | 2020 | 2027-09-15 | 2 | 62 | Peace River | At Peace River | Scope of Work: Specialized Bridge Access Headslope Grading Repairs Partial Depth Repair – Deck Underside Concrete Sealer – Barriers and Bridgerail Grout Pads Concrete Sealer – Bearing Grout Pads Bearing Grout Pad Repairs at Abutments 1 and 2 Pier 1 and Pier 2 – Optional Bridge Jacking Pier 1 and Pier 2 Bearing Anchor Bolt Repairs Pier 3 and Pier 7 Rocker Bent Repairs East Approach Spans – Bottom Flange Repairs at Piers 1 and 2 East Approach Spans – Girder Field Splice Repairs Arch Spans – End Floor Beam Repairs Arch Spans – Arch Tie Corrosion Repairs Arch Spans – Arch Tie Access Hatch Repairs Arch Spans – Optional Access Holes in Arch Ties Protection of the Environment Surface Preparation and Painting including Touch-up Arch Spans – Repair of Stringer to Floor Beam Joints Arch Spans – Stringer and Floor Beam Hole Repairs Arch Spans – Hanger Supply Arch Spans – Hanger Fabrication Arch Spans – Hanger Deliver Arch Spans – Hanger Erection Deck Joints Removal ACP and Concrete Deck Removal Concrete – Supply and Place – Class HPC Corrosion Resistant Reinforcing Steel – Supply Stainless Steel Reinforcing Steel – Supply Reinforcing Steel – Place Strip Seal Deck Joint and Curb Cover Plate Replacement at Abutment 1 Finger Plate Deck Joint Assemblies – Supply, Fabrication, Delivery and Installation Deck Surface Preparation for Waterproofing Deck Surface Testing and Inspection Deck Waterproofing System Testing and Repair Asphalt Concrete Pavement – Mix Type H2 (PG58-28) PVC Deck Drains at Pier 4 and Pier 6 Barrier Cover Plate Repairs at Abutment 2 and Pier 6 Asphalt Replacement SS-1 Liquid Asphalt Application Thrie Beam to Bridge Barrier Repairs Bridgerail Reflectors Bridgerail and Guardrail Galvanizing Repairs
Go To | 24468 | 76060 | 1 | 2026-02-12 | 2 | 2025-2026 | Peace | Complex | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | FM | 13 x 1370 FM | 38 | 38 | 21.8 | 2020 | 2027-09-15 | 2 | 62 | CNR Railway | At Peace River | Scope of Work: Abutment shear block replacement South bridgerail anchorage replacement Replacement of the strip seal deck joints and curb cover plates Replacement of 50 mm ACP on the bridge deck, approach slabs and approach transitions SS1 liquid sealer application South bridgerail horizontal rail section replacement Bolt and fastener hardware replacement between the south bridgerail posts and rails Nut and washer replacement for south bridgerail posts Hot dip galvanizing repairs by metalizing Bridgerail and barrier reflector installation Removal of existing drain trough at the bridge northwest corner Filling voids around guardrail posts at drain trough inlets
Go To | 19893 | 9309 | 1 | 2026-02-24 | 4 | 2025-2026 | North Central | Single | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Welded Girder | 5 x 800 WG | 16 ¦ 19 ¦ 16 | 51 | 10.5 | 2020 | 2026-10-15 | 757 | 4 | Paddle River | 7 km North of Sangudo | Scope of Work: Traffic accommodation for bridge construction ACP surface removal on the approach road transitions Surface removal on the bridge deck Demolition and disposal of bridge structure elements Concrete repair of deck, curbs, and abutments Concrete crack repairs of abutments Deck and abutment end modifications for deck joint assemblies Supply and installation of galvanic corrosion protection anodes Replacement of deck joint assemblies Bridge deck surface preparation Waterproofing Weeping drain installation Asphalt concrete pavement Concrete cleaning and sealing Supply and installation of guardrail, approach rail transitions, and end terminals Roadway work Gabion, gabion mat, and riprap headslope erosion repair Access road construction
Go To | 24814 | 78895 | 1 | 2026-02-25 | 3 | 2025-2026 | Southern | Multiple | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Welded Box Girder | 3 x 1820 Welded Box Girder | 48 ¦ 54 ¦ 54 ¦ 54 ¦ 40 | 250 | 15.3 | 2020 | 2027-05-15 | 2 | 15 | Ogden Road ¦ CPR Railway ¦ CNR Railway | At Calgary | Scope of Work: Traffic accommodation Access to property in vicinity of railways and utilities Environmental controls Access to the work, including temporary access equipment / structures, curtain wall access doors, confined space management, construction debris cleanup and bird feces cleanup Girder web crack repair, including non-destructive testing Supply, fabrication, delivery and installation of bottom flange connector plate complete with all associated hardware, including non-destructive testing Field welding of top flange to stiffener connection complete with mock up repairs, including non-destructive testing
Go To | 24814 | 78895 | 2 | 2026-02-25 | 3 | 2025-2026 | Southern | Multiple | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Steel | Welded Box Girder | 3 x 1820 Welded Box Girder | 48 ¦ 50 ¦ 54 ¦ 54 ¦ 40 | 246 | 15.3 | 2020 | 2027-05-15 | 2 | 15 | Ogden Road ¦ CPR Railway ¦ CNR Railway | At Calgary | Scope of Work: Traffic accommodation Access to property in vicinity of railways and utilities Environmental controls Access to the work, including temporary access equipment / structures, curtain wall access doors, confined space management, construction debris cleanup and bird feces cleanup Girder web crack repair, including non-destructive testing Supply, fabrication, delivery and installation of bottom flange connector plate complete with all associated hardware, including non-destructive testing Field welding of top flange to stiffener connection complete with mock up repairs, including non-destructive testing
Go To | 23904 | 74355 | 1 | 2026-02-26 | 6 | 2025-2026 | Southern | Multiple | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | CT | 6 x 2080 CT | 18 ¦ 25 ¦ 25 ¦ 18 | 86 | 16.8 | 2020 | 2027-10-31 | 1 | 6 | Jumpingpound Creek | 16 km Southwest of Cochrane | Scope of Work: Traffic accommodation Environmental controls and care of birds Surface removals Surface preparation Concrete partial depth and full depth repairs, and crack repairs Grout pocket repairs at existing shear strengthening, at deck top Chip seal coat Deck joint maintenance and gland replacement Approach road partial reconstruction and approach transition paving Bridgerail grout pad repairs and baseplate coating repairs Bearing maintenance repairs Miscellaneous concrete girder crack repairs and/or repairs to existing girder strengthening system Concrete sealer application Painted roadway markings HTCB removal and reinstallation for traffic accommodation Deck joint maintenance – Snowplough guard replacement W-beam guardrail installation
Go To | 23904 | 74458 | 1 | 2026-02-26 | 6 | 2025-2026 | Southern | Multiple | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | CT | 6 x 2080 CT | 18 ¦ 25 ¦ 25 ¦ 18 | 86 | 16.9 | 2020 | 2027-10-31 | 2 | 12 | Highwood River | 1 km Southeast of Aldersyde | Scope of Work: Traffic accommodation Environmental controls and care of birds Surface removals Surface preparation Concrete partial depth and full depth repairs, and crack repairs Grout pocket repairs at existing shear strengthening, at deck top Chip seal coat Deck joint maintenance and gland replacement Approach road partial reconstruction and approach transition paving Bridgerail grout pad repairs and baseplate coating repairs Bearing maintenance repairs Miscellaneous concrete girder crack repairs and/or repairs to existing girder strengthening system Concrete sealer application Painted roadway markings Concrete partial depth repairs – girders Thrie-beam and W-beam guardrail upgrades and repairs
Go To | 23518 | 75340 | 1 | 2026-02-27 | 3 | 2025-2026 | Central | Multiple | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | Type-O | 10 x 1320 Type-O | 15 ¦ 29 ¦ 15 | 59 | 17.4 | 2020 | 2027-10-01 | 2 | 26 | Highway 12 | 3 km West of Lacombe | Scope of Work: Traffic accommodation including detours Concrete demolition of approach slabs Construction of new approach slabs Concrete surface removal of bridge deck Cold milling asphalt pavement HPC concrete Expansion joint replacement Deck slab concrete repair Fibre Reinforced High Performance Concrete (FRHPC) deck overlay Concrete repairs to girders, abutments, wingwalls, piers, curbs, and deck end beams Epoxy injection of crack repairs to abutments, piers, curbs and decks Gravity fed crack repairs to deck and top surfaces of abutments, piers, and curbs Abutment void fill Slope protection – partial removal and replacement Girder shear strengthening (external stirrups) New drain troughs Elastomeric bearing pad replacement Recoat (paint) structural steel Deck drain extensions Sealing existing concrete Asphalt concrete pavement Roadway markings Removal and replacement of vertical clearance signs Addition of bridge plaques
Go To | 23518 | 75340 | 2 | 2026-02-27 | 3 | 2025-2026 | Central | Multiple | Bridge Rehabilitation | Bridge Rehabilitation | Bridge | Concrete | Type-O | 10 x 1320 Type-O | 15 ¦ 29 ¦ 15 | 59 | 17.4 | 2020 | 2027-10-01 | 2 | 26 | Highway 12 | 3 km West of Lacombe | Scope of Work: Traffic accommodation including detours Concrete demolition of approach slabs Construction of new approach slabs Concrete surface removal of bridge deck Cold milling asphalt pavement HPC concrete Expansion joint replacement Deck slab concrete repair Fibre Reinforced High Performance Concrete (FRHPC) deck overlay Concrete repairs to girders, abutments, wingwalls, piers, curbs, and deck end beams Epoxy injection of crack repairs to abutments, piers, curbs and decks Gravity fed crack repairs to deck and top surfaces of abutments, piers, and curbs Abutment void fill Slope protection – partial removal and replacement Girder shear strengthening (external stirrups) New drain troughs Elastomeric bearing pad replacement Recoat (paint) structural steel Deck drain extensions Sealing existing concrete Asphalt concrete pavement Roadway markings Removal and replacement of vertical clearance signs Addition of bridge plaques
Go To | 22934 | 78177 | 2 | 2026-03-12 | 10 | 2025-2026 | Southern | Single | Replace Culvert with Culvert | Construct PBC Culvert | Culvert | Concrete | PBC | 1 x 3000 PBC | 41 | 41 | 3 | 2020 | 2026-10-15 | 549 | 4 | Tributary to Pothole Creek | Near Millarville | Scope of Work: Traffic Accommodation for Bridge Construction, Staged Construction Dust Abatement, If Required Clearing of Swallow Nests, Monitoring and Deterring Further Nesting Activities Total Suspended Solids (TSS) Testing Fish Capture and Release Care of Water and Environmental Management Demolition and Disposal of Existing Culvert Structure Excavation (Structural and Channel) Backfill Supply & Installation of New Single 1.5 m x 3.0 m (inside dimensions), 34.0 m long, Concrete Box Culvert, and Associated Work Waterproofing Top and Sides of Concrete Box Culvert Heavy Rock Riprap – Class 1 Removal of Existing Fence Class B and Wooden Plank Installation and Maintenance of Temporary Fencing Installation of New Class B Fence Installation of New Wooden Plank Fence Erosion and Sediment Control Barriers and Soil Covering Granular Base Reconstruction and Paving Temporary and Permanent Fencing NW Access and Associated Work Removal & Re-Installation of High-Tension Cable Barrier Installation of Permanent Signage Line Painting

## FY 2025-2026
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24815 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabillitation | 2025-2026 | 2025-04-01 | 5 | 2025-10-25
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75726-1 | 10 km Northwest of Ponoka | Central | Local Road | Highway 2 | 5 x 910 FR | 30 ¦ 9 ¦ 30 | 69 | 10.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 90000 | 90000 | 93999.78 | 93999.78 | 9.2%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 80000 | 80000 | 91800.81 | 91800.81 | 41.7%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (B.F. 75726) (BCS 6.4.2) | lump sum | 1 | 120000 | 120000 | 300639.4 | 300639.4 | 17.1%
F020 | Wearing Surface Crack Sealing (Special Provisions) | metre | 250 | 60 | 15000 | 31.04 | 7760 | 72.8%
F018 | Pothole Repairs (Special Provisions) | lump sum | 1 | 10000 | 10000 | 9153.38 | 9153.38 | 28.2%
F760 | Partial Depth Repair - Bridge Curbs (BCS 20.6.2) | square metre | 10 | 3000 | 30000 | 2040.87 | 20408.7 | 43.9%
F760 | Partial Depth Repair - Wingwalls (BCS 20.6.2) | square metre | 10 | 3500 | 35000 | 2995.92 | 29959.2 | 18.5%
F020 | Concrete Crack Sealing - Gravity Flow Sealant (Special Provisions) | metre | 50 | 130 | 6500 | 172.72 | 8636 | 30.6%
F022 | Concrete Sealer - Type 1c (Special Provisions) | square metre | 50 | 60 | 3000 | 98.33 | 4916.5 | 61.6%
F022 | Concrete Sealer - Pigmented (Special Provisions) | square metre | 150 | 60 | 9000 | 277.18 | 41577 | 85.2%
F018 | Recast Pier Grout Pads (Special Provisions) | lump sum | 1 | 80000 | 80000 | 7511.53 | 7511.53 | 33.8%
F018 | Bridge Rail Repair (Special Provisions) | lump sum | 1 | 15000 | 15000 | 8839.71 | 8839.71 | 10.2%
F018 | Approach Rail Transition - Supply and Install (Special Provisions) | lump sum | 1 | 100000 | 100000 | 40982.28 | 40982.28 | 84.9%
F018 | Remove Approach ACP Curb (Special Provisions) | lump sum | 1 | 35000 | 35000 | 3458.04 | 3458.04 | 40.8%
F911 | Drain Troughs (BCS 9.7) | metre | 60 | 2500 | 150000 | 968.65 | 58119 | 17.3%
F018 | Slope Protection Repair (Special Provisions) | lump sum | 1 | 25000 | 25000 | 14311.45 | 14311.45 | 18%
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 5000 | 5000 | 7714.06 | 7714.06 | 9.4%
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 50000 | 50000 | 50000 | 50000 | 0%
|  | Bridge File Modified Tender Value |  |  | 858500 |  | 799786.84 | 2.4%
|  | Total Tender Value |  |  |  |  | 926288.33 | 4.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 55 | 82500 | 77 | 115500 | 21.5%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 3 | 4500 | 7 | 10500 | 30.9%
Tender: 24815 ¦ Bridge File: 75726-1 ¦ Tender Opening Date: 2025-04-01
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24779 | Construct SLW Precast Concrete Girder Bridge | Bridge | Multiple | Replace Bridge with Bridge | 2025-2026 | 2025-04-03 | 5 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
72485-2 | 30 km Southeast of Manning | Peace | 690:02 | Tributary to Rousseau Creek | 8 x 510 SLW | 6 ¦ 12 ¦ 6 | 24 | 9.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 183000 | 183000 | 173333.33 | 173333.33 | 7.2%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 20000 | 20000 | 13850 | 13850 | 20.2%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 80000 | 80000 | 18900.33 | 18900.33 | 71.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 2000 | 20000 | 587.67 | 5876.7 | 139.9%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 160000 | 160000 | 81666.67 | 81666.67 | 27.5%
F812 | Supply of Piling - Plain Steel H-Pile - HP310X94 (BCS 3.6.1) | metre | 305 | 280 | 85400 | 190.33 | 58050.65 | 18.6%
F813 | Supply of Piling - Galvanized Steel H-Pile - HP310X94 (BCS 3.6.1) | metre | 92 | 300 | 27600 | 290.67 | 26741.64 | 16.9%
F816 | Pile Set-up (Driven Piles) - H-Pile 310X94 (BCS 3.6.1) | pile | 32 | 5000 | 160000 | 3616.67 | 115733.44 | 28%
F818 | Pile Driving - H-Pile 310X94 (BCS 3.6.1) | metre | 397 | 60 | 23820 | 7 | 2779 | 30.9%
F820 | PDA Testing (BCS 3.6.4) | test | 4 | 3000 | 12000 | 3433.33 | 13733.32 | 48.2%
F018 | Abutment Construction (Special Provisions) | lump sum | 1 | 80000 | 80000 | 184000 | 184000 | 6.2%
F018 | Pier Construction (Special Provisions) | lump sum | 1 | 40000 | 40000 | 83933.33 | 83933.33 | 17.9%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 225 | 350 | 78750 | 338.33 | 76124.25 | 35.3%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - Type SLW510 (BCS 7.4) (Special Provisions) | lump sum | 1 | 600000 | 600000 | 500000 | 500000 | 9.7%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1440 | 8 | 11520 | 10 | 14400 | 0%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1440 | 3 | 4320 | 2.5 | 3600 | 16.3%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 11 | 3000 | 33000 | 4300 | 47300 | 18.7%
F974 | Waterproofing (BCS 16.5) | square metre | 270 | 125 | 33750 | 82 | 22140 | 3.4%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 82 | 450 | 36900 | 646.33 | 52999.06 | 16.5%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 80000 | 80000 | 144300 | 144300 | 24.8%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 2000 | 2000 | 2026.67 | 2026.67 | 30%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 50000 | 50000 | 35433.33 | 35433.33 | 36.1%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 200 | 30 | 6000 | 16.67 | 3334 | 40.8%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 600 | 15 | 9000 | 14.67 | 8802 | 31.6%
|  | Bridge File Modified Tender Value |  |  | 1837060 |  | 1689057.72 | 4.7%
|  | Total Tender Value |  |  |  |  | 3020916.67 | 1.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 120 | 180000 | 57 | 85500 | 39.4%
Tender: 24779 ¦ Bridge File: 72485-2 ¦ Tender Opening Date: 2025-04-03
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24779 | Construct SLW Precast Concrete Girder Bridge | Bridge | Multiple | Replace Bridge with Bridge | 2025-2026 | 2025-04-03 | 5 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
72488-2 | 33 km Southeast of Manning | Peace | 690:02 | Rousseau Creek | 8 x 510 SLW | 14 | 14 | 9.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 137000 | 137000 | 123333.33 | 123333.33 | 5.1%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 20000 | 20000 | 9390 | 9390 | 51.6%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 60000 | 60000 | 18900.33 | 18900.33 | 71.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 2000 | 20000 | 587 | 5870 | 140.1%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 160000 | 160000 | 81666.67 | 81666.67 | 27.5%
F812 | Supply of Piling - Plain Steel H-Pile - HP310X94 (BCS 3.6.1) | metre | 234 | 280 | 65520 | 190.33 | 44537.22 | 18.6%
F813 | Supply of Piling - Galvanized Steel H-Pile - HP310X94 (BCS 3.6.1) | metre | 32 | 300 | 9600 | 290.67 | 9301.44 | 16.9%
F816 | Pile Set-up (Driven Piles) - H-Pile 310X94 (BCS 3.6.1) | pile | 20 | 5000 | 100000 | 4133.33 | 82666.6 | 26.3%
F818 | Pile Driving - H-Pile 310X94 (BCS 3.6.1) | metre | 266 | 60 | 15960 | 7 | 1862 | 30.9%
F820 | PDA Testing (BCS 3.6.4) | test | 2 | 3000 | 6000 | 3350 | 6700 | 52.7%
F018 | Abutment Construction (Special Provisions) | lump sum | 1 | 80000 | 80000 | 156666.67 | 156666.67 | 10.5%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 100 | 350 | 35000 | 398.67 | 39867 | 20.5%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - Type SLW510 (BCS 7.4) | lump sum | 1 | 400000 | 400000 | 273533.33 | 273533.33 | 18.7%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1440 | 8 | 11520 | 10 | 14400 | 0%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1440 | 3 | 4320 | 2.5 | 3600 | 16.3%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 11 | 3000 | 33000 | 4300 | 47300 | 18.7%
F974 | Waterproofing (BCS 16.5) | square metre | 180 | 125 | 22500 | 96.33 | 17339.4 | 24%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28)Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 65 | 450 | 29250 | 695 | 45175 | 19.9%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 100000 | 100000 | 148533.33 | 148533.33 | 20.5%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 30000 | 30000 | 30083.33 | 30083.33 | 36%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 200 | 30 | 6000 | 16.67 | 3334 | 40.8%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 600 | 15 | 9000 | 14.67 | 8802 | 31.6%
|  | Bridge File Modified Tender Value |  |  | 1354670 |  | 1172861.65 | 5.9%
|  | Total Tender Value |  |  |  |  | 3020916.67 | 1.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 100 | 150000 | 49 | 73500 | 46%
Tender: 24779 ¦ Bridge File: 72488-2 ¦ Tender Opening Date: 2025-04-03
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22891 | Construct SLW Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2025-2026 | 2025-04-29 | 5 | 2025-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
80940-2 | 82 km Northeast of Enilda | Peace | 750:06 | Utikuma River | 9 x 510 SLW | 8 ¦ 14 ¦ 8 | 30 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 300000 | 300000 | 307866.71 | 307866.71 | 7.5%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 350000 | 350000 | 394000 | 394000 | 25.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 20 | 2000 | 40000 | 1700 | 34000 | 4.2%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 200000 | 200000 | 252636 | 252636 | 7.6%
F018 | Headslope Preparation and Backfill (Special Provisions) | lump sum | 1 | 55000 | 55000 | 165333.33 | 165333.33 | 64.5%
F812 | Supply of Piling - Plain Steel H-Pile - 310 x 94 mm (BCS 3.6.1) | metre | 575 | 340 | 195500 | 220.33 | 126689.75 | 20.1%
F813 | Supply of Piling - Galvanized Steel H-Pile - 310 x 94 mm (BCS 3.6.1) | metre | 110 | 350 | 38500 | 317.33 | 34906.3 | 14.3%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 36 | 5000 | 180000 | 3854.33 | 138755.88 | 66.1%
F818 | Pile Driving (BCS 3.6.1) | metre | 685 | 61 | 41785 | 109.33 | 74891.05 | 88.4%
F820 | PDA Testing (BCS 3.6.4) | test | 8 | 1937 | 15496 | 3060 | 24480 | 16.3%
F018 | Abutment, Pier and Wingwall Construction (Special Provisions) | lump sum | 1 | 210000 | 210000 | 283333.33 | 283333.33 | 12.7%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (18 - 8 m SLW-510) (BCS 7.4) | lump sum | 1 | 360000 | 360000 | 315000 | 315000 | 2.9%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (9-14 m SLW-510) (BCS 7.4) | lump sum | 1 | 279000 | 279000 | 260333.33 | 260333.33 | 12.9%
F018 | Approach Slabs (Special Provisions) | lump sum | 1 | 40000 | 40000 | 65333.33 | 65333.33 | 39.4%
F974 | Waterproofing (BCS 16.5) | square metre | 366 | 100 | 36600 | 71.33 | 26106.78 | 18.8%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (B.F. _____) (BCS 12.4) | lump sum | 1 | 35000 | 35000 | 44966.67 | 44966.67 | 7.8%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 35000 | 35000 | 51633.33 | 51633.33 | 2.4%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 170 | 450 | 76500 | 676.33 | 114976.1 | 19.2%
F492 | Roadway Work (Special Provisions) (BCS 18.7) | lump sum | 1 | 75000 | 75000 | 106666.67 | 106666.67 | 25.6%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 225 | 375 | 84375 | 375.33 | 84449.25 | 45.7%
E020 | Rock Ditch Drains - Class 1M (Special Provisions) | metre | 20 | 450 | 9000 | 866.67 | 17333.4 | 30.6%
E020 | Erosion Control Barrier (Straw Roll) (Special Provisions) | metre | 200 | 15 | 3000 | 40 | 8000 | 28.3%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 685 | 15 | 10275 | 17.67 | 12103.95 | 46.3%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 70 | 15 | 1050 | 98 | 6860 | 81.1%
|  | Bridge File Modified Tender Value |  |  | 2671081 |  | 2950655.16 | 5.7%
|  | Total Tender Value |  |  |  |  | 3110660.05 | 6.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 107 | 160500 | 23.3%
Tender: 22891 ¦ Bridge File: 80940-2 ¦ Tender Opening Date: 2025-04-29
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20364 | Construct CSP Culvert | Culvert | Complex | Replace Culvert with Culvert | 2025-2026 | 2025-05-01 | 5 | 2026-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
109-2 | Near Tofield | Central | 834:04 | Hastings Creek | 2 x 2200 CSP | 37 - 37 | 74 | 2.2
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 46022.01 | 46022.01 | 83178.79 | 83178.79 | 5.1%
F750 | Traffic Accommodation for Bridge Construction (B.F. 109) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 150000 | 150000 | 188333.33 | 188333.33 | 23.2%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 15000 | 15000 | 26000 | 26000 | 0%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 5 | 2500 | 12500 | 2300 | 11500 | 0%
E018 | Fish Capture and Release (Special Provisions) | lump sum | 1 | 20000 | 20000 | 8500 | 8500 | 0%
F170 | Demolition and Disposal of Bridge Structure (B.F. 109) (BCS 21.4.1) | lump sum | 1 | 20000 | 20000 | 29950 | 29950 | 0%
F495 | CSP with Couplers - Supply (B.F. 109) (BCS 18.7) | metre | 74 | 1100 | 81400 | 705 | 52170 | 0%
F496 | CSP - Assembly (B.F. 109) (BCS 18.7) | metre | 74 | 140 | 10360 | 962 | 71188 | 0%
F190 | Backfill (B.F. 109) (BCS 2.4) | lump sum | 1 | 45000 | 45000 | 95995 | 95995 | 0%
F500 | Heavy Rock Riprap (Class 1) (B.F. 109) (BCS 10.7) | cubic metre | 80 | 250 | 20000 | 220 | 17600 | 0%
F186 | Excavation - Structural (B.F. 109) (BCS 1.6.1) | lump sum | 1 | 80000 | 80000 | 35040 | 35040 | 0%
E020 | Straw Roll (Fibre Roll) - Supply and Install (Special Provisions) | metre | 200 | 25 | 5000 | 45 | 9000 | 0%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 5 | 1000 | 23 | 4600 | 0%
|  | Bridge File Modified Tender Value |  |  | 506282.01 |  | 633055.12 | 7.3%
|  | Total Tender Value |  |  |  |  | 38884658.13 | 3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 50 | 75000 | 0%
Tender: 20364 ¦ Bridge File: 109-2 ¦ Tender Opening Date: 2025-05-01
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20364 | Construct SPCSP Culvert | Culvert | Complex | Replace Bridge with Culvert | 2025-2026 | 2025-05-01 | 5 | 2026-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
237-2 | Near Chipman | Central | 834:04 | Norris Creek | 1 x 3360 SPCSP | 39 | 39 | 3.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 63205.81 | 63205.81 | 94092.9 | 94092.9 | 6.2%
F750 | Traffic Accommodation for Bridge Construction (B.F. 237) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 150000 | 150000 | 165000 | 165000 | 36.4%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 15000 | 15000 | 20500 | 20500 | 0%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 5 | 2500 | 12500 | 2300 | 11500 | 0%
E018 | Fish Capture and Release (Special Provisions) | lump sum | 1 | 20000 | 20000 | 10625 | 10625 | 0%
F170 | Demolition and Disposal of Bridge Structure (B.F. 237) (BCS 21.4.1) | lump sum | 1 | 30000 | 30000 | 26000 | 26000 | 0%
F186 | Excavation - Structural (B.F. 237) (BCS 1.6.1) | lump sum | 1 | 60000 | 60000 | 35000 | 35000 | 0%
F493 | SPCSP - Supply (B.F. 273) (BCS 18.7) | metre | 39.01 | 3990 | 155649.9 | 2073.33 | 80880.6 | 0.9%
F494 | SPCSP - Assembly (B.F. 273) (BCS 18.7) | metre | 39.01 | 1300 | 50713 | 2366.67 | 92323.8 | 1%
F190 | Backfill (B.F. 273) (BCS 2.4) | lump sum | 1 | 56000 | 56000 | 99270 | 99270 | 0%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 45000 | 45000 | 40000 | 40000 | 0%
F500 | Heavy Rock Riprap (Class 1) (B.F. 237) (BCS 10.7) | cubic metre | 125 | 250 | 31250 | 220 | 27500 | 0%
E020 | Straw Roll (Fibre Roll) - Supply and Install (Special Provisions) | metre | 200 | 25 | 5000 | 45 | 9000 | 0%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 5 | 1000 | 23 | 4600 | 0%
|  | Bridge File Modified Tender Value |  |  | 695318.71 |  | 716292.3 | 8.9%
|  | Total Tender Value |  |  |  |  | 38884658.13 | 3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 55 | 82500 | 0%
Tender: 20364 ¦ Bridge File: 237-2 ¦ Tender Opening Date: 2025-05-01
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20364 | Construct SPCSP Culvert | Culvert | Complex | Replace Culvert with Culvert | 2025-2026 | 2025-05-01 | 5 | 2026-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
416-2 | Near Tofield | Central | 834:04 | Katchemut Creek | 1 x 3670 SPCSP | 50 | 50 | 3.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 80912.69 | 80912.69 | 111594.43 | 111594.43 | 5.3%
F750 | Traffic Accommodation for Bridge Construction (B.F. 416) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 150000 | 150000 | 165666.67 | 165666.67 | 36%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 15000 | 15000 | 30000 | 30000 | 0%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 5 | 2500 | 12500 | 2300 | 11500 | 0%
E018 | Fish Capture and Release (Special Provisions) | lump sum | 1 | 20000 | 20000 | 10625 | 10625 | 0%
F170 | Demolition and Disposal of Bridge Structure (B.F. 416) (BCS 21.4.1) | lump sum | 1 | 30000 | 30000 | 37200 | 37200 | 0%
F493 | SPCSP - Supply (B.F. 416) (BCS 18.7) | metre | 49.99 | 3990 | 199460.1 | 2163.33 | 108144.87 | 1.2%
F494 | SPCSP - Assembly (B.F. 416) (BCS 18.7) | metre | 49.99 | 1300 | 64987 | 2046.67 | 102313.03 | 1.8%
F190 | Backfill (B.F. 416) (BCS 2.4) | lump sum | 1 | 80000 | 80000 | 141590 | 141590 | 0%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 45000 | 45000 | 40000 | 40000 | 0%
F500 | Heavy Rock Riprap (Class 1) (B.F. 416) (BCS 10.7) | cubic metre | 105 | 250 | 26250 | 220 | 23100 | 0%
F186 | Excavation - Structural (B.F. 416) (BCS 1.6.1) | lump sum | 1 | 160000 | 160000 | 53550 | 53550 | 0%
E020 | Straw Roll (Fibre Roll) - Supply and Install (Special Provisions) | metre | 200 | 25 | 5000 | 45 | 9000 | 0%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 5 | 1000 | 23 | 4600 | 0%
|  | Bridge File Modified Tender Value |  |  | 890109.79 |  | 848884 | 7.3%
|  | Total Tender Value |  |  |  |  | 38884658.13 | 3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 55 | 82500 | 0%
Tender: 20364 ¦ Bridge File: 416-2 ¦ Tender Opening Date: 2025-05-01
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20364 | Construct SPCSP Culvert | Culvert | Complex | Replace Culvert with Culvert | 2025-2026 | 2025-05-01 | 5 | 2026-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
708-2 | Near Tofield | Central | 834:04 | Wakinagan Creek | 1 x 3360 SPCSP | 43 | 43 | 3.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 68541.48 | 68541.48 | 106230.71 | 106230.71 | 4.6%
F750 | Traffic Accommodation for Bridge Construction (B.F. 708) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 150000 | 150000 | 184250 | 184250 | 25.2%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 15000 | 15000 | 26000 | 26000 | 0%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 5 | 2500 | 12500 | 2300 | 11500 | 0%
E018 | Fish Capture and Release (Special Provisions) | lump sum | 1 | 20000 | 20000 | 10625 | 10625 | 0%
F170 | Demolition and Disposal of Bridge Structure (B.F. 708) (BCS 21.4.1) | lump sum | 1 | 30000 | 30000 | 33620 | 33620 | 0%
F186 | Excavation - Structural (B.F. 708) (BCS 1.6.1) | lump sum | 1 | 80000 | 80000 | 49000 | 49000 | 0%
F493 | SPCSP - Supply (B.F. 708) (BCS 18.7) | metre | 42.67 | 3990 | 170253.3 | 2056.67 | 87758.11 | 1.5%
F494 | SPCSP - Assembly (B.F. 708) (BCS 18.7) | metre | 42.67 | 1300 | 55471 | 2195.33 | 93674.73 | 0.2%
F190 | Backfill (B.F. 708) (BCS 2.4) | lump sum | 1 | 60000 | 60000 | 115125 | 115125 | 0%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 45000 | 45000 | 40000 | 40000 | 0%
F500 | Heavy Rock Riprap (Class 1) (B.F. 708) (BCS 10.7) | cubic metre | 165 | 250 | 41250 | 220 | 36300 | 0%
E020 | Straw Roll (Fibre Roll) - Supply and Install (Special Provisions) | metre | 200 | 25 | 5000 | 45 | 9000 | 0%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 5 | 1000 | 23 | 4600 | 0%
|  | Bridge File Modified Tender Value |  |  | 754015.78 |  | 807683.55 | 5.9%
|  | Total Tender Value |  |  |  |  | 38884658.13 | 3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 55 | 82500 | 0%
Tender: 20364 ¦ Bridge File: 708-2 ¦ Tender Opening Date: 2025-05-01
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22515 | Construct Precast Box Concrete Girder Bridge | Bridge | Complex | Replace Bridge with Bridge | 2025-2026 | 2025-05-02 | 4 | 2026-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
2143E-4 | 19 km West of Calgary | Southern | 8:06 | Elbow River | 11 x 900 PB | 27 ¦ 30 ¦ 27 | 84 | 14.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 1273404.4 | 1273404.4 | 1447959.81 | 1447959.81 | 18.3%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 165781.26 | 165781.26 | 290617.92 | 290617.92 | 43.5%
F994 | Temporary Access Berms, Cofferdams and Dikes (BCS 1.6.2) (Special Provisions) | lump sum | 1 | 1200000 | 1200000 | 518480.7 | 518480.7 | 47.6%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 350000 | 350000 | 330592.89 | 330592.89 | 22%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 150000 | 150000 | 82160.99 | 82160.99 | 26.7%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 150000 | 150000 | 353237.2 | 353237.2 | 21.8%
F505 | Heavy Rock Riprap (Class 1M) (BCS 10.7) (Special Provisions) | cubic metre | 298 | 350 | 104300 | 293.31 | 87406.38 | 7%
F515 | Heavy Rock Riprap (Class 2) (BCS 10.7) (Special Provisions) | cubic metre | 1320 | 500 | 660000 | 221.88 | 292881.6 | 15.3%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 570 | 460 | 262200 | 368.57 | 210084.9 | 2.4%
F819 | Pile Tip Reinforcement (BCS 3.6.1) | pile | 34 | 640 | 21760 | 312.81 | 10635.54 | 12.7%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 34 | 10000 | 340000 | 8707.66 | 296060.44 | 6.3%
F818 | Pile Driving (BCS 3.6.1) | metre | 570 | 56 | 31920 | 25.3 | 14421 | 108.2%
F820 | PDA Testing (BCS 3.6.4) | test | 10 | 2500 | 25000 | 1846.91 | 18469.1 | 4.8%
F824 | Drill Rig Set-up (Drilled Piles) (BCS 3.6.2) | pile | 6 | 22500 | 135000 | 58512.41 | 351074.46 | 17.6%
F826 | Pile Installation (Drilled Piles) (BCS 3.6.2) | metre | 120 | 2750 | 330000 | 2468.82 | 296258.4 | 5.7%
F833 | Concrete (Class Tremie) - Supply and Place (BCS 4.27.1) | cubic metre | 266 | 1400 | 372400 | 815.36 | 216885.76 | 19%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 96514 | 3.65 | 352276.1 | 2.62 | 252866.68 | 9.5%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 96191 | 20.5 | 1971915.5 | 10.01 | 962871.91 | 1.6%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 192705 | 2.7 | 520303.5 | 1.31 | 252443.55 | 6.9%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 377 | 2130 | 803010 | 2447.86 | 922843.22 | 10.3%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 518 | 2580 | 1336440 | 2437.29 | 1262516.22 | 6.8%
F906 | Bearings - Supply and Fabrication, Delivery and Installation (BCS 8.5) | lump sum | 1 | 13500 | 13500 | 23362.76 | 23362.76 | 16.7%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - End Span Girders (BCS 7.4) | lump sum | 1 | 1950000 | 1950000 | 2033784.3 | 2033784.3 | 16.3%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - Main Span Girders (BCS 7.4) | lump sum | 1 | 1100000 | 1100000 | 1076981.32 | 1076981.32 | 11.5%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 155000 | 155000 | 229170.75 | 229170.75 | 16.4%
F974 | Waterproofing (BCS 16.5) | square metre | 1287 | 113 | 145431 | 50.45 | 64929.15 | 12.6%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 237 | 325 | 77025 | 351.67 | 83345.79 | 12.7%
F911 | Drain Troughs (BCS 9.7) | metre | 20 | 1000 | 20000 | 1055.03 | 21100.6 | 39.2%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 20000 | 20000 | 53108.17 | 53108.17 | 44.1%
|  | Bridge File Modified Tender Value |  |  | 14036666.76 |  | 12056551.51 | 4%
|  | Total Tender Value |  |  |  |  | 31293771.2 | 8.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy - Bridge Construction and Sign Structure Construction (GCS 1.2.41.9) | day | 1500 | - | - | 278 | 417000 | 10.9%
Tender: 22515 ¦ Bridge File: 2143-4 ¦ Tender Opening Date: 2025-05-02
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22515 | Construct Sign Structures | Sign Structure | Complex | New Sign Structures | 2025-2026 | 2025-05-02 | 4 | 2026-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
Multiple | Hwy 8 West of Calgary | Southern | - | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 49435.15 | 49435.15 | 61713.96 | 61713.96 | 32%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 6435.84 | 6435.84 | 11361.19 | 11361.19 | 32.5%
F018 | Overhead Sign Structure - Foundation Supply & Installation and Structure Installation (B.F. 82475ZE1) (Special Provisions) | lump sum | 1 | 140000 | 140000 | 125527.39 | 125527.39 | 14.7%
F018 | Overhead Sign Structure - Foundation Supply & Installation and Structure Installation (B.F. 82475ZE2) (Special Provisions) | lump sum | 1 | 140000 | 140000 | 125841.05 | 125841.05 | 13.9%
F018 | Overhead Sign Structure - Foundation Supply & Installation and Structure Installation (B.F. 77546ZW1) (Special Provisions) | lump sum | 1 | 170000 | 170000 | 131247.39 | 131247.39 | 7.7%
F992 | Sign Panels - Extruded Aluminum - Supply and Install (BCS 24.5) | square metre | 21 | 650 | 13650 | 598.08 | 12559.68 | 3.8%
F022 | Sign Panels - Extruded Aluminum - Install (Special Provisions) | square metre | 67 | 200 | 13400 | 217.04 | 14541.68 | 4.7%
F046 | Overhead Sign Structure - Sign Panel Removal and Installation (Special Provisions) | panel | 1 | 12000 | 12000 | 17887.22 | 17887.22 | 34.3%
|  | Bridge File Modified Tender Value |  |  | 544920.99 |  | 500679.56 | 11.5%
|  | Total Tender Value |  |  |  |  | 31293771.2 | 8.1%
Tender: 22515 ¦ Bridge File: Multiple ¦ Tender Opening Date: 2025-05-02
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23931 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2025-2026 | 2025-05-06 | 4 | 2026-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76392-1 | At Dewinton | Southern | 2A:06 | Highway 2 | 10 x 1320 VF | 38 ¦ 38 | 76 | 16.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 352000 | 352000 | 341666.67 | 341666.67 | 9.1%
F750 | Traffic Accommodation for Bridge Construction (B.F. 76392-1) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 270000 | 270000 | 289021.33 | 289021.33 | 14%
F018 | Bridge Washing (Special Provisions) | lump sum | 1 | 15000 | 15000 | 22560.67 | 22560.67 | 72.3%
F018 | Consultant's Level 1.5 Inspection Access (Special Provisions) | lump sum | 1 | 20000 | 20000 | 17639.67 | 17639.67 | 47.5%
F018 | Remove, Salvage and Reinstall Existing Median Delineators (Special Provisions) | lump sum | 1 | 25000 | 25000 | 29465 | 29465 | 36.6%
F018 | Remove and Dispose of Existing Deck Joint Assemblies incl. End Dams (3 Locations) (Special Provisions) | lump sum | 1 | 70000 | 70000 | 95508 | 95508 | 66.4%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (B.F. 76392-1) Type 1 Strip Seal (3 Locations) (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 235000 | 235000 | 269339 | 269339 | 15.3%
F853 | Stainless Reinforcing Steel - Supply (B.F. 76932-1) Deck Joint End Dams (BCS 5.6) (Special Provisions) | kilogram | 1450 | 20 | 29000 | 20.67 | 29971.5 | 12.1%
F854 | Reinforcing Steel - Place (B.F. 76932-1) Deck Joint End Dams (BCS 5.6) (Special Provisions) | kilogram | 1450 | 2.5 | 3625 | 5.67 | 8221.5 | 36.2%
F052 | Reinforcing Steel - Dowel Install - (B.F. 76392) Deck Joint End Dams (Special Provisions) | unit | 935 | 50 | 46750 | 37 | 34595 | 32.5%
F841 | Concrete (Class HPC) - Supply and Place (B.F. 76392-1) Deck Joint End Dams (BCS 4.27.1) (Special Provisions) | cubic metre | 6 | 3500 | 21000 | 5387.67 | 32326.02 | 11%
F755 | Surface Removal (B.F. 76392-1) Bridge Deck and Roof Slabs (BCS 20.6.1) (Special Provisions) | square metre | 1375 | 150 | 206250 | 121.33 | 166828.75 | 13.5%
F760 | Partial Depth Repair - Deck Top (BCS 20.6.2) (Special Provisions) | square metre | 90 | 1700 | 153000 | 1130.67 | 101760.3 | 29.1%
F760 | Partial Depth Repair - Girders, Curb Fascia, and Precast Side Panels (BCS 20.6.2) (Special Provisions) | square metre | 8 | 5000 | 40000 | 3291.33 | 26330.64 | 36.7%
F760 | Partial Depth Repair - Curb (Interior Faces) (BCS 20.6.2) (Special Provisions) | square metre | 8 | 2500 | 20000 | 1949.67 | 15597.36 | 21.3%
F760 | Partial Depth Repair - Pier Cap and Pier Shaft (BCS 20.6.2) (Special Provisions) | square metre | 15 | 4500 | 67500 | 2667.33 | 40009.95 | 30.8%
F760 | Partial Depth Repair - Abutments (BCS 20.6.2) (Special Provisions) | square metre | 6 | 4000 | 24000 | 2290.33 | 13741.98 | 6.1%
F765 | Full Depth Repair - Girder Concrete Diaphragms (BCS 20.6.2) (Special Provisions) | square metre | 4 | 6000 | 24000 | 5460.67 | 21842.68 | 10.3%
F765 | Full Depth Repair - Headslope Protection (BCS 20.6.2) (Special Provisions) | square metre | 2 | 2000 | 4000 | 2405.67 | 4811.34 | 11.9%
F053 | Galvanic Corrosion Protection - Install (Special Provisions) | unit | 350 | 30 | 10500 | 57 | 19950 | 71.4%
F020 | Crack Sealing - Gravity Fed Repair - Horizontal (Deck) (Special Provisions) | metre | 400 | 150 | 60000 | 144.67 | 57868 | 47.8%
F020 | Crack Sealing - Pressure Injection - Vertical or Overhead (Girders, Diaphragms, and Pier) (Special Provisions) | metre | 35 | 750 | 26250 | 614.33 | 21501.55 | 49.3%
F770 | Abrasive Blasting - Deck Surface (B.F. 76392-1) Bridge Deck and Roof Slabs (BCS 20.6.3) (Special Provisions) | square metre | 1375 | 50 | 68750 | 20.67 | 28421.25 | 34.5%
F775 | Deck Overlay Concrete - Supply (B.F. 76392-1) Class HPC with Steel Fibres (BCS 20.6.4) (Special Provisions) | cubic metre | 69 | 2500 | 172500 | 1937.33 | 133675.77 | 16.1%
F776 | Deck Overlay Concrete - Place (B.F. 76392-1) Class HPC with Steel Fibres (BCS 20.6.4) (Special Provisions) | square metre | 1375 | 175 | 240625 | 106.67 | 146671.25 | 24.6%
F053 | Existing Lateral Stressing Strands - Anchor Chuck Paint Repairs (Special Provisions) | unit | 160 | 250 | 40000 | 330.67 | 52907.2 | 38.6%
F018 | Bridgerail - Grout Pad Repairs and Baseplate Coating Repairs (Special Provisions) | lump sum | 1 | 50000 | 50000 | 30921.33 | 30921.33 | 69.1%
F053 | Bearing - Grout Pad Repairs (Special Provisions) | unit | 40 | 1000 | 40000 | 702 | 28080 | 10.5%
F053 | Bearing - Masonry Plate Coating Repairs (Special Provisions) | unit | 80 | 750 | 60000 | 1336.33 | 106906.4 | 51.7%
F018 | Shear Block Replacement - Pier Cap Below Girder 2 (Special Provisions) | lump sum | 1 | 10000 | 10000 | 18129.67 | 18129.67 | 31.2%
F022 | Remove Parging & Sack Rub - Abutment 2 (Special Provisions) | square metre | 14 | 200 | 2800 | 326.67 | 4573.38 | 20.8%
F018 | Roof Slab Inspection Access (Special Provisions) | lump sum | 1 | 25000 | 25000 | 23818 | 23818 | 52.5%
F021 | Void Grout - Under Approach Slab at Abutment 1 (Special Provisions) | cubic metre | 2 | 2500 | 5000 | 3768.67 | 7537.34 | 42%
F020 | Curb Control Joint Sealing Replacement (Special Provisions) | metre | 4 | 250 | 1000 | 289 | 1156 | 35.3%
F022 | Concrete Cleaning and Sealing - Type 1c - Curbs (Special Provisions) | square metre | 200 | 100 | 20000 | 47.67 | 9534 | 33.2%
F022 | Concrete Cleaning and Sealing - Type 3 - Exterior Girders, Curb Fascia, and Precast Side Panels (Special Provisions) | square metre | 360 | 250 | 90000 | 61.67 | 22201.2 | 26.8%
F022 | Concrete Cleaning and Sealing - Type 3 - Pier and Abutments (Special Provisions) | square metre | 320 | 100 | 32000 | 56.33 | 18025.6 | 18.4%
F018 | Bridge Plaque - Supply and Install (Special Provisions) | lump sum | 1 | 2500 | 2500 | 3137.33 | 3137.33 | 26.1%
Q018 | Approach Road Transitions - Milling and Pavement - Approach Slabs and Approach Roads Tie-ins (Special Provisions) | lump sum | 1 | 60000 | 60000 | 93721.33 | 93721.33 | 2.9%
S350 | Roadway Lines - Supplying Paint and Painting (Directional Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.3 | 10000 | 3000 | 8670 | 2601 | 35.6%
S352 | Roadway Lines - Supplying Paint and Painting (Lane Dividing Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.3 | 10000 | 3000 | 2016.67 | 605 | 15.2%
S341 | Durable Pavement Message - Turn or Straight Arrows (Single or Double) (HCS 7.3.5) (HCS 5.20.5) | message | 5 | 1000 | 5000 | 950 | 4750 | 18.7%
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | 100000 | 100000 | 0%
|  | Bridge File Modified Tender Value |  |  | 2754050 |  | 2497929.96 | 9.3%
|  | Total Tender Value |  |  |  |  | 3501913.33 | 9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 3000 | 90 | 270000 | 120 | 360000 | 20.8%
F003 | Lane Closure for Bridge Construction - HWY 2A (GCS 1.2.42.5) (Special Provisions) | day | 3500 | 90 | 315000 | 125 | 437500 | 6.2%
F003 | Lane Closure for Bridge Construction - HWY 2 NB (GCS 1.2.42.5) (Special Provisions) | day | 7500 | 15 | 112500 | 14 | 105000 | 30.9%
F003 | Lane Closure for Bridge Construction - HWY 2 SB (GCS 1.2.42.5) (Special Provisions) | day | 7500 | 15 | 112500 | 14 | 105000 | 32.1%
Tender: 23931 ¦ Bridge File: 76392-1 ¦ Tender Opening Date: 2025-05-06
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
12477 | Construct SLW Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2025-2026 | 2025-05-08 | 5 | 2025-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
1704-2 | 4 km East of Trochu | Central | 585:02 | Ghostpine Creek | 8 x 510 SLW | 14 | 14 | 9.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 180000 | 180000 | 234026.51 | 234026.51 | 20.8%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 150000 | 150000 | 258185.95 | 258185.95 | 23.1%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 15000 | 15000 | 18736.38 | 18736.38 | 61.7%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 1732.84 | 5198.52 | 58.9%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 4 | 1500 | 6000 | 2632.09 | 10528.36 | 58.2%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 75000 | 75000 | 103507.26 | 103507.26 | 62.2%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 23841.77 | 23841.77 | 79.6%
F813 | Supply of Piling - Galvanized Steel H-Pile (BCS 3.6.1) | metre | 165 | 400 | 66000 | 292.09 | 48194.85 | 13.5%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 393 | 300 | 117900 | 191.82 | 75385.26 | 20.8%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 40 | 5000 | 200000 | 3804.29 | 152171.6 | 52.6%
F818 | Pile Driving (BCS 3.6.1) | metre | 558 | 75 | 41850 | 46.98 | 26214.84 | 70.5%
F018 | Abutment Construction (Special Provisions) | lump sum | 1 | 150000 | 150000 | 252151.79 | 252151.79 | 11.9%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1517 | 9 | 13653 | 13.54 | 20540.18 | 30%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1517 | 3 | 4551 | 3.52 | 5339.84 | 11.6%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 13 | 3000 | 39000 | 2313.72 | 30078.36 | 9.6%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 100 | 300 | 30000 | 316.95 | 31695 | 24.7%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) | lump sum | 1 | 310000 | 310000 | 248193.36 | 248193.36 | 3.9%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 5000 | 5000 | 2557.79 | 2557.79 | 13.3%
F974 | Waterproofing (BCS 16.5) | square metre | 180 | 100 | 18000 | 116.74 | 21013.2 | 5.3%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 35 | 650 | 22750 | 521.18 | 18241.3 | 47%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 150000 | 150000 | 191710.16 | 191710.16 | 16.7%
F018 | Drain Troughs - Supply and Install (Special Provisions) | lump sum | 1 | 80000 | 80000 | 33647.49 | 33647.49 | 13.4%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 25000 | 25000 | 18079.61 | 18079.61 | 9.6%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 80000 | 80000 | 67835.47 | 67835.47 | 9.1%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.4 | 10000 | 4000 | 23559.24 | 9423.7 | 21.4%
E020 | Straw Rolls (Special Provisions) | metre | 200 | 20 | 4000 | 17.91 | 3582 | 16.5%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 2000 | 10 | 20000 | 4.34 | 8680 | 59.8%
|  | Bridge File Modified Tender Value |  |  | 1844704 |  | 1918760.55 | 8.7%
|  | Total Tender Value |  |  |  |  | 2048771.67 | 9.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 50 | 75000 | 87 | 130500 | 28.3%
Tender: 12477 ¦ Bridge File: 1704-2 ¦ Tender Opening Date: 2025-05-08
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23213 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2025-2026 | 2025-06-03 | 3 | 2026-06-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
78802N-1 | 3 km West of Edmonton | North Central | 60:04 | Highway 16 | 3 x 1530 WG | 28 ¦ 34 ¦ 34 | 96 | 9.2
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 130000 | 130000 | 209333.33 | 209333.33 | 15.9%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 100000 | 100000 | 227500 | 227500 | 19.7%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | 139333.33 | 139333.33 | 9.8%
F755 | Surface Removal (BCS 20.6.1) | square metre | 795 | 30 | 23850 | 68 | 54060 | 38.1%
Q565 | Cold Milling Asphalt Pavement (HCS 3.16.6) | square metre | 246 | 30 | 7380 | 56.17 | 13817.82 | 54.5%
F760 | Partial Depth Repair - Curbs (BCS 20.6.2) | square metre | 15 | 2300 | 34500 | 1800 | 27000 | 19.8%
F760 | Partial Depth Repair - Abutment and Wingwalls (BCS 20.6.2) (Special Provisions) | square metre | 8 | 2500 | 20000 | 3000 | 24000 | 40.8%
F760 | Partial Depth Repair - Pier Caps (BCS 20.6.2) | square metre | 15 | 3500 | 52500 | 3250 | 48750 | 28.8%
F020 | Concrete Crack Repair - Pressure Injected Epoxy (Special Provisions) | metre | 100 | 500 | 50000 | 466.67 | 46667 | 5.1%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation - Abutment 1 (BCS 6.4.2) | lump sum | 1 | 160000 | 160000 | 174333.33 | 174333.33 | 16.9%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation - Abutment 2 (BCS 6.4.2) | lump sum | 1 | 180000 | 180000 | 217666.67 | 217666.67 | 29.6%
F018 | Approach Rail Transition - Supply and Install (Special Provisions) | lump sum | 1 | 40000 | 40000 | 71500 | 71500 | 20.7%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 106 | 200 | 21200 | 216.67 | 22967.02 | 20.8%
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 2 | 6000 | 12000 | 10666.67 | 21333.34 | 30.7%
F018 | Concrete Sealer - Type 2a/2b (Special Provisions) | lump sum | 1 | 15000 | 15000 | 17666.67 | 17666.67 | 42.9%
F018 | Concrete Sealer - Type 3 Pigmented (Special Provisions) | lump sum | 1 | 35000 | 35000 | 60666.67 | 60666.67 | 26.6%
F022 | Deck Waterproofing Repair (Special Provisions) | square metre | 10 | 200 | 2000 | 1601.67 | 16016.7 | 84.8%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 104 | 420 | 43680 | 485 | 50440 | 33.6%
F018 | Concrete Slope Protection Repair (Special Provisions) | lump sum | 1 | 75000 | 75000 | 174333.33 | 174333.33 | 47.3%
F911 | Drain Troughs (BCS 9.7) | metre | 20 | 1250 | 25000 | 1633.33 | 32666.6 | 22.5%
X002 | Extra Work - Various Repairs (Special Provisions) | Total Force Account | 1 | 50000 | 50000 | 50000 | 50000 | 0%
|  | Bridge File Modified Tender Value |  |  | 1177110 |  | 1700051.81 | 15.5%
|  | Total Tender Value |  |  |  |  | 2118050.33 | 16.6%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 90 | 135000 | 115 | 172500 | 14.2%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 80 | 120000 | 164 | 246000 | 33.1%
Tender: 23213 ¦ Bridge File: 78802-1 ¦ Tender Opening Date: 2025-06-03
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21653 | Bridge/Culvert Rehabilitation | Bridge/Culvert | Highway | Bridge/Culvert Rehabilitation | 2025-2026 | 2025-06-10 | 4 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
73436-1 | 8 km South of Paddle Prairie | Peace | 35:12 | Boyer River | 14 x 510 HC / 1 x 7060 Elliptical SPCSP | 9 / 16 | 16 | 7.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 17740.66 | 17740.66 | 38553.41 | 38553.41 | 42%
F750 | Traffic Accommodation for Bridge Construction (B.F. 73436) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 60000 | 60000 | 90000 | 90000 | 7.9%
F018 | Demolition and Disposal of Bridge Curb Structures (B.F. 73436) (Special Provisions) | lump sum | 1 | 35000 | 35000 | 35500 | 35500 | 9%
F834 | Concrete (Class C) - Supply and Place (B.F. 73436) (BCS 4.27.1) | cubic metre | 3 | 3000 | 9000 | 3508.33 | 10524.99 | 46.5%
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 73436) (BCS 5.6) | kilogram | 808 | 15 | 12120 | 15.67 | 12661.36 | 64.7%
F854 | Reinforcing Steel - Place (B.F. 73436) (BCS 5.6) | kilogram | 808 | 5 | 4040 | 10.47 | 8459.76 | 98.2%
F018 | Curb Construction (B.F. 73436) (Special Provisions) | lump sum | 1 | 15000 | 15000 | 27166.67 | 27166.67 | 20.4%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (B.F. 73436) (BCS 12.4) | lump sum | 1 | 15000 | 15000 | 26250 | 26250 | 10.3%
F492 | Roadway Work (B.F. 73436) (BCS 18.7) | lump sum | 1 | 25000 | 25000 | 49716.67 | 49716.67 | 58.2%
|  | Bridge File Modified Tender Value |  |  | 192900.66 |  | 298832.86 | 19.4%
|  | Total Tender Value |  |  |  |  | 16680230.93 | 2.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | - | - | 18 | 27000 | 13.1%
Tender: 21653 ¦ Bridge File: 73436-1 ¦ Tender Opening Date: 2025-06-10
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23214 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2025-2026 | 2025-06-11 | 6 | 2026-06-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76646W-2 | 5 km East of Edmonton | North Central | 16:18 | Clover Bar Road | 19 x 610 Type M / 4 x 610 Type-M (Modified) | 11 ¦ 17 ¦ 11 | 39 | 18.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 210000 | 210000 | 182529.33 | 182529.33 | 44.3%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 200000 | 200000 | 271376.33 | 271376.33 | 24.6%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 125000 | 125000 | 232250.33 | 232250.33 | 26.5%
F169 | Salvage of Existing Bridge Materials (BCS 21.4.2) | lump sum | 1 | 20000 | 20000 | 38232.67 | 38232.67 | 42.2%
F755 | Surface Removal (BCS 20.6.1) | square metre | 717 | 200 | 143400 | 72 | 51624 | 31.6%
F770 | Abrasive Blasting - Deck Surface (BCS 20.6.3) | square metre | 717 | 120 | 86040 | 44.33 | 31784.61 | 38%
Q565 | Cold Milling Asphalt Pavement (HCS 3.16.6) | square metre | 580 | 30 | 17400 | 47.33 | 27451.4 | 26.5%
F760 | Partial Depth Repair - Girders (BCS 20.6.2) | square metre | 4 | 2500 | 10000 | 4261 | 17044 | 37.2%
F760 | Partial Depth Repair - Deck and Approach Slab (BCS 20.6.2) | square metre | 68 | 2500 | 170000 | 1172.67 | 79741.56 | 21.7%
F760 | Partial Depth Repair - Abutment and Wingwall (BCS 20.6.2) | square metre | 10 | 2500 | 25000 | 2887.67 | 28876.7 | 21.8%
F760 | Partial Depth Repair - Pier Caps and Columns (BCS 20.6.2) | square metre | 50 | 3500 | 175000 | 2876 | 143800 | 3.7%
F020 | Concrete Crack Repair - Gravity-Feed Epoxy (Special Provisions) | metre | 60 | 100 | 6000 | 188 | 11280 | 34.1%
F020 | Concrete Crack Repair - Pressure-Injected Epoxy (Special Provisions) | metre | 40 | 500 | 20000 | 497.33 | 19893.2 | 29.5%
F021 | Grouting Voids Under Approach Slabs (Special Provisions) | cubic metre | 3 | 3500 | 10500 | 5097 | 15291 | 2.7%
F775 | Deck Overlay Concrete - Supply - Class HPC Fibre-Reinforced (BCS 20.6.4) | cubic metre | 36 | 1800 | 64800 | 2292 | 82512 | 35.8%
F776 | Deck Overlay Concrete - Place (BCS 20.6.4) | square metre | 717 | 200 | 143400 | 253.67 | 181881.39 | 60.8%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 15 | 3500 | 52500 | 8093 | 121395 | 44%
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 76646-W) (BCS 5.6) | kilogram | 265 | 10 | 2650 | 13.33 | 3532.45 | 46.8%
F854 | Reinforcing Steel - Place (B.F. 76646-W) (BCS 5.6) | kilogram | 265 | 4 | 1060 | 7.67 | 2032.55 | 26.8%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 65000 | 65000 | 131843.67 | 131843.67 | 17.1%
F018 | Approach Rail Transition - Supply and Install (Special Provisions) | lump sum | 1 | 80000 | 80000 | 39833.67 | 39833.67 | 3.6%
F018 | Strong-Post W-Beam Guardrail Reinstallation (Special Provisions) | lump sum | 1 | 15000 | 15000 | 32235.67 | 32235.67 | 53.7%
F018 | Pedestrian Rail Reinstallation (Special Provisions) | lump sum | 1 | 10000 | 10000 | 6255.33 | 6255.33 | 34.9%
F018 | Repair of Concrete Slope Protection (Special Provisions) | lump sum | 1 | 75000 | 75000 | 119837.67 | 119837.67 | 36.3%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 73 | 700 | 51100 | 728.33 | 53168.09 | 8.1%
F018 | Concrete Sealer - Type 3 Pigmented (Special Provisions) | lump sum | 1 | 15000 | 15000 | 39933.67 | 39933.67 | 32.3%
F911 | Drain Troughs (BCS 9.7) | metre | 30 | 1250 | 37500 | 1338 | 40140 | 13.9%
X002 | Extra Work - Various Repairs (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | 100000 | 100000 | 0%
|  | Bridge File Modified Tender Value |  |  | 1931350 |  | 2105776.29 | 5.5%
|  | Total Tender Value |  |  |  |  | 2558278.33 | 8.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 110 | 165000 | 146 | 219000 | 27.8%
F003 | Lane Closure for Bridge Construction - Hwy 16 Westbound (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 110 | 165000 | 156 | 234000 | 21.3%
Tender: 23214 ¦ Bridge File: 76646-2 ¦ Tender Opening Date: 2025-06-11
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
19440 | Construct NU Precast Concrete Girder Bridge | Bridge | Complex | Replace Bridge with Bridge | 2025-2026 | 2025-06-12 | 5 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75337N-3 | 13 km Northwest of Red Deer | Central | 2:26 | CNR Railway | 7 x 1600 NU | 34 | 34 | 21.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 4535536.45 | 4535536.45 | 786935.41 | 786935.41 | 24.3%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 500000 | 500000 | 408270.55 | 408270.55 | 5.4%
F186 | Excavation - Structural (BF75337-N) (BCS 1.6.1) | lump sum | 1 | 20000 | 20000 | 212313.53 | 212313.53 | 63.4%
F812 | Supply of Piling - Plain Steel H-Pile (BF75337-N) (BCS 3.6.1) | metre | 740 | 400 | 296000 | 316.83 | 234454.2 | 3.5%
F819 | Pile Tip Reinforcement (B.F 75337-N) (BCS 3.6.1) | pile | 24 | 500 | 12000 | 448.37 | 10760.88 | 11.1%
F816 | Pile Set-up (Driven Piles) (BF75337-N) (BCS 3.6.1) | pile | 24 | 6000 | 144000 | 5774 | 138576 | 10.1%
F818 | Pile Driving (BF75337-N) (BCS 3.6.1) | metre | 740 | 100 | 74000 | 9.59 | 7096.6 | 40.6%
F820 | PDA Testing (B.F. 75337-N) (BCS 3.6.4) | test | 4 | 1000 | 4000 | 2233.33 | 8933.32 | 12.4%
F017 | Steel CSP Castings (Special Provisions) | lump sum | 1 | 40000 | 40000 | 66641.67 | 66641.67 | 17%
F190 | Backfill - Granular (BF75337-N) (BCS 2.4) | lump sum | 1 | 20000 | 20000 | 125879.15 | 125879.15 | 54.9%
F850 | Plain Reinforcing Steel - Supply (BF75337-N) (BCS 5.6) | kilogram | 29500 | 3.5 | 103250 | 2.32 | 68440 | 15.3%
F853 | Stainless Reinforcing Steel - Supply (BF75337-N) (BCS 5.6) | kilogram | 106000 | 13 | 1378000 | 11.55 | 1224300 | 14.4%
F854 | Reinforcing Steel - Place (BF75337-N) (BCS 5.6) | kilogram | 135500 | 3 | 406500 | 2.59 | 350945 | 8%
F834 | Concrete (Class C) - Supply and Place (BF75337-N) (BCS 4.27.1) | cubic metre | 360 | 2500 | 900000 | 1589.83 | 572338.8 | 19.6%
F595 | Concrete Slope Protection (BF75337-N) (BCS 4.27.2) | square metre | 320 | 800 | 256000 | 510.7 | 163424 | 21.8%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 7 NU Girders, 1.60 m Deep (BF75337-N) (BCS 7.4) | lump sum | 1 | 800000 | 800000 | 946733.33 | 946733.33 | 3.9%
F903 | Structural Steel - Supply and Fabrication, Delivery and Erection - Intermediate Diaphragms (B.F. 75337-N) (BCS 6.4.1) | lump sum | 1 | 60000 | 60000 | 241501.33 | 241501.33 | 73.2%
F841 | Concrete (Class HPC) - Supply and Place (BF75337-N) (BCS 4.27.1) | cubic metre | 455 | 3000 | 1365000 | 2750 | 1251250 | 9.1%
F970 | Miscellaneous Iron (BF75337-N) (BCS 13.5) | lump sum | 1 | 10000 | 10000 | 10654.33 | 10654.33 | 75.2%
F974 | Waterproofing (BF75337-N) (BCS 16.5) | square metre | 1050 | 150 | 157500 | 62.36 | 65478 | 7.5%
F042 | Asphalt Concrete Pavement - Superpave - Mix Type 100-F-12.5(PG 64-34) (BCS 17.7.2) | tonne | 200 | 600 | 120000 | 463.62 | 92724 | 12%
X325 | Curb and Gutter - Mountable (300mm high) (HCS 4.2.5) | metre | 30 | 450 | 13500 | 385.33 | 11559.9 | 17.9%
F911 | Drain Troughs (B.F. 75337-N) (BCS 9.7) | metre | 62 | 300 | 18600 | 1410.09 | 87425.58 | 41.1%
X370 | Mechanically Stabilized Earth Walls (BF75337-N) (BCS 25.6) | square metre | 760 | 1500 | 1140000 | 2841.94 | 2159874.4 | 4%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (B.F. 75337-N) (BCS 12.4) | lump sum | 1 | 90000 | 90000 | 129435.33 | 129435.33 | 16.8%
S018 | Concrete Barrier - Supply and Install (BF 75337-N) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 106753.33 | 106753.33 | 13.4%
F170 | Demolition and Disposal of Bridge Structure (BF75337-N) (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | 261482 | 261482 | 36.8%
|  | Bridge File Modified Tender Value |  |  | 12613886.45 |  | 9744180.64 | 4.7%
|  | Total Tender Value |  |  |  |  | 55653342.06 | 5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 257 | 385500 | 29.1%
Tender: 19440 ¦ Bridge File: 75337-3 ¦ Tender Opening Date: 2025-06-12
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
19440 | Construct NU Precast Concrete Girder Bridge | Bridge | Complex | Replace Bridge with Bridge | 2025-2026 | 2025-06-12 | 5 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75337S-4 | 13 km Northwest of Red Deer | Central | 2:26 | CNR Railway | 7 x 1600 NU | 34 | 34 | 21.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 781977.1 | 781977.1 | 810808.58 | 810808.58 | 23.3%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 86205.58 | 86205.58 | 422523.03 | 422523.03 | 7.3%
F186 | Excavation - Structural (BF75337-S) (BCS 1.6.1) | lump sum | 1 | 20000 | 20000 | 358803.87 | 358803.87 | 45.3%
F812 | Supply of Piling - Plain Steel H-Pile (BF75337-S) (BCS 3.6.1) | metre | 740 | 400 | 296000 | 316.5 | 234210 | 3.7%
F819 | Pile Tip Reinforcement (B.F 75337-S) (BCS 3.6.1) | pile | 24 | 500 | 12000 | 448.37 | 10760.88 | 11.1%
F816 | Pile Set-up (Driven Piles) (BF75337-S) (BCS 3.6.1) | pile | 24 | 6000 | 144000 | 5653.67 | 135688.08 | 7.3%
F818 | Pile Driving (BF75337-S) (BCS 3.6.1) | metre | 740 | 100 | 74000 | 9.59 | 7096.6 | 40.6%
F820 | PDA Testing (B.F. 75337-S) (BCS 3.6.4) | test | 4 | 1000 | 4000 | 2233.33 | 8933.32 | 12.4%
F017 | Steel CSP Castings (Special Provisions) | lump sum | 1 | 40000 | 40000 | 66641.67 | 66641.67 | 17%
F190 | Backfill - Granular (BF75337-S) (BCS 2.4) | lump sum | 1 | 20000 | 20000 | 124319.15 | 124319.15 | 53.9%
F850 | Plain Reinforcing Steel - Supply (BF75337-S) (BCS 5.6) | kilogram | 31000 | 3.5 | 108500 | 2.32 | 71920 | 15.3%
F853 | Stainless Reinforcing Steel - Supply (BF75337-S) (BCS 5.6) | kilogram | 106000 | 13 | 1378000 | 11.55 | 1224300 | 14.4%
F854 | Reinforcing Steel - Place (BF75337-S) (BCS 5.6) | kilogram | 137000 | 3 | 411000 | 2.59 | 354830 | 8%
F834 | Concrete (Class C) - Supply and Place (BF75337-S) (BCS 4.27.1) | cubic metre | 380 | 2500 | 950000 | 1684.83 | 640235.4 | 16.7%
F595 | Concrete Slope Protection (BF75337-S) (BCS 4.27.2) | square metre | 320 | 800 | 256000 | 491.5 | 157280 | 18.7%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 7 NU Girders, 1.60 m Deep (BF75337-S) (BCS 7.4) | lump sum | 1 | 800000 | 800000 | 940530 | 940530 | 3%
F903 | Structural Steel - Supply and Fabrication, Delivery and Erection (B.F. 75337-S) (BCS 6.4.1) (Special Provisions) | lump sum | 1 | 60000 | 60000 | 241501.33 | 241501.33 | 73.2%
F841 | Concrete (Class HPC) - Supply and Place (BF75337-S) (BCS 4.27.1) | cubic metre | 455 | 3000 | 1365000 | 2711.33 | 1233655.15 | 5.4%
F970 | Miscellaneous Iron (BF75337-S) (BCS 13.5) | lump sum | 1 | 10000 | 10000 | 11982.33 | 11982.33 | 93.9%
F974 | Waterproofing (BF75337-S) (BCS 16.5) | square metre | 1050 | 150 | 157500 | 62.29 | 65404.5 | 7.3%
F042 | Asphalt Concrete Pavement - Superpave - Mix Type 100-F-12.5 (PG 64-34) (BCS 17.7.2) | tonne | 200 | 600 | 120000 | 463.62 | 92724 | 12%
X325 | Curb and Gutter - Mountable(300 mm high) (HCS 4.2.5) | metre | 60 | 450 | 27000 | 382.27 | 22936.2 | 24.9%
F911 | Drain Troughs (B.F. 75337-S) (BCS 9.7) | metre | 72 | 300 | 21600 | 1391.66 | 100199.52 | 41.1%
X370 | Mechanically Stabilized Earth Walls (BF75337-S) (BCS 25.6) | square metre | 810 | 1500 | 1215000 | 2774.74 | 2247539.4 | 5.8%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (B.F.75337-S) (BCS 12.4) | lump sum | 1 | 90000 | 90000 | 136525 | 136525 | 12.6%
S018 | Concrete Barrier - Supply and Install (BF 75337-S) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 98714.33 | 98714.33 | 15.2%
F170 | Demolition and Disposal of Bridge Structure (BF75337-S) (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | 246062 | 246062 | 35.5%
|  | Bridge File Modified Tender Value |  |  | 8597782.68 |  | 10066124.34 | 3.2%
|  | Total Tender Value |  |  |  |  | 55653342.06 | 5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 263 | 394500 | 29.9%
Tender: 19440 ¦ Bridge File: 75337-4 ¦ Tender Opening Date: 2025-06-12
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
19440 | Construct DMS Structure | DMS Structure | Complex | New DMS Structure | 2025-2026 | 2025-06-12 | 5 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
83091ZN-2 | 13 km Northwest of Red Deer | Central | 2:26 | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 137384.2 | 137384.2 | 177624.4 | 177624.4 | 27%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 15145.31 | 15145.31 | 92621.99 | 92621.99 | 13.6%
F018 | Existing Overhead Sign Structure - Remove and Dispose (Special Provisions) | lump sum | 1 | 75000 | 75000 | 90414.77 | 90414.77 | 64.4%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 83091ZN2) (BCS 24.5) | lump sum | 1 | 400000 | 400000 | 695497.72 | 695497.72 | 9.5%
U018 | TMC Service Provider Services (Special Provisions) | lump sum | 1 | 10000 | 10000 | 44906.88 | 44906.88 | 5.9%
U018 | Spare Parts (Special Provisions) | lump sum | 1 | 15000 | 15000 | 19963.11 | 19963.11 | 11.6%
U018 | Systems Acceptance Testing and Handover (Special Provisions) | lump sum | 1 | 5000 | 5000 | 40578.24 | 40578.24 | 129.7%
U018 | Training (Special Provisions) | lump sum | 1 | 5000 | 5000 | 13104.51 | 13104.51 | 40.5%
U018 | Maintenance and Warranty for ITS Work (Special Provisions) | lump sum | 1 | 110000 | 110000 | 116411.02 | 116411.02 | 59.4%
U018 | Removal of ITS Equipment (Special Provisions) | lump sum | 1 | 30000 | 30000 | 25706.34 | 25706.34 | 38.3%
U102 | Dynamic Message Sign and Controller - Supply and Install (Special Provisions) | unit | 1 | 250000 | 250000 | 233316.58 | 233316.58 | 5.9%
U102 | Dynamic Message Sign Cabinet - Supply and Install (Special Provisions) | unit | 1 | 15000 | 15000 | 32672.63 | 32672.63 | 5.9%
U102 | Modem - Supply and Install (Special Provisions) | unit | 1 | 2000 | 2000 | 6432.43 | 6432.43 | 6.2%
U102 | Uninterruptible Power Supply (Special Provisions) | unit | 2 | 11600 | 23200 | 8113.2 | 16226.4 | 7.9%
U105 | Secondary Cable - Supply and Install - No. 2 (HCS 2.25.8) | metre | 110 | 30 | 3300 | 110.68 | 12174.8 | 53%
S400 | Underground Electrical Conduit - Supply and Install - Trench Excavation - RPVC 53 MM (HCS 2.7.4) | metre | 140 | 200 | 28000 | 111.54 | 15615.6 | 8.3%
S400 | Underground Electrical Conduit - Supply and Install - Trench Excavation (RPVC 27 MM) (HCS 2.7.4) | metre | 3 | 500 | 1500 | 193.95 | 581.85 | 108%
U018 | Grounding and Bonding - Supply and Install (Special Provisions) | lump sum | 1 | 5000 | 5000 | 3704.32 | 3704.32 | 42.4%
U102 | Concrete Bases for Cabinets - Supply and Install (Special Provisions) | unit | 1 | 5000 | 5000 | 6312.78 | 6312.78 | 16.7%
U018 | RWIS (Special Provisions) | lump sum | 1 | 375000 | 375000 | 554896.11 | 554896.11 | 5.9%
|  | Bridge File Modified Tender Value |  |  | 1510529.51 |  | 2198762.48 | 9.3%
|  | Total Tender Value |  |  |  |  | 55653342.06 | 5%
Tender: 19440 ¦ Bridge File: 83091-2 ¦ Tender Opening Date: 2025-06-12
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23207 | Install Erosion and Sediment Control Measures | Culvert | Multiple | Culvert Maintenance | 2025-2026 | 2025-06-25 | 2 | 2026-03-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76001-2 | 9 km South of Ft McMurray | North Central | 63:11 | Prairie Creek | 1 x 2100 SWSP | 118 | 118 | 2.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 60000 | 60000 | 22450 | 22450 | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 76001) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 5000 | 5000 | 17075 | 17075 | -
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 2000 | 2000 | 22975 | 22975 | -
G225 | Common Excavation (HCS 2.3.6) | cubic metre | 2000 | 15 | 30000 | 22.05 | 44100 | -
G300 | Topsoil Placement (HCS 2.6.4) | square metre | 5000 | 2 | 10000 | 2.35 | 11750 | -
E608 | Broadcast Seeding (HCS 2.20.4) | hectare | 1.5 | 5000 | 7500 | 5568.5 | 8352.75 | -
E610 | Slope Texturing (HCS 2.20.4) | square metre | 1500 | 1.5 | 2250 | 3.18 | 4770 | -
F505 | Heavy Rock Riprap (Class 1M) (B.F. 76001) (BCS 10.7) | cubic metre | 15 | 300 | 4500 | 381 | 5715 | -
F500 | Heavy Rock Riprap (Class 1) (B.F. 76001) (BCS 10.7) | cubic metre | 75 | 400 | 30000 | 362.5 | 27187.5 | -
F515 | Heavy Rock Riprap (Class 2) (B.F. 76001) (BCS 10.7) | cubic metre | 150 | 400 | 60000 | 425 | 63750 | -
S355 | Roadway Lines - Supplying Paint and Painting (Directional Dividing and 1 Edge Line) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.4 | 10000 | 4000 | 5568.5 | 2227.4 | -
F018 | High Tension Cable Barrier - Re-tension (Special Provisions) | lump sum | 1 | 3000 | 3000 | 7625 | 7625 | -
E018 | Sedimentation Pond (Special Provisions) | lump sum | 1 | 10000 | 10000 | 56550 | 56550 | -
E003 | Willow Plantings (Special Provisions) | planting | 35 | 75 | 2625 | 638.5 | 22347.5 | -
E020 | Straw Rolls (Special Provisions) | metre | 1050 | 20 | 21000 | 22.75 | 23887.5 | -
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 150 | 15 | 2250 | 22 | 3300 | -
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 5100 | 8 | 40800 | 6.6 | 33660 | -
E331 | Gabion Mattress - Supply and Install (HCS 6.10.4) | square metre | 75 | 250 | 18750 | 661 | 49575 | -
|  | Bridge File Modified Tender Value |  |  | 313675 |  | 427297.65 | -
|  | Total Tender Value |  |  |  |  | 3971009.46 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 15 | 22500 | 20 | 30000 | -
Tender: 23207 ¦ Bridge File: 76001-2 ¦ Tender Opening Date: 2025-06-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23207 | Construct SWSP Culvert | Culvert | Multiple | Replace Culvert with Culvert | 2025-2026 | 2025-06-25 | 2 | 2026-03-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76002S-3 | 15 km South of Ft McMurray | North Central | 63:10 | Halfway Creek | 1 x 3350 SWSP | 80 | 80 | 3.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 239615 | 239615 | 173975 | 173975 | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 76002S) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 250000 | 250000 | 37950 | 37950 | -
E018 | Environmental Protection Works (Special Provisions) | lump sum | 1 | 30000 | 30000 | 21050 | 21050 | -
C025 | Care of Water (Special Provisions) | lump sum | 1 | 30000 | 30000 | 51000 | 51000 | -
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 83700 | 83700 | -
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 20 | 1800 | 36000 | 1584 | 31680 | -
D020 | Supply of S.W.S.P - (3353 mm dia. X 15.9 mm thickness) (Special Provisions) | metre | 80.47 | 8500 | 683995 | 9931.5 | 799187.81 | -
D020 | Installation of S.W.S.P by Tunneling / Auguring (2743 mm dia. X 15.9 mm thickness) (Special Provisions) | metre | 80.47 | 14000 | 1126580 | 22125 | 1780398.75 | -
F196 | Backfill - Non-Granular (Clay Seals) (BCS 2.4) | lump sum | 1 | 12500 | 12500 | 48275 | 48275 | -
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 175 | 600 | 105000 | 1072 | 187600 | -
F018 | Concrete End Treatment - Upstream End Only (Special Provisions) | lump sum | 1 | 40000 | 40000 | 73650 | 73650 | -
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 250 | 300 | 75000 | 361 | 90250 | -
E608 | Broadcast Seeding (HCS 2.20.4) | hectare | 1.5 | 4000 | 6000 | 5568.5 | 8352.75 | -
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 2500 | 20 | 50000 | 6.9 | 17250 | -
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 200 | 20 | 4000 | 22 | 4400 | -
|  | Bridge File Modified Tender Value |  |  | 2713690 |  | 3408719.31 | -
|  | Total Tender Value |  |  |  |  | 3971009.46 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 60 | 90000 | 70 | 105000 | -
Tender: 23207 ¦ Bridge File: 76002-3 ¦ Tender Opening Date: 2025-06-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22880 | Construct CSP Culvert | Culvert | Single | Replace Bridge with Culvert | 2025-2026 | 2025-07-09 | 12 | 2026-06-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
72029-2 | 25 km Southwest of Tilley | Southern | 875:04 | EID - Irrigation Canal | 1 x 3600 CSP | 62 | 62 | 3.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 126696.41 | 126696.41 | 169763.14 | 169763.14 | 24.6%
F750 | Traffic Accommodation for Bridge Construction (B.F. 72029) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 161062.1 | 161062.1 | 52191.74 | 52191.74 | 48.8%
C025 | Care of Water (Special Provisions) | lump sum | 1 | 20187.5 | 20187.5 | 19305.09 | 19305.09 | 67%
E612 | Fish Capture and Release (Special Provisions) | day | 2 | 3500 | 7000 | 4490.44 | 8980.88 | 22.6%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 15 | 2050 | 30750 | 1881.11 | 28216.65 | 47.5%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 67399.43 | 67399.43 | 48093.64 | 48093.64 | 43.6%
F186 | Excavation - Structural (BCS 1.6.1) (Special Provisions) | lump sum | 1 | 25496.25 | 25496.25 | 30007.71 | 30007.71 | 33.3%
F495 | CSP with Couplers - Supply (BCS 18.7) | metre | 62 | 2755 | 170810 | 3024.4 | 187512.8 | 12.6%
F496 | CSP - Assembly (BCS 18.7) | metre | 62 | 592.41 | 36729.42 | 514 | 31868 | 48.6%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 43200 | 43200 | 49457.82 | 49457.82 | 33.6%
F204 | Backfill - Crushed Aggregate (BCS 2.4) | lump sum | 1 | 115740.6 | 115740.6 | 162692.4 | 162692.4 | 25%
F196 | Backfill - Non-Granular (BCS 2.4) | lump sum | 1 | 130035.3 | 130035.3 | 237189.18 | 237189.18 | 50.5%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 200 | 316.2 | 63240 | 223.59 | 44718 | 33.9%
D100 | Culverts - Remove and Dispose (C.S.P.) (up to 700 mm dia.) (HCS 2.4.4) | metre | 33 | 117.35 | 3872.55 | 243.08 | 8021.64 | 99.1%
D410 | Culverts - Supply and Install (600 mm dia. C.S.P.) (HCS 2.4.4) (HCS 5.23.4) | metre | 48 | 439.73 | 21107.04 | 529.78 | 25429.44 | 22.8%
D125 | Culverts - Remove, Salvage and Re-Install (C.S.P.) (over 700 mm dia.) (HCS 2.4.4) (Special Provisions) | metre | 30 | 951.1 | 28533 | 646.31 | 19389.3 | 35.5%
D431 | Culverts - Supply and Install (1 000 mm dia. C.S.P.) (HCS 2.4.4) (HCS 5.23.4) | metre | 9 | 951.1 | 8559.9 | 1217.68 | 10959.12 | 45.8%
F505 | Heavy Rock Riprap (Class 1M) (BCS 10.7) | cubic metre | 6 | 382.42 | 2294.52 | 303.03 | 1818.18 | 36.6%
F492 | Roadway Work (B.F. 72029) (BCS 18.7) (Special Provisions) | lump sum | 1 | 172497.89 | 172497.89 | 49615.94 | 49615.94 | 27.3%
F983 | Asphalt Concrete Pavement - Mix Type M1 (PG52-34) Mix Type M1 (PG 52-34) (BCS 17.7.1) (Special Provisions) | lump sum | 1 | 28847.72 | 28847.72 | 70473.37 | 70473.37 | 30.8%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) (Special Provisions) | metre | 180 | 20 | 3600 | 8.72 | 1569.6 | 57.7%
|  | Bridge File Modified Tender Value |  |  | 1267659.63 |  | 1257273.64 | 7.9%
|  | Total Tender Value |  |  |  |  | 1396275.22 | 7.6%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 42 | 63000 | 50 | 75000 | 16.3%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 42 | 63000 | 43 | 64500 | 24.1%
Tender: 22880 ¦ Bridge File: 72029-2 ¦ Tender Opening Date: 2025-07-09
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
12463 | Construct CSP Culvert | Culvert | Single | Replace Bridge with Culvert | 2025-2026 | 2025-07-15 | 8 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
7816-2 | 7 km North of Round Hill | Central | 834:02 | Amisk Creek | 2 x 2700 CSP | 27 - 27 | 54 | 2.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 100000 | 100000 | 95198.37 | 95198.37 | 35.9%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 40000 | 40000 | 20375 | 20375 | 42.5%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 40000 | 40000 | 20966.33 | 20966.33 | 54.4%
C025 | Care of Water - Water management (Special Provisions) | lump sum | 1 | 30000 | 30000 | 25540 | 25540 | 86.3%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 48000 | 48000 | 17843.33 | 17843.33 | 35.3%
E612 | Total Suspended Solids (TSS) Testing | day | 10 | 1800 | 18000 | 1636.67 | 16366.7 | 7.6%
E612 | Fish Capture and Release | day | 3 | 1800 | 5400 | 2258.33 | 6774.99 | 39.2%
F495 | CSP with Couplers - Supply (BCS 18.7) | metre | 54 | 2000 | 108000 | 1072.07 | 57891.78 | 4.8%
F496 | CSP - Assembly (BCS 18.7) | metre | 54 | 800 | 43200 | 832.7 | 44965.8 | 23.9%
F204 | Backfill - Crushed Aggregate - Des2 Cl40 & Des2 Cl25 (BCS 2.4) | lump sum | 1 | 33750 | 33750 | 22827.77 | 22827.77 | 61.3%
F196 | Backfill - Non-Granular - Clay seals (BCS 2.4) | lump sum | 1 | 24000 | 24000 | 27322.75 | 27322.75 | 7.6%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 185 | 300 | 55500 | 285.67 | 52848.95 | 41.8%
F018 | Roadway Work | lump sum | 1 | 100000 | 100000 | 82500 | 82500 | 10.8%
F018 | Removal and Transport Detour Bridge | lump sum | 1 | 30000 | 30000 | 17333.33 | 17333.33 | 28.5%
F018 | Removal of Detour Road and Site Restoration | lump sum | 1 | 30000 | 30000 | 32566.67 | 32566.67 | 19.2%
S836 | High Tension Cable Barrier - - Supply and Install (HCS 2.11.9) | metre | 351 | 300 | 105300 | 150.67 | 52885.17 | 18.4%
S837 | High Tension Cable Barrier End Terminal (Crashworthy) - Supply and Install (HCS 2.11.9) | unit | 4 | 4000 | 16000 | 13934.53 | 55738.12 | 38.5%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 500 | 20 | 10000 | 15.67 | 7835 | 26.7%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 150 | 20 | 3000 | 30 | 4500 | 36%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.15 | 25000 | 3750 | 53333.33 | 8000 | 39.3%
|  | Bridge File Modified Tender Value |  |  | 843900 |  | 670280.06 | 2.8%
|  | Total Tender Value |  |  |  |  | 716776.96 | 3.6%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 30 | 45000 | 31 | 46500 | 20.9%
Tender: 12463 ¦ Bridge File: 7816-2 ¦ Tender Opening Date: 2025-07-15
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21869 | Construct SPCSP Culvert | Culvert | Single | Replace Bridge with Culvert | 2025-2026 | 2025-07-22 | 5 | 2025-11-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
8320-2 | Near Falher | Peace | 49:10 | Tributary to Peavine Creek | 1 x 3670 SPCSP | 41 | 41 | 3.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 90000 | 90000 | 174148.33 | 174148.33 | 82.9%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 175000 | 175000 | 161933.33 | 161933.33 | 38%
E612 | Total Suspended Solids (TSS) Testing | day | 20 | 1500 | 30000 | 1456.67 | 29133.4 | 50.3%
E018 | Fish Capture and Release (Special Provisions) | lump sum | 1 | 10000 | 10000 | 10849.33 | 10849.33 | 78.9%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 15000 | 15000 | 88600 | 88600 | 89.5%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 32000 | 32000 | 66700 | 66700 | 89.4%
F488 | SPCSP - Supply (BCS 18.7) | lump sum | 1 | 195000 | 195000 | 142043.81 | 142043.81 | 4%
F489 | SPCSP - Assembly (BCS 18.7) | lump sum | 1 | 78000 | 78000 | 64329.6 | 64329.6 | 20.2%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 55000 | 55000 | 176661.33 | 176661.33 | 30.8%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 30000 | 30000 | 54000 | 54000 | 38.8%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 325000 | 325000 | 343605.91 | 343605.91 | 30.1%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 170 | 350 | 59500 | 231 | 39270 | 31.8%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 300 | 15 | 4500 | 13.67 | 4101 | 46.4%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 50 | 15 | 750 | 20.67 | 1033.5 | 53.9%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 425 | 15 | 6375 | 12.67 | 5384.75 | 48.4%
E020 | Class 1M Rock Ditch Drains (Special Provisions) | metre | 20 | 350 | 7000 | 414.67 | 8293.4 | 28.1%
|  | Bridge File Modified Tender Value |  |  | 1113125 |  | 1370087.69 | 7.9%
|  | Total Tender Value |  |  |  |  | 1431584.99 | 7.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 41 | 61500 | 17%
Tender: 21869 ¦ Bridge File: 8320-2 ¦ Tender Opening Date: 2025-07-22
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23792 | Construct SWSP Culvert | Culvert | Multiple | Replace Culvert with Culvert | 2025-2026 | 2025-07-22 | 5 | 2026-06-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
73127-2 | Near Trochu | Central | 585:02 | Tributary to Ghostpine Creek | 1 x 2100 SWSP | 65 | 65 | 2.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 100000 | 100000 | 158829.6 | 158829.6 | 40.6%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 10000 | 10000 | 9028.24 | 9028.24 | 91.4%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 30000 | 30000 | 24290.94 | 24290.94 | 52.5%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 1936.89 | 5810.67 | 88.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 1500 | 9000 | 1364.68 | 8188.08 | 80%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 7500 | 7500 | 8977.46 | 8977.46 | 30.9%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 6500 | 6500 | 16452.82 | 16452.82 | 51.1%
F020 | SWSP - Supply (2.13 m OD) (Special Provisions) | metre | 65 | 4500 | 292500 | 3300.31 | 214520.15 | 18.2%
F020 | SWSP - Bore (2.13 m OD) (Special Provisions) | metre | 65 | 6000 | 390000 | 5153.97 | 335008.05 | 9.3%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 17500 | 17500 | 17519.49 | 17519.49 | 54.2%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 50 | 250 | 12500 | 317.02 | 15851 | 16.3%
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 95 | 750 | 71250 | 594.77 | 56503.15 | 10.9%
F018 | Embankment & Berm Construction (Special Provisions) | lump sum | 1 | 15000 | 15000 | 17352.23 | 17352.23 | 39.1%
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.15 | 13500 | 2025 | 74581.25 | 11187.19 | 75.3%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.1 | 15000 | 1500 | 50208.92 | 5020.89 | 59.2%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 200 | 25 | 5000 | 13.7 | 2740 | 33.8%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 250 | 12 | 3000 | 5.51 | 1377.5 | 61.4%
|  | Bridge File Modified Tender Value |  |  | 985275 |  | 908657.46 | 7.7%
|  | Total Tender Value |  |  |  |  | 1985016.2 | 15.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 25 | 37500 | 39 | 58500 | 4.8%
Tender: 23792 ¦ Bridge File: 73127-2 ¦ Tender Opening Date: 2025-07-22
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23792 | Construct SWSP Culvert | Culvert | Multiple | Replace Culvert with Culvert | 2025-2026 | 2025-07-22 | 5 | 2026-06-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
73865-2 | Near Myrnam | Central | 45:08 | 2nd Order Tributary to Slawa Creek | 1 x 2440 SWSP | 38 | 38 | 2.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 80000 | 80000 | 215875.26 | 215875.26 | 51.6%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 10000 | 10000 | 11357.45 | 11357.45 | 58.5%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 30000 | 30000 | 13597.05 | 13597.05 | 49.4%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 1936.89 | 5810.67 | 88.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 1500 | 9000 | 1364.68 | 8188.08 | 80%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 8000 | 8000 | 9255.25 | 9255.25 | 16.5%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 7800 | 7800 | 16036.72 | 16036.72 | 45.4%
F020 | SWSP - Supply (2.44 m OD) (Special Provisions) | metre | 38 | 6000 | 228000 | 4288.02 | 162944.76 | 29.7%
F020 | SWSP - Bore (2.44 m OD) (Special Provisions) | metre | 38 | 8000 | 304000 | 9916.26 | 376817.88 | 35.4%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 28000 | 28000 | 18124.52 | 18124.52 | 43%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 80 | 250 | 20000 | 352.91 | 28232.8 | 21.1%
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 75 | 750 | 56250 | 658.86 | 49414.5 | 6.3%
F018 | Embankment & Berm Construction (Special Provisions) | lump sum | 1 | 15000 | 15000 | 20825.82 | 20825.82 | 37%
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.2 | 13500 | 2700 | 60516.87 | 12103.37 | 60%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.1 | 15000 | 1500 | 41571.63 | 4157.16 | 44%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 200 | 25 | 5000 | 13.7 | 2740 | 33.8%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 250 | 12 | 3000 | 5.51 | 1377.5 | 61.4%
|  | Bridge File Modified Tender Value |  |  | 820250 |  | 956858.79 | 24.4%
|  | Total Tender Value |  |  |  |  | 1985016.2 | 15.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 20 | 30000 | 41 | 61500 | 29.7%
Tender: 23792 ¦ Bridge File: 73865-2 ¦ Tender Opening Date: 2025-07-22
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22256 | Construct CSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2025-2026 | 2025-08-07 | 3 | 2026-03-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
80927-2 | Near John D'Or Prairie | Peace | 58:12 | 2nd Order Tributary to Lawrence River | 1 x 2400 CSP | 40 | 40 | 2.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 155000 | 155000 | 97341.67 | 97341.67 | 61.3%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 225000 | 225000 | 179166.67 | 179166.67 | 43.8%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1000 | 10000 | 713.33 | 7133.3 | 131.6%
E018 | Fish Capture and Release (Special Provisions) (Deletable) | lump sum | 1 | 10000 | 10000 | 7157.33 | 7157.33 | 71.2%
E018 | Water Management (Special Provisions) | lump sum | 1 | 30000 | 30000 | 15892 | 15892 | 84%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 20000 | 20000 | 46397.67 | 46397.67 | 93.2%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 21000 | 21000 | 88421 | 88421 | 85.4%
F490 | CSP with couplers - Supply (BCS 18.7) | lump sum | 1 | 118000 | 118000 | 72943.33 | 72943.33 | 14.4%
F491 | CSP - Assembly (BCS 18.7) | lump sum | 1 | 47000 | 47000 | 16568.33 | 16568.33 | 41.4%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 45000 | 45000 | 176819.33 | 176819.33 | 16%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 75000 | 75000 | 60788.67 | 60788.67 | 62.6%
F515 | Heavy Rock Riprap (Class 2) (BCS 10.7) | cubic metre | 170 | 370 | 62900 | 441 | 74970 | 8.7%
E020 | Rock Ditch Drains - Class 1M (Special Provisions) | metre | 20 | 450 | 9000 | 1070.33 | 21406.6 | 59.6%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 160 | 15 | 2400 | 31 | 4960 | 20.9%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 120 | 15 | 1800 | 25 | 3000 | 16.3%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 390 | 10 | 3900 | 11.33 | 4418.7 | 23.2%
|  | Bridge File Modified Tender Value |  |  | 836000 |  | 877384.6 | 27.7%
|  | Total Tender Value |  |  |  |  | 915886 | 26.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 26 | 39000 | 12.7%
Tender: 22256 ¦ Bridge File: 80927-2 ¦ Tender Opening Date: 2025-08-07
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22726 | Construct SLW Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2025-2026 | 2025-08-20 | 2 | 2026-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
72398-2 | 19 km North of Vegreville | Central | 837:04 | 2nd Order Tributary to Vermilion River | 9 x 510 SLW | 14 | 14 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 240000 | 240000 | 344500 | 344500 | -
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 350000 | 350000 | 615000 | 615000 | -
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 30000 | 30000 | 47500 | 47500 | -
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 755 | 2265 | -
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 2000 | 12000 | 755 | 4530 | -
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | 249000 | 249000 | -
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 40000 | 40000 | 17500 | 17500 | -
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 40000 | 40000 | 27500 | 27500 | -
F813 | Supply of Piling - Galvanized Steel H-Pile (BCS 3.6.1) | metre | 150 | 350 | 52500 | 555 | 83250 | -
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 137 | 250 | 34250 | 435 | 59595 | -
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 30 | 5000 | 150000 | 3475 | 104250 | -
F818 | Pile Driving (BCS 3.6.1) | metre | 287 | 50 | 14350 | 80 | 22960 | -
F018 | Abutment Construction (Special Provisions) | lump sum | 1 | 200000 | 200000 | 262500 | 262500 | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1749 | 9 | 15741 | 12.5 | 21862.5 | -
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1749 | 3.5 | 6121.5 | 3.5 | 6121.5 | -
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 15 | 3000 | 45000 | 2250 | 33750 | -
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 170 | 300 | 51000 | 345 | 58650 | -
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) (Special Provisions) | lump sum | 1 | 260000 | 260000 | 285000 | 285000 | -
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 5000 | 5000 | 4500 | 4500 | -
F974 | Waterproofing (BCS 16.5) | square metre | 210 | 125 | 26250 | 85 | 17850 | -
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 40 | 400 | 16000 | 485 | 19400 | -
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 600000 | 600000 | 899000 | 899000 | -
F018 | Drain Troughs - Supply and Install (Special Provisions) | lump sum | 1 | 40000 | 40000 | 44000 | 44000 | -
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (B.F. _____) (BCS 12.4) | lump sum | 1 | 30000 | 30000 | 40000 | 40000 | -
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 40000 | 40000 | 61000 | 61000 | -
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.8 | 30000 | 24000 | 8125 | 6500 | -
E020 | Straw Rolls (Special Provisions) | metre | 200 | 20 | 4000 | 18 | 3600 | -
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 500 | 10 | 5000 | 10 | 5000 | -
|  | Bridge File Modified Tender Value |  |  | 2443212.5 |  | 3346584 | -
|  | Total Tender Value |  |  |  |  | 3496584 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 70 | 105000 | 100 | 150000 | -
Tender: 22726 ¦ Bridge File: 72398-2 ¦ Tender Opening Date: 2025-08-20
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
25141 | Remove Sign Structure | Sign Structure | Highway | Remove Sign Structure | 2025-2026 | 2025-08-26 | 3 | 2026-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75651ZS-5 | 5 km West of Ponoka | Central | 2:28 | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 5036.82 | 5036.82 | 5969.5 | 5969.5 | 46.7%
F170 | Demolition and Disposal of Bridge Structure (Overhead Sign Structure - B.F. 75651ZS-5) (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 46283.33 | 46283.33 | 30.4%
|  | Bridge File Modified Tender Value |  |  | 55036.82 |  | 52252.83 | 28.9%
|  | Total Tender Value |  |  |  |  | 19354291.69 | 11.4%
Tender: 25141 ¦ Bridge File: 75651-5 ¦ Tender Opening Date: 2025-08-26
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
25520 | Construct WSP Culvert - Install CSP Culvert Liner | Culvert | Multiple | New and Lined Culverts | 2025-2026 | 2025-09-18 | 3 | 2026-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76028-2 | 24 km Northeast of Swan Hills | Peace | 33:12 | Tributary to Swan River | 2 x 2440 SWSP - 1 x 2400 CSP Liner | 115 - 115 - 107 | 337 | 2.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 260038.99 | 260038.99 | 504246.47 | 504246.47 | 23%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 5 | 2000 | 10000 | 513.33 | 2566.65 | 126.5%
E612 | Fish Capture and Release (Special Provisions) | day | 2 | 2000 | 4000 | 961.67 | 1923.34 | 69.5%
G101 | Clearing and Mulching (HCS 2.1.4) | hectare | 0.6 | 72000 | 43200 | 13333.33 | 8000 | 35.4%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 200 | 28 | 5600 | 20 | 4000 | 20.4%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 300 | 15.5 | 4650 | 15 | 4500 | 27.2%
E020 | Fibre/Straw Rolls - Supply and Install (Special Provisions) | metre | 200 | 24 | 4800 | 18.33 | 3666 | 25.7%
E052 | Tree Planting (Special Provisions) | unit | 875 | 28 | 24500 | 26.67 | 23336.25 | 23.4%
F750 | Traffic Accommodation for Bridge Construction (B.F. 76028) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 15000 | 15000 | 83000 | 83000 | 28.1%
F186 | Excavation - Structural (B.F. 76028) (BCS 1.6.1) | lump sum | 1 | 25100 | 25100 | 183333.33 | 183333.33 | 34%
F187 | Excavation - Channel (B.F. 76028) (BCS 1.6.1) | lump sum | 1 | 9000 | 9000 | 96666.67 | 96666.67 | 38.1%
F020 | CSP Liner Supply and Install (2400 mm dia.) (Special Provisions) | metre | 110 | 1500 | 165000 | 2900 | 319000 | 27.2%
F021 | Grouting Liners (B.F. 76028) (Special Provisions) | cubic metre | 720 | 720 | 518400 | 933.33 | 671997.6 | 20.2%
F020 | Smooth Wall Steel Pipe - Supply (2438 mm OD) (Special Provisions) | metre | 230 | 2900 | 667000 | 6333.33 | 1456665.9 | 26.8%
F020 | Smooth Wall Steel Pipe - Install (2438 mm OD) (Special Provisions) | metre | 230 | 3600 | 828000 | 8000 | 1840000 | 10.2%
F715 | Substrate Holders - Steel (B.F. 76028) (BCS 18.7) | unit | 22 | 2300 | 50600 | 1166.67 | 25666.74 | 53.5%
F021 | Substrate Material (Class 1M) (B.F. 76028) (Special Provisions) | cubic metre | 42 | 400 | 16800 | 616.67 | 25900.14 | 44.1%
F196 | Backfill - Non-Granular (B.F. 76028) (BCS 2.4) | lump sum | 1 | 32000 | 32000 | 85000 | 85000 | 12.7%
F500 | Heavy Rock Riprap (Class 1) (B.F. 76028) (BCS 10.7) | cubic metre | 310 | 405 | 125550 | 391.67 | 121417.7 | 10.8%
F021 | Washed Rock (Special Provisions) | cubic metre | 10 | 500 | 5000 | 540 | 5400 | 49.8%
F492 | Roadway Work (B.F. 76028) (BCS 18.7) | lump sum | 1 | 45000 | 45000 | 91666.67 | 91666.67 | 34%
|  | Bridge File Modified Tender Value |  |  | 2859238.99 |  | 5557953.46 | 5.7%
|  | Total Tender Value |  |  |  |  | 8541846.67 | 5.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | PRORATED - Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 84 | 126000 | 13.3%
Tender: 25520 ¦ Bridge File: 76028-2 ¦ Tender Opening Date: 2025-09-18
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
25520 | Construct WSP Culvert Install CSP Culvert Liner | Culvert | Multiple | New and Lined Culverts | 2025-2026 | 2025-09-18 | 3 | 2026-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76042-2 | 33 km Northeast of Swan Hills | Peace | 33:14 | Tributary to Chalmers Creek | 1 x 2440 SWSP - 1 x 2000 CSP Liner | 95 - 83 | 178 | 2.2
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 128961.01 | 128961.01 | 250086.86 | 250086.86 | 26.9%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 5 | 2000 | 10000 | 513.33 | 2566.65 | 126.5%
E612 | Fish Capture and Release (Special Provisions) | day | 2 | 2000 | 4000 | 961.67 | 1923.34 | 69.5%
G101 | Clearing and Mulching (HCS 2.1.4) | hectare | 0.6 | 72000 | 43200 | 13333.33 | 8000 | 35.4%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 200 | 28 | 5600 | 20 | 4000 | 20.4%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 300 | 15.5 | 4650 | 15 | 4500 | 27.2%
E020 | Fibre/Straw Rolls - Supply and Install (Special Provisions) | metre | 200 | 24 | 4800 | 18.33 | 3666 | 25.7%
E052 | Tree Planting (Special Provisions) | unit | 875 | 28 | 24500 | 26.67 | 23336.25 | 23.4%
F750 | Traffic Accommodation for Bridge Construction (B.F. 76042) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 15000 | 15000 | 68666.67 | 68666.67 | 32.5%
F186 | Excavation - Structural (B.F. 76042) (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 125000 | 125000 | 49%
F187 | Excavation - Channel (B.F. 76042) (BCS 1.6.1) | lump sum | 1 | 13500 | 13500 | 58333.33 | 58333.33 | 20.2%
F020 | CSP Liner Supply and Install (2000 mm dia.) (Special Provisions) | metre | 83 | 1400 | 116200 | 2500 | 207500 | 16.3%
F021 | Grouting Liners (B.F. 76042) (Special Provisions) | cubic metre | 340 | 720 | 244800 | 1033.33 | 351332.2 | 31.9%
F020 | Smooth Wall Steel Pipe - Supply (2438 mm OD) (B.F. 76042) (Special Provisions) | metre | 95 | 2900 | 275500 | 6400 | 608000 | 25.1%
F020 | Smooth Wall Steel Pipe - Install (2438 mm OD) (B.F. 76042) (Special Provisions) | metre | 95 | 3600 | 342000 | 8333.33 | 791666.35 | 15%
F715 | Substrate Holders - Steel (B.F. 76042) (BCS 18.7) | unit | 11 | 2300 | 25300 | 1166.67 | 12833.37 | 53.5%
F021 | Substrate Material (Class 1M) (B.F. 76042) (Special Provisions) | cubic metre | 19 | 400 | 7600 | 616.67 | 11716.73 | 44.1%
F196 | Backfill - Non-Granular (B.F. 76042) (BCS 2.4) | lump sum | 1 | 20000 | 20000 | 75000 | 75000 | 27.2%
F500 | Heavy Rock Riprap (Class 1) (B.F. 76042) (BCS 10.7) | cubic metre | 154 | 405 | 62370 | 400 | 61600 | 10.2%
F492 | Roadway Work (B.F. 76042) (BCS 18.7) | lump sum | 1 | 45000 | 45000 | 61666.67 | 61666.67 | 45.1%
|  | Bridge File Modified Tender Value |  |  | 1417981.01 |  | 2731394.42 | 9.8%
|  | Total Tender Value |  |  |  |  | 8541846.67 | 5.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | PRORATED - Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 84 | 126000 | 13.3%
Tender: 25520 ¦ Bridge File: 76042-2 ¦ Tender Opening Date: 2025-09-18
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22993 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2025-2026 | 2025-09-23 | 4 | 2026-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75932-1 | 14 km South of Cochrane | Southern | 22:14 | Highway 1 | 5 x 910 RB | 13 ¦ 27 ¦ 27 ¦ 13 | 80 | 12.5
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 129000 | 129000 | 283666.67 | 283666.67 | 14.4%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 400000 | 400000 | 447584 | 447584 | 32.6%
F018 | Temporary Traffic Barriers (Special Provisions) | lump sum | 1 | 58000 | 58000 | 86666.67 | 86666.67 | 33.2%
F022 | ACP Surface Removal (Special Provisions) | square metre | 360 | 120 | 43200 | 143.33 | 51598.8 | 23%
F765 | Full Depth Repair - Deck (BCS 20.6.2) | square metre | 6 | 2500 | 15000 | 3900 | 23400 | 16.6%
F760 | Partial Depth Repair - Deck Top (BCS 20.6.2) | square metre | 15 | 2300 | 34500 | 1639.67 | 24595.05 | 27.8%
F760 | Partial Depth Repair - Deck Underside (BCS 20.6.2) | square metre | 50 | 2300 | 115000 | 3233.33 | 161666.5 | 15.2%
F760 | Partial Depth Repair - Curbs (Face and Top) (BCS 20.6.2) | square metre | 10 | 1800 | 18000 | 2141.67 | 21416.7 | 17.5%
F760 | Partial Depth Repair - Curbs (Fascia and Soffit) (BCS 20.6.2) | square metre | 30 | 2800 | 84000 | 3198.33 | 95949.9 | 13.6%
F760 | Partial Depth Repair - Abutments and Wingwalls (BCS 20.6.2) | square metre | 8 | 2600 | 20800 | 2450 | 19600 | 12.6%
F760 | Partial Depth Repair - Piers (BCS 20.6.2) | square metre | 8 | 3300 | 26400 | 2553.33 | 20426.64 | 8.5%
F018 | Abutment and Curb Modifications (Special Provisions) | lump sum | 1 | 40000 | 40000 | 62793.33 | 62793.33 | 23.2%
F020 | Deck Overlay Crack Repairs (Special Provisions) | metre | 180 | 150 | 27000 | 253.33 | 45599.4 | 41.4%
F018 | Deck Joint Replacements (Special Provisions) | lump sum | 1 | 115000 | 115000 | 349973.33 | 349973.33 | 19.8%
F993 | Galvanic Corrosion Protection - Supply and Install (Special Provisions) | anodes | 98 | 120 | 11760 | 133.33 | 13066.34 | 18.7%
F018 | Abutment Bearing Replacements (Special Provisions) | lump sum | 1 | 140000 | 140000 | 301358.33 | 301358.33 | 24%
Q795 | Chip Seal Coat (CRS-2P) - Bridge Decks Des. 3 Class 12.5BW (HCS 3.24.12) | square metre | 550 | 50 | 27500 | 188.33 | 103581.5 | 32.6%
F018 | Steel Girder Pressure Washing (Special Provisions) | lump sum | 1 | 18000 | 18000 | 64588.33 | 64588.33 | 39.7%
F018 | Concrete Cleaning and Sealing (Special Provisions) | lump sum | 1 | 30000 | 30000 | 29736.67 | 29736.67 | 24.8%
F020 | Median Traffic Separator System Repairs (Special Provisions) | metre | 24 | 600 | 14400 | 708.33 | 16999.92 | 32.4%
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 15000 | 15000 | 11480 | 11480 | 47.9%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 42 | 550 | 23100 | 1678.33 | 70489.86 | 43.8%
|  | Bridge File Modified Tender Value |  |  | 1405660 |  | 2306237.94 | 15.8%
|  | Total Tender Value |  |  |  |  | 2855242.33 | 14.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 135 | 202500 | 16.1%
F003 | Lane Closure for Bridge Construction - Hwy 22 (GCS 1.2.42.5) (Special Provisions) | day | 1500 | - | - | 150 | 225000 | 5.4%
F003 | Lane Closure for Bridge Construction - Hwy 1 WBL (GCS 1.2.42.5) (Special Provisions) | day | 1500 | - | - | 13 | 19500 | 72.5%
F003 | Lane Closure for Bridge Construction - Hwy 1 EBL (GCS 1.2.42.5) (Special Provisions) | day | 1500 | - | - | 13 | 19500 | 72.5%
F003 | Lane Closure for Bridge Construction - Hwy 1 Single WBL (GCS 1.2.42.5) (Special Provisions) | day | 1500 | - | - | 27 | 40500 | 42.9%
F003 | Lane Closure for Bridge Construction - Hwy 1 Single EBL (GCS 1.2.42.5) (Special Provisions) | day | 1500 | - | - | 27 | 40500 | 42.9%
Tender: 22993 ¦ Bridge File: 75932-1 ¦ Tender Opening Date: 2025-09-23
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22743 | Remove CSP Culvert | Culvert | Highway | Remove Culvert | 2025-2026 | 2025-09-25 | 5 | 2027-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
9223-1 | Near Cooking Lake | North Central | 14:06 | Cattlepass | 1 x 2250 CSP | 34 | 34 | 2.3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 1483.33 | 1483.33 | 5138.77 | 5138.77 | 14.5%
X018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 541.66 | 541.66 | 2035.72 | 2035.72 | 86%
F018 | Excavation - Structural (B.F. 09223) (Special Provisions) | lump sum | 1 | 10000 | 10000 | 22966.67 | 22966.67 | 9.3%
F486 | Demolition, Disposal and Salvage of Existing Structure (Cattlepass B.F. 09223) (BCS 18.7) (Special Provisions) | lump sum | 1 | 8000 | 8000 | 13233.33 | 13233.33 | 67.3%
|  | Bridge File Modified Tender Value |  |  | 20024.99 |  | 43374.49 | 22.3%
|  | Total Tender Value |  |  |  |  | 39248409.69 | 4.9%
Tender: 22743 ¦ Bridge File: 9223-1 ¦ Tender Opening Date: 2025-09-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22743 | Bridge Rehabilitation | Bridge | Highway | Bridge Rehabilitation | 2025-2026 | 2025-09-25 | 5 | 2027-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
77126-1 | 10 km East of Sherwood Park | North Central | 21:26 | Highway 14 | 14 x 1270 FC | 36 ¦ 36 | 72 | 23.5
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 81797.26 | 81797.26 | 185435.4 | 185435.4 | 11.3%
X018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 29869.52 | 29869.52 | 74972.97 | 74972.97 | 94.1%
X002 | Extra Work - BF 77126 High Load Damage Repairs (Special Provisions) | Total Force Account | 1 | 500000 | 500000 | 500000 | 500000 | 0%
F018 | Bridgerail Upgrade (BF 77126) (Special Provisions) | lump sum | 1 | 120000 | 120000 | 162737.55 | 162737.55 | 56%
F018 | Approach Rail Transitions - Supply and Install (Special Provisions) | lump sum | 1 | 40000 | 40000 | 40570.88 | 40570.88 | 16.8%
F018 | Remove Existing Concrete Median (BF 77126) (Special Provisions) | lump sum | 1 | 40000 | 40000 | 170101.33 | 170101.33 | 76.1%
F018 | Concrete Median - Supply and Install (BF 77126) (Special Provisions) | lump sum | 1 | 162000 | 162000 | 70400 | 70400 | 45.1%
F993 | Galvanic Corrosion Protection - Supply and Install (Special Provisions) | anodes | 240 | 90 | 21600 | 160.67 | 38560.8 | 17.3%
F018 | Deck Joint Modifications (Special Provisions) | lump sum | 1 | 30000 | 30000 | 96333.33 | 96333.33 | 54.2%
F018 | Deck Joint Cover Plates - Supply and Install (Special Provisions) | lump sum | 1 | 30000 | 30000 | 54103.33 | 54103.33 | 60.6%
F018 | Deck Joint Seals - Supply and install (Special Provisions) | lump sum | 1 | 10000 | 10000 | 58283.33 | 58283.33 | 52.7%
F018 | Existing Drain Troughs - Removal (Special Provisions) | lump sum | 1 | 15000 | 15000 | 28550 | 28550 | 53.7%
F911 | Drain Troughs (BF 77126) (BCS 9.7) | metre | 60 | 400 | 24000 | 1023.33 | 61399.8 | 22.8%
|  | Bridge File Modified Tender Value |  |  | 1104266.78 |  | 1541448.72 | 7.8%
|  | Total Tender Value |  |  |  |  | 39248409.69 | 4.9%
Tender: 22743 ¦ Bridge File: 77126-1 ¦ Tender Opening Date: 2025-09-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22743 | Construct Sign Structures | Sign Structure | Highway | New Sign Structures | 2025-2026 | 2025-09-25 | 5 | 2027-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
85071ZW1-13 | 3 km East of Edmonton | North Central | 14:04 | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 24805.77 | 24805.77 | 67967.69 | 67967.69 | 11.7%
X018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 9058.2 | 9058.2 | 28238.35 | 28238.35 | 97.6%
F170 | Demolition and Disposal of Bridge Structure (Overhead Sign Structure B.F. 85071 ZW1-10) (BCS 21.4.1) | lump sum | 1 | 25000 | 25000 | 41359.33 | 41359.33 | 6.2%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 85071 ZW1-13) (BCS 24.5) | lump sum | 1 | 250000 | 250000 | 405357.33 | 405357.33 | 6%
F992 | Sign Panels - Extruded Aluminum - Supply and Install (B.F. 85071 ZW1-13) (BCS 24.5) | square metre | 43 | 605 | 26015 | 483.67 | 20797.81 | 6%
|  | Bridge File Modified Tender Value |  |  | 334878.97 |  | 563720.51 | 4.6%
|  | Total Tender Value |  |  |  |  | 39248409.69 | 4.9%
Tender: 22743 ¦ Bridge File: 85071-13 ¦ Tender Opening Date: 2025-09-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
25083 | Replace Superstructure SLW Precast Concrete Girder Bridge | Bridge | Single | Bridge Rehabilitation | 2025-2026 | 2025-10-09 | 6 | 2026-05-16
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76396-1 | 8 km North of Lac La Biche | North Centra | Local Road | Lac La Biche | 10 x 510 SLW | 10 ¦ 12 ¦ 10 | 32 | 12.3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 119000 | 119000 | 244333.33 | 244333.33 | 8%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 5000 | 5000 | 33750 | 33750 | 86.8%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 10000 | 10000 | 51666.67 | 51666.67 | 25.4%
F486 | Demolition, Disposal and Salvage of Existing Structure (BCS 18.7) (Special Provisions) | lump sum | 1 | 80000 | 80000 | 191733.33 | 191733.33 | 16.7%
F189 | Excavation - Channel (BCS 1.6.1) | cubic metre | 750 | 60 | 45000 | 53.33 | 39997.5 | 37.8%
F814 | Supply of Piling - Plain Steel Pipe Pile (BCS 3.6.1) (Special Provisions) | metre | 157.1 | 350 | 54985 | 168.33 | 26444.64 | 59.9%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 6 | 6000 | 36000 | 12000 | 72000 | 25.5%
F818 | Pile Driving (BCS 3.6.1) (Special Provisions) | metre | 68 | 30 | 2040 | 23.5 | 1598 | 92%
F822 | Pile Concrete (Class) - Supply and Place (BCS 4.27.1) (Special Provisions) | cubic metre | 3 | 2000 | 6000 | 6500 | 19500 | 37.1%
F820 | PDA Testing (BCS 3.6.4) (Special Provisions) | test | 4 | 3500 | 14000 | 3496.67 | 13986.68 | 53.5%
F760 | Partial Depth Repair (BCS 20.6.2) (Special Provisions) | square metre | 20.4 | 2500 | 51000 | 1591.67 | 32470.07 | 62.8%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1013 | 3 | 3039 | 4.33 | 4386.29 | 21.8%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1013 | 2.5 | 2532.5 | 4.83 | 4892.79 | 39.9%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 6 | 3000 | 18000 | 4616.67 | 27700.02 | 32.8%
F018 | Pier Construction (Special Provisions) | lump sum | 1 | 150000 | 150000 | 189666.67 | 189666.67 | 15%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 210 | 320 | 67200 | 400 | 84000 | 23.4%
F017 | Misc. Bridge Material - Plain Elastometric Bearing - Supply and Place (Special Provisions) | lump sum | 1 | 5000 | 5000 | 25283.33 | 25283.33 | 28.8%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - SLW-510 Girders (BCS 7.4) (Special Provisions) | lump sum | 1 | 120000 | 120000 | 745600 | 745600 | 4.5%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - Approach Slabs (BCS 7.4) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 115866.67 | 115866.67 | 6.2%
F970 | Miscellaneous Iron - Benchmark Tablet and Plaques (BCS 13.5) (Special Provisions) | lump sum | 1 | 5000 | 5000 | 7833.33 | 7833.33 | 82.7%
F204 | Backfill - Crushed Aggregate (BCS 2.4) (Special Provisions) | lump sum | 1 | 20000 | 20000 | 50950 | 50950 | 23.4%
F974 | Waterproofing (BCS 16.5) | square metre | 292 | 150 | 43800 | 86.67 | 25307.64 | 21.8%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 179.4 | 450 | 80730 | 583.33 | 104649.4 | 28.3%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 60000 | 60000 | 51933.33 | 51933.33 | 28.3%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 92.5 | 200 | 18500 | 371.67 | 34379.48 | 62.1%
F018 | Pedestrian Handrail Removal and Reinstall (Special Provisions) | lump sum | 1 | 10000 | 10000 | 13500 | 13500 | 62.5%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 250000 | 250000 | 105000 | 105000 | 37.5%
E020 | Erosion Control Barrier (Straw Wattle) (Special Provisions) | metre | 100 | 20 | 2000 | 46.67 | 4667 | 41.3%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) (Special Provisions) | square metre | 200 | 15 | 3000 | 31.67 | 6334 | 52.1%
|  | Bridge File Modified Tender Value |  |  | 1331826.5 |  | 2329430.17 | 7%
|  | Total Tender Value |  |  |  |  | 2424938.17 | 7.7%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 90 | 135000 | 64 | 96000 | 27.1%
Tender: 25083 ¦ Bridge File: 76396-1 ¦ Tender Opening Date: 2025-10-09
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
12478 | Construct SPCSP Culvert | Culvert | Multiple | Replace Bridge with Culvert | 2025-2026 | 2025-10-28 | 8 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
1974-2 | Near Trochu | Central | 585:02 | Tributary to Ghostpine Creek | 1 x 3670 SPCSP | 40 | 40 | 3.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 78000 | 78000 | 166047.11 | 166047.11 | 18%
F750 | Traffic Accommodation for Bridge Construction (B.F. 1974) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 30000 | 30000 | 11977.26 | 11977.26 | 5.6%
F170 | Demolition and Disposal of Bridge Structure (B.F. 1974) (BCS 21.4.1) | lump sum | 1 | 50000 | 50000 | 16226.44 | 16226.44 | 63.8%
F018 | Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 10000 | 10000 | 4599.77 | 4599.77 | 1.7%
F018 | Environmental Protection Works (Special Provisions) | lump sum | 1 | 25000 | 25000 | 10764.44 | 10764.44 | 61%
C025 | Care of Water (Water Management) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 31866.63 | 31866.63 | 21.7%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 30000 | 30000 | 15384.42 | 15384.42 | 16.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 15 | 1600 | 24000 | 1653.14 | 24797.1 | 29%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 1600 | 4800 | 2284.37 | 6853.11 | 29.2%
F493 | SPCSP - Supply (BCS 18.7) | metre | 40.23 | 3500 | 140805 | 3262.55 | 131252.39 | 9.5%
F494 | SPCSP - Assembly (BCS 18.7) | metre | 40.23 | 1600 | 64368 | 1540.94 | 61992.02 | 16.9%
F204 | Backfill - Crushed Aggregate (Des 2 Cl 40 & Des 2 Cl 25) (BCS 2.4) | lump sum | 1 | 49500 | 49500 | 99242.75 | 99242.75 | 3%
F196 | Backfill - Non-Granular (Clay Seals) (BCS 2.4) | lump sum | 1 | 37500 | 37500 | 58253.65 | 58253.65 | 18%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 190 | 300 | 57000 | 244.43 | 46441.7 | 21.8%
F018 | Concrete End Treatment - Upstream End Only (Special Provisions) | lump sum | 1 | 40000 | 40000 | 51609.51 | 51609.51 | 11.2%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 100000 | 100000 | 113800.74 | 113800.74 | 18.4%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.2 | 25000 | 5000 | 27376.76 | 5475.35 | 46.8%
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.06 | 50000 | 3000 | 69664.32 | 4179.86 | 26.4%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 300 | 20 | 6000 | 15.98 | 4794 | 40.2%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 600 | 20 | 12000 | 11.17 | 6702 | 68.9%
|  | Bridge File Modified Tender Value |  |  | 791973 |  | 872260.25 | 1.4%
|  | Total Tender Value |  |  |  |  | 3179582.82 | 4.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 40 | 60000 | 27 | 40500 | 14.9%
Tender: 12478 ¦ Bridge File: 1974-2 ¦ Tender Opening Date: 2025-10-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
12478 | Construct CSP Culvert | Culvert | Multiple | Replace Culvert with Culvert | 2025-2026 | 2025-10-28 | 8 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
70562-2 | 21 km South of Delia | Central | 576:02 | McConnell Coulee | 1 x 2400 CSP | 63 | 63 | 2.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 68000 | 68000 | 169031.95 | 169031.95 | 24.1%
F750 | Traffic Accommodation for Bridge Construction (B.F. 70562) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 150000 | 150000 | 58604.75 | 58604.75 | 49.5%
F170 | Demolition and Disposal of Bridge Structure (B.F. 70562) (BCS 21.4.1) | lump sum | 1 | 25000 | 25000 | 9116.15 | 9116.15 | 18.9%
F018 | Environmental Protection Works (Special Provisions) | lump sum | 1 | 25000 | 25000 | 13289.44 | 13289.44 | 89.3%
C025 | Care of Water (Water Management) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 35579.95 | 35579.95 | 19.1%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 90000 | 90000 | 52585.84 | 52585.84 | 22.2%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 15 | 1600 | 24000 | 1576.47 | 23647.05 | 26.6%
E612 | Fish Capture and Release | day | 3 | 1600 | 4800 | 1897.7 | 5693.1 | 17.2%
F495 | CSP with Couplers - Supply (BCS 18.7) | metre | 64 | 2000 | 128000 | 877.49 | 56159.36 | 2.4%
F496 | CSP - Assembly (BCS 18.7) | metre | 64 | 800 | 51200 | 252.74 | 16175.36 | 26.3%
F204 | Backfill - Crushed Aggregate (Des 2 Cl 40 & Des 2 Cl 25) (BCS 2.4) | lump sum | 1 | 69000 | 69000 | 130156.38 | 130156.38 | 18.1%
F196 | Backfill - Non-Granular (Clay Seals) (BCS 2.4) | lump sum | 1 | 14000 | 14000 | 23004.47 | 23004.47 | 9.4%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 90 | 300 | 27000 | 334.24 | 30081.6 | 25.3%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 125000 | 125000 | 218954.6 | 218954.6 | 29.4%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.2 | 25000 | 5000 | 27360.1 | 5472.02 | 46.9%
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.03 | 50000 | 1500 | 73912.67 | 2217.38 | 29.3%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 350 | 20 | 7000 | 14.27 | 4994.5 | 29.8%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 300 | 20 | 6000 | 11.31 | 3393 | 67.4%
|  | Bridge File Modified Tender Value |  |  | 845500 |  | 858156.9 | 11.4%
|  | Total Tender Value |  |  |  |  | 3179582.82 | 4.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 30 | 45000 | 29 | 43500 | 22.9%
Tender: 12478 ¦ Bridge File: 70562-2 ¦ Tender Opening Date: 2025-10-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
12478 | Construct SPCSP Culvert | Culvert | Multiple | Replace Culvert with Culvert | 2025-2026 | 2025-10-28 | 8 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
77652-2 | 5 km West of Winfield | Central | 13:04 | Modeste Creek | 1 x 3990 SPCSP | 51 | 51 | 4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 90000 | 90000 | 228900.71 | 228900.71 | 36.7%
F750 | Traffic Accommodation for Bridge Construction (B.F. 77652) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 100000 | 100000 | 62730.66 | 62730.66 | 57.9%
F170 | Demolition and Disposal of Bridge Structure (B.F. 77652) (BCS 21.4.1) | lump sum | 1 | 30000 | 30000 | 9107.82 | 9107.82 | 18.9%
F018 | Environmental Protection Works | lump sum | 1 | 25000 | 25000 | 12208.41 | 12208.41 | 68.5%
C025 | Care of Water (Special Provisions) | lump sum | 1 | 30000 | 30000 | 36548.04 | 36548.04 | 18.3%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 87500 | 87500 | 46397.68 | 46397.68 | 33.9%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 15 | 1600 | 24000 | 1586.47 | 23797.05 | 26.9%
E612 | Fish Capture and Release | day | 3 | 1600 | 4800 | 2001.04 | 6003.12 | 18.6%
F493 | SPCSP - Supply (BCS 18.7) | metre | 51.21 | 3800 | 194598 | 3493.11 | 178882.16 | 11.7%
F494 | SPCSP - Assembly (BCS 18.7) | metre | 51.21 | 2000 | 102420 | 1492.14 | 76412.49 | 13.8%
F204 | Backfill - Crushed Aggregate (BCS 2.4) | lump sum | 1 | 82500 | 82500 | 156090.69 | 156090.69 | 5%
F196 | Backfill - Non-Granular (BCS 2.4) | lump sum | 1 | 40000 | 40000 | 127152.78 | 127152.78 | 42.3%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 200 | 300 | 60000 | 299.01 | 59802 | 38.4%
F018 | Concrete End Treatment - Upstream End Only | lump sum | 1 | 42000 | 42000 | 51923.43 | 51923.43 | 10.9%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 100000 | 100000 | 209330.45 | 209330.45 | 26.1%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.2 | 25000 | 5000 | 27376.76 | 5475.35 | 46.8%
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.03 | 50000 | 1500 | 73896 | 2216.88 | 29.3%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 200 | 20 | 4000 | 16.59 | 3318 | 35.9%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 300 | 20 | 6000 | 11.23 | 3369 | 67.8%
|  | Bridge File Modified Tender Value |  |  | 1029318 |  | 1299666.72 | 2.3%
|  | Total Tender Value |  |  |  |  | 3179582.82 | 4.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 40 | 60000 | 44 | 66000 | 26.7%
Tender: 12478 ¦ Bridge File: 77652-2 ¦ Tender Opening Date: 2025-10-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20171 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2025-2026 | 2025-10-28 | 7 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
77728-2 | Near Nordegg | Central | 11:04 | Shunda Creek | 16 x 700 SLC | 20 | 20 | 19.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 400000 | 400000 | 551472.81 | 551472.81 | 11.1%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 250000 | 250000 | 139111.06 | 139111.06 | 57%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 50000 | 50000 | 54157.32 | 54157.32 | 25%
E612 | Fish Capture and Release (Special Provisions) | day | 4 | 4000 | 16000 | 3227.02 | 12908.08 | 70.6%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 8 | 2000 | 16000 | 2202.68 | 17621.44 | 121.8%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 120000 | 120000 | 342376.84 | 342376.84 | 55.1%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 20000 | 20000 | 45364.09 | 45364.09 | 118.2%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 15000 | 15000 | 18002.2 | 18002.2 | 47.6%
F812 | Supply of Piling - Plain Steel H-Pile - HP 310 x 94 (BCS 3.6.1) | metre | 370 | 250 | 92500 | 216.48 | 80097.6 | 20.6%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 24 | 5000 | 120000 | 5867.2 | 140812.8 | 51.7%
F818 | Pile Driving (BCS 3.6.1) | metre | 370 | 50 | 18500 | 50.24 | 18588.8 | 84.2%
F820 | PDA Testing (BCS 3.6.4) | test | 4 | 2000 | 8000 | 1741.7 | 6966.8 | 17.8%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 8200 | 4 | 32800 | 3.05 | 25010 | 6.1%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 19100 | 9 | 171900 | 13 | 248300 | 13.2%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1100 | 14 | 15400 | 16.78 | 18458 | 10.9%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 28400 | 3.5 | 99400 | 3.24 | 92016 | 13.5%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 65 | 2500 | 162500 | 3871.13 | 251623.45 | 21.8%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 500 | 300 | 150000 | 224.07 | 112035 | 24.7%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) (Special Provisions) | lump sum | 1 | 1000000 | 1000000 | 767926.39 | 767926.39 | 13%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 120 | 3000 | 360000 | 4678.52 | 561422.4 | 7.2%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 7500 | 7500 | 7718.65 | 7718.65 | 44.7%
F974 | Waterproofing (BCS 16.5) | square metre | 610 | 125 | 76250 | 75.22 | 45884.2 | 24.4%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 120 | 400 | 48000 | 390.19 | 46822.8 | 23%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 600000 | 600000 | 1020483.41 | 1020483.41 | 23.4%
F018 | Drain Troughs (Special Provisions) | lump sum | 1 | 40000 | 40000 | 41716.57 | 41716.57 | 13.5%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 45000 | 45000 | 47678.73 | 47678.73 | 7.4%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 40000 | 40000 | 64616.85 | 64616.85 | 16.2%
E052 | Class 3 Rock Riprap Boulders (Special Provisions) | unit | 28 | 250 | 7000 | 624.61 | 17489.08 | 43.4%
E003 | Willow Shrub Plantings (1 Gallon pot) (Special Provisions) | planting | 60 | 75 | 4500 | 160.82 | 9649.2 | 62.5%
E003 | Willow Shrub Plantings (5 Gallon pot) (Special Provisions) | planting | 55 | 250 | 13750 | 271.35 | 14924.25 | 60.4%
E020 | Straw Rolls (Special Provisions) | metre | 250 | 20 | 5000 | 13.06 | 3265 | 16.6%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 400 | 10 | 4000 | 8.18 | 3272 | 28.2%
|  | Bridge File Modified Tender Value |  |  | 4009000 |  | 4827791.82 | 6.1%
|  | Total Tender Value |  |  |  |  | 5002199.17 | 5.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 100 | 150000 | 116 | 174000 | 35.5%
Tender: 20171 ¦ Bridge File: 77728-2 ¦ Tender Opening Date: 2025-10-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21391 | Construct SPCSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2025-2026 | 2025-11-25 | 7 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
77462-2 | 39 km East of Nordegg | Central | 11:08 | Jackfish Creek | 1 x 3050 SPCSP | 69 | 69 | 3.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 216300 | 216300 | 190123.33 | 190123.33 | 15.8%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 450000 | 450000 | 252557 | 252557 | 10.5%
C025 | Care of Water (Special Provisions) | lump sum | 1 | 15000 | 15000 | 122341.67 | 122341.67 | 74%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 2500 | 15000 | 1335.67 | 8014.02 | 46.8%
E612 | Fish Capture and Release (Special Provisions) | day | 2 | 5000 | 10000 | 2211.67 | 4423.34 | 54.2%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 15000 | 15000 | 38042.67 | 38042.67 | 37.6%
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 65 | 800 | 52000 | 808.33 | 52541.45 | 27.8%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 350000 | 350000 | 275244.33 | 275244.33 | 22.3%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 10000 | 10000 | 18243.33 | 18243.33 | 48.2%
G210 | Rippable Rock Excavation - Premium (HCS 2.3.6) | cubic metre | 2200 | 5.5 | 12100 | 47.39 | 104258 | 45%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 355000 | 355000 | 290956.67 | 290956.67 | 15.3%
G022 | Import Topsoil - Supply and Placement (Provisional) (Special Provisions) | square metre | 4000 | 2.5 | 10000 | 17.77 | 71080 | 56.9%
F493 | SPCSP - Supply (3.05 m dia.) (BCS 18.7) | metre | 69 | 3500 | 241500 | 2938 | 202722 | 16%
F494 | SPCSP - Assembly (3.05 m dia.) (BCS 18.7) | metre | 69 | 1100 | 75900 | 1524.67 | 105202.23 | 41.1%
F655 | Concrete End Treatment (BCS 18.7) | unit | 2 | 30000 | 60000 | 50148.33 | 100296.66 | 7.7%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 110 | 350 | 38500 | 248.93 | 27382.3 | 7.6%
F505 | Heavy Rock Riprap (Class 1M) (BCS 10.7) | cubic metre | 25 | 320 | 8000 | 319.2 | 7980 | 12.9%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 1500 | 1500 | 2321.33 | 2321.33 | 23.7%
F981 | Asphalt Concrete Pavement - Mix Type H2 (PG58-28) Mix Type H2 (PG 58-28) (BCS 17.7.1) | lump sum | 1 | 370500 | 370500 | 230318.33 | 230318.33 | 15.5%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 75000 | 75000 | 121775.33 | 121775.33 | 18.8%
E020 | Erosion Control Barrier (Fibre Rolls) (Special Provisions) | metre | 300 | 20 | 6000 | 19.2 | 5760 | 24.6%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 200 | 10 | 2000 | 14.79 | 2958 | 65.3%
|  | Bridge File Modified Tender Value |  |  | 2389300 |  | 2234541.99 | 10.2%
|  | Total Tender Value |  |  |  |  | 2339064.67 | 8.7%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 60 | 90000 | 70 | 105000 | 26.1%
Tender: 21391 ¦ Bridge File: 77462-2 ¦ Tender Opening Date: 2025-11-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23914 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2025-2026 | 2025-11-27 | 10 | 2026-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74600W-3 | 37 km West of Cochrane | Southern | 1:04 | Bear Hill Road | 15 x 510 SLC | 10 ¦ 16 ¦ 10 | 36 | 18.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 669000 | 669000 | 460293.33 | 460293.33 | 42.9%
F750 | Traffic Accommodation for Bridge Construction (B.F. 74600W) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 600000 | 600000 | 1077981.33 | 1077981.33 | 41.3%
E018 | Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 5000 | 5000 | 10577.67 | 10577.67 | 42%
F170 | Demolition and Disposal of Bridge Structure (B.F. 74600W) (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 244351.67 | 244351.67 | 41.9%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 20000 | 20000 | 51839.33 | 51839.33 | 37.6%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 30000 | 30000 | 66063.67 | 66063.67 | 45.7%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 26 | 4000 | 104000 | 2504 | 65104 | 21.3%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 310 | 250 | 77500 | 153.17 | 47482.7 | 1.5%
F817 | Test Pile Driving (B.F. ____) (BCS 3.6.1) | metre | 24 | - | - | 157 | 3768 | 3.2%
F818 | Pile Driving (BCS 3.6.1) | metre | 273 | 75 | 20475 | 42.33 | 11556.09 | 121.4%
F809 | Additional Pile Splicing (B.F. ____) (BCS 3.6.1) | splice | 26 | - | - | 1138.33 | 29596.58 | 1.4%
F819 | Pile Tip Reinforcement (BCS 3.6.1) | pile | 26 | 300 | 7800 | 280.67 | 7297.42 | 1.7%
F824 | Drill Rig Set-up (Drilled Piles) (BCS 3.6.2) | pile | 18 | 7500 | 135000 | 9563.33 | 172139.94 | 5.5%
F814 | Supply of Piling - Plain Steel Pipe Pile (BCS 3.6.1) | metre | 142 | 700 | 99400 | 442.67 | 62859.14 | 16.5%
F815 | Supply of Piling - Galvanized Steel Pipe Pile (BCS 3.6.1) | metre | 100 | 1250 | 125000 | 737 | 73700 | 1.5%
F826 | Pile Installation (Drilled Piles) (BCS 3.6.2) | metre | 174 | 200 | 34800 | 932.67 | 162284.58 | 3.5%
F820 | PDA Testing (BCS 3.6.4) | test | 4 | 3500 | 14000 | 1936 | 7744 | 1.8%
X018 | Drainage Culvert Modification (Special Provisions) | lump sum | 1 | 25000 | 25000 | 44655 | 44655 | 39.9%
F018 | Construction of Abutments (Special Provisions) | lump sum | 1 | 20000 | 20000 | 65373 | 65373 | 43.4%
F018 | Construction of Piers (Special Provisions) | lump sum | 1 | 50000 | 50000 | 108411.67 | 108411.67 | 48.8%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (10.0 m SLC-510 - Interior) (BCS 7.4) | lump sum | 1 | 585000 | 585000 | 444702 | 444702 | 1.9%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (10.0 m SLC-510 - Exterior (BCS 7.4) | lump sum | 1 | 102000 | 102000 | 124920.67 | 124920.67 | 3.2%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (16.0 m SLC-510 - Interior) (BCS 7.4) | lump sum | 1 | 468000 | 468000 | 342314 | 342314 | 1.6%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (16.0 m SLC-510 - Exterior) (BCS 7.4) | lump sum | 1 | 81600 | 81600 | 111000.67 | 111000.67 | 2%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 25352 | 7.5 | 190140 | 9.83 | 249210.16 | 8.6%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 862 | 10.75 | 9266.5 | 12.5 | 10775 | 8.6%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 14485 | 3.15 | 45627.75 | 2.42 | 35053.7 | 2.6%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 40699 | 2.5 | 101747.5 | 1.78 | 72444.22 | 18.7%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 150 | 2400 | 360000 | 1895.33 | 284299.5 | 10.8%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 95 | 1900 | 180500 | 1667 | 158365 | 49.5%
F822 | Pile Concrete (Class) - Supply and Place (BCS 4.27.1) | cubic metre | 180 | 1000 | 180000 | 799.67 | 143940.6 | 23.3%
F595 | Concrete Slope Protection (BCS 4.27.2) | square metre | 465 | 150 | 69750 | 455 | 211575 | 14.3%
F911 | Drain Troughs (BCS 9.7) | metre | 80 | 400 | 32000 | 493.33 | 39466.4 | 20.1%
F974 | Waterproofing (BCS 16.5) | square metre | 856 | 75 | 64200 | 47.08 | 40300.48 | 3.5%
F978 | Asphalt Concrete Pavement Mix Type H1 (PG 58-28) (BCS 17.7.2) | tonne | 161 | 400 | 64400 | 351.33 | 56564.13 | 13.1%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 100000 | 100000 | 85953 | 85953 | 20.9%
F752 | Guardrail - Supply and Install (BCS 14.5) (Special Provisions) | lump sum | 1 | 60000 | 60000 | 59535 | 59535 | 4.6%
G452 | Remove and Dispose of Existing Fence (HCS 2.12.5) | kilometre | 0.18 | 30000 | 5400 | 14546.93 | 2618.45 | 51.1%
C248 | Temporary Fencing (Special Provisions) | metre | 200 | 40 | 8000 | 25.33 | 5066 | 54.5%
G480 | New Fence - Supply and Install - Class C (HCS 2.12.5) | kilometre | 0.15 | 50000 | 7500 | 51271.67 | 7690.75 | 32.3%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) (Special Provisions) | square metre | 2800 | 20 | 56000 | 3.64 | 10192 | 22.6%
E020 | Erosion Control Barrier (Fibre Rolls) - Supply and Install | metre | 750 | 15 | 11250 | 14.67 | 11002.5 | 6.4%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 2000 | 2000 | 8159.67 | 8159.67 | 71.5%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 250000 | 250000 | 369398.33 | 369398.33 | 18.9%
|  | Bridge File Modified Tender Value |  |  | 5121356.75 |  | 5657626.35 | 8%
|  | Total Tender Value |  |  |  |  | 5857798.83 | 7.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1250 | 130 | 162500 | 160 | 200000 | 5.1%
Tender: 23914 ¦ Bridge File: 74600-3 ¦ Tender Opening Date: 2025-11-27
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
12482 | Construct SPCSP Culvert | Culvert | Multiple | Replace Bridge with Culvert | 2025-2026 | 2025-12-11 | 10 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
629-2 | 10 km East of Red Willow | Central | 601:04 | Tributary to Red Willow Creek | 1 x 4300 SPCSP | 43 | 43 | 4.3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 100000 | 100000 | 82188.33 | 82188.33 | 34.2%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 30000 | 30000 | 16798.33 | 16798.33 | 49.5%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 30000 | 30000 | 45536 | 45536 | 7.6%
F018 | Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 10000 | 10000 | 3380.67 | 3380.67 | 36.6%
F018 | Environmental Protection Works (Special Provisions) | lump sum | 1 | 25000 | 25000 | 14255 | 14255 | 48.5%
C025 | Care of Water (Special Provisions) | lump sum | 1 | 25000 | 25000 | 13377 | 13377 | 63.2%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 48000 | 48000 | 58855.67 | 58855.67 | 57%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 15 | 1600 | 24000 | 765.67 | 11485.05 | 26.8%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 1600 | 4800 | 2593.33 | 7779.99 | 52.2%
F493 | SPCSP - Supply (BCS 18.7) | metre | 42.67 | 4000 | 170680 | 3974.9 | 169608.98 | 18.1%
F494 | SPCSP - Assembly (BCS 18.7) | metre | 42.67 | 2000 | 85340 | 1475.87 | 62975.37 | 30.2%
F204 | Backfill - Crushed Aggregate (Des 2 Cl 40 & Des 2 Cl 25) (BCS 2.4) | lump sum | 1 | 91000 | 91000 | 127745 | 127745 | 25.1%
F196 | Backfill - Non-Granular (Clay Seals) (BCS 2.4) | lump sum | 1 | 48000 | 48000 | 58102 | 58102 | 27.9%
F515 | Heavy Rock Riprap (Class 2) (BCS 10.7) | cubic metre | 470 | 350 | 164500 | 227.33 | 106845.1 | 28.2%
F018 | Concrete End Treatment - Upstream & Downstream Ends (Special Provisions) | lump sum | 1 | 90000 | 90000 | 84641.67 | 84641.67 | 7.8%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 100000 | 100000 | 44991 | 44991 | 40.4%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.4 | 25000 | 10000 | 25286.67 | 10114.67 | 49.8%
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.03 | 50000 | 1500 | 123280 | 3698.4 | 91.4%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 200 | 20 | 4000 | 25.13 | 5026 | 65%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 300 | 20 | 6000 | 13.77 | 4131 | 53.4%
|  | Bridge File Modified Tender Value |  |  | 1067820 |  | 931535.23 | 9%
|  | Total Tender Value |  |  |  |  | 1452486.61 | 7.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 40 | 60000 | 44 | 66000 | 23.9%
Tender: 12482 ¦ Bridge File: 629-2 ¦ Tender Opening Date: 2025-12-11
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
12482 | Construct CSP Culvert | Culvert | Multiple | Replace Culvert with Culvert | 2025-2026 | 2025-12-11 | 10 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75521-2 | 32 km Northeast of Gadsby | Central | 855:06 | Slough Creek | 1 x 2200 CSP | 32 | 32 | 2.2
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 100000 | 100000 | 42085 | 42085 | 50.7%
F750 | Traffic Accommodation for Bridge Construction (B.F. 75521) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 30000 | 30000 | 29456.67 | 29456.67 | 49.5%
F170 | Demolition and Disposal of Bridge Structure (B.F. 75521) (BCS 21.4.1) | lump sum | 1 | 25000 | 25000 | 13758 | 13758 | 69.2%
F018 | Environmental Protection Works (Special Provisions) | lump sum | 1 | 25000 | 25000 | 8185.33 | 8185.33 | 50.3%
C025 | Care of Water (Special Provisions) | lump sum | 1 | 25000 | 25000 | 11668.33 | 11668.33 | 53.4%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 40000 | 40000 | 35270 | 35270 | 55.6%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 15 | 1600 | 24000 | 765.67 | 11485.05 | 26.8%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 1600 | 4800 | 2593.33 | 7779.99 | 52.2%
F495 | CSP with Couplers - Supply (BCS 18.7) | metre | 32 | 1800 | 57600 | 1295.33 | 41450.56 | 36.7%
F496 | CSP - Assembly (BCS 18.7) | metre | 32 | 800 | 25600 | 422.67 | 13525.44 | 80.1%
F204 | Backfill - Crushed Aggregate (Des 2 Cl 40 & Des 2 Cl 25) (BCS 2.4) | lump sum | 1 | 34000 | 34000 | 59972 | 59972 | 48.4%
F196 | Backfill - Non-Granular (Clay Seal) (BCS 2.4) | lump sum | 1 | 12000 | 12000 | 29970 | 29970 | 48.3%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 70 | 300 | 21000 | 225.33 | 15773.1 | 27.4%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 100000 | 100000 | 72334 | 72334 | 21.8%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.2 | 25000 | 5000 | 33408 | 6681.6 | 51.1%
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.03 | 50000 | 1500 | 123280 | 3698.4 | 91.4%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 200 | 20 | 4000 | 25.13 | 5026 | 65%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 300 | 20 | 6000 | 14.43 | 4329 | 56.9%
|  | Bridge File Modified Tender Value |  |  | 540500 |  | 412448.47 | 9.9%
|  | Total Tender Value |  |  |  |  | 1452486.61 | 7.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 30 | 45000 | 28 | 42000 | 30.9%
Tender: 12482 ¦ Bridge File: 75521-2 ¦ Tender Opening Date: 2025-12-11
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
18625 | Construct WSP Culvert - Install WSP Culvert Liner | Culvert | Single | New and Lined Culverts | 2025-2026 | 2026-01-14 | 3 | 2026-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74295-2 | 4 km Southeast of Beaverlodge | Peace | 43:02 | Tributary to Beaverlodge River | 1 x 1830 WSP - 1 x 1680 WSP Liner | 161 - 123 | 284 | 1.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 419000 | 419000 | 276666.67 | 276666.67 | 44.4%
F750 | Traffic Accommodation for Bridge Construction (B.F. 74295) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 100000 | 100000 | 45833.33 | 45833.33 | 12.9%
X018 | Work Within CN Rail Right-of-Way (Special Provisions) | lump sum | 1 | 100000 | 100000 | 76666.67 | 76666.67 | 68.5%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 2000 | 20000 | 900 | 9000 | 59.5%
E612 | Fish Capture and Release (Special Provisions) | day | 2 | 2500 | 5000 | 3100 | 6200 | 52.9%
F188 | Excavation - Structural (B.F. 74295) (BCS 1.6.1) | cubic metre | 205 | 60 | 12300 | 51.67 | 10592.35 | 66.3%
F189 | Excavation - Channel (B.F. 74295) (BCS 1.6.1) | cubic metre | 2085 | 80 | 166800 | 30 | 62550 | 49.1%
F020 | Welded Steel Pipe - Supply (1829 mm OD) (B.F. 74295) (Special Provisions) | metre | 160.8 | 4000 | 643200 | 3903.33 | 627655.46 | 26.7%
F020 | Welded Steel Pipe - Supply (1678 mm OD) (B.F. 74295) (Special Provisions) | metre | 122.8 | 3600 | 442080 | 3570 | 438396 | 21.3%
F020 | Welded Steel Pipe - Install (1829 mm OD) (B.F. 74295) (Special Provisions) | metre | 95 | 8000 | 760000 | 6500 | 617500 | 32.6%
F020 | Welded Steel Pipe Extension - Install (1829 mm OD) (B.F. 74295) (Special Provisions) | metre | 65.8 | 2000 | 131600 | 2425 | 159565 | 54.3%
F020 | Welded Steel Pipe Extension - Install (1678 mm OD) (B.F. 74295) (Special Provisions) | metre | 65.8 | 2000 | 131600 | 2091.67 | 137631.89 | 45.6%
F020 | Welded Steel Pipe Liner - Install (1678 mm OD) (B.F. 74295) (Special Provisions) | metre | 57 | 3000 | 171000 | 2500 | 142500 | 43.2%
F021 | Grouting Liner (Special Provisions) | cubic metre | 71 | 900 | 63900 | 816.67 | 57983.57 | 16.1%
D494 | Drop Inlet Assemblies - Supply and Install (800 mm dia. C.S.P.) (Special Provisions) | metre | 2.8 | 3000 | 8400 | 4666.67 | 13066.68 | 44%
F203 | Backfill - Crushed Granular (B.F. 74295) Des. 2 Class 25 (BCS 2.4) | cubic metre | 250 | 215 | 53750 | 98.33 | 24582.5 | 43.6%
F200 | Backfill - Granular (B.F. 74295) Des. 2 Class 40 (BCS 2.4) | cubic metre | 3040 | 150 | 456000 | 90 | 273600 | 49.1%
F195 | Backfill - Non-Granular (B.F. 74295) (BCS 2.4) | cubic metre | 15004 | 45 | 675180 | 24.67 | 370148.68 | 34.8%
F515 | Heavy Rock Riprap (Class 2) (B.F. 74295) (BCS 10.7) | cubic metre | 95 | 400 | 38000 | 345.33 | 32806.35 | 10.2%
F525 | Heavy Rock Riprap (Class 3) (B.F. 74295) (BCS 10.7) | cubic metre | 150 | 500 | 75000 | 426.33 | 63949.5 | 17.7%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 250 | 35 | 8750 | 18.33 | 4582.5 | 12.9%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 800 | 17 | 13600 | 11.67 | 9336 | 20.2%
F020 | Fibre/Straw Rolls - Supply and Install (Special Provisions) | metre | 200 | 20 | 4000 | 20 | 4000 | 0%
E609 | Hydro-Seeding (HCS 2.20.4) | hectare | 1.2 | 15000 | 18000 | 26666.67 | 32000 | 19.3%
G101 | Clearing and Mulching (HCS 2.1.4) | hectare | 1 | 40000 | 40000 | 18333.33 | 18333.33 | 56%
F492 | Roadway Work (B.F. 74295) (BCS 18.7) | lump sum | 1 | 50000 | 50000 | 33333.33 | 33333.33 | 37.4%
|  | Bridge File Modified Tender Value |  |  | 4607160 |  | 3548479.81 | 14.4%
|  | Total Tender Value |  |  |  |  | 3663429 | 13.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 77 | 115500 | 3.1%
Tender: 18625 ¦ Bridge File: 74295-2 ¦ Tender Opening Date: 2026-01-14
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23958 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2025-2026 | 2026-01-15 | 6 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
2235-1 | 1 km South of Eckville | Central | 766:12 | Lasthill Creek | 4 x 1120 Type-O | 17 ¦ 18 ¦ 17 | 52 | 9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 280000 | 280000 | 298333.33 | 298333.33 | 0.4%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 200000 | 200000 | 153333.33 | 153333.33 | 18.7%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 200000 | 200000 | 214950 | 214950 | 66.8%
F755 | Surface Removal - Concrete Deck Overlay (BCS 20.6.1) | square metre | 430 | 150 | 64500 | 295 | 126850 | 13.2%
F770 | Abrasive Blasting - Deck Surface (BCS 20.6.3) | square metre | 430 | 160 | 68800 | 30.33 | 13041.9 | 18.3%
F760 | Partial Depth Repair - Deck (BCS 20.6.2) | square metre | 86 | 2000 | 172000 | 963.33 | 82846.38 | 19.1%
F760 | Partial Depth Repair - Girder Bearing End and Deck Underside (BCS 20.6.2) | square metre | 10 | 4000 | 40000 | 5456.67 | 54566.7 | 37%
F760 | Partial Depth Repair - Curb (BCS 20.6.2) | square metre | 16 | 2500 | 40000 | 2133.33 | 34133.28 | 21.8%
F760 | Partial Depth Repair - Piers, Abutments, and Diaphragms (BCS 20.6.2) | square metre | 15 | 3000 | 45000 | 3330 | 49950 | 23%
F775 | Deck Overlay Concrete - Supply (BCS 20.6.4) | cubic metre | 22 | 2500 | 55000 | 2653.33 | 58373.26 | 26.7%
F776 | Deck Overlay Concrete - Place (BCS 20.6.4) | square metre | 430 | 400 | 172000 | 225 | 96750 | 35.4%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 10 | 3000 | 30000 | 4346.67 | 43466.7 | 27.6%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1201 | 8.5 | 10208.5 | 19 | 22819 | 30.1%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 87 | 15 | 1305 | 24.33 | 2116.71 | 28.1%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1288 | 3 | 3864 | 5.33 | 6865.04 | 8.8%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 7 | 500 | 3500 | 2296.67 | 16076.69 | 21.7%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 200000 | 200000 | 269000 | 269000 | 24.6%
F020 | Concrete Crack Repair - Gravity-Fed Epoxy (Special Provisions) | metre | 60 | 100 | 6000 | 168.33 | 10099.8 | 18.2%
F020 | Concrete Crack Repair - Pressure Injected Epoxy (Special Provisions) | metre | 70 | 350 | 24500 | 380 | 26600 | 34.6%
F018 | Concrete Modifications - Piers and Abutments including shear blocks and corbels (Special Provisions) | lump sum | 1 | 300000 | 300000 | 262666.67 | 262666.67 | 2.3%
F906 | Bearings - Supply and Fabrication, Delivery and Installation (BCS 8.5) (Special Provisions) | lump sum | 1 | 600000 | 600000 | 576500 | 576500 | 12.6%
F022 | Supply and Apply Type 1c Sealer (Curbs and Deck Overlay) (Special Provisions) | square metre | 501 | 60 | 30060 | 45.67 | 22880.67 | 10.8%
F022 | Supply and Apply Pigment Sealer (Fascia of Curbs and Exterior Girders) (Special Provisions) | square metre | 433 | 80 | 34640 | 110 | 47630 | 26.8%
F018 | Bridgerail Upgrade (Special Provisions) | lump sum | 1 | 45000 | 45000 | 26250 | 26250 | 6.4%
F018 | Approach Rail Transition Upgrading (Special Provisions) | lump sum | 1 | 35000 | 35000 | 27016.67 | 27016.67 | 34%
F752 | Guardrail - Supply and Install (BCS 14.5) (Special Provisions) | lump sum | 1 | 40000 | 40000 | 124333.33 | 124333.33 | 33.1%
F911 | Drain Troughs - Heavy Riprap (BCS 9.7) (Special Provisions) | metre | 30 | 1000 | 30000 | 1160 | 34800 | 4.9%
F018 | Headslope Protection Erosion Repairs (Special Provisions) | lump sum | 1 | 25000 | 25000 | 29166.67 | 29166.67 | 46.3%
F018 | Lasthill Creek Sign - Supply and Install (Special Provisions) | lump sum | 1 | 5000 | 5000 | 1225 | 1225 | 45.7%
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 15000 | 15000 | 25483.33 | 25483.33 | 68.1%
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 75000 | 75000 | 75000 | 75000 | 0%
F018 | Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 60000 | 60000 | 48000 | 48000 | 35.8%
|  | Bridge File Modified Tender Value |  |  | 2911377.5 |  | 2881124.46 | 4.6%
|  | Total Tender Value |  |  |  |  | 3086129.33 | 4.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 90 | 135000 | 137 | 205500 | 3.4%
Tender: 23958 ¦ Bridge File: 2235-1 ¦ Tender Opening Date: 2026-01-15
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
12498 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2025-2026 | 2026-01-21 | 5 | 2026-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
72242-2 | 31 km Northwest of Rocky Mountain House | Central | 11:08 | Chambers Creek | 12 x 510 SLC | 14 ¦ 14 ¦ 14 | 42 | 13.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 600000 | 600000 | 614257.09 | 614257.09 | 10%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 750000 | 750000 | 369468.81 | 369468.81 | 40.5%
F018 | Temporary Access Berms, Cofferdams, Dikes and Channel Diversions (BCS 1.6.2) | lump sum | 1 | 50000 | 50000 | 45505.6 | 45505.6 | 50.3%
E612 | Fish Capture and Release (Special Provisions) | day | 4 | 5000 | 20000 | 2944.28 | 11777.12 | 50.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1500 | 15000 | 2561.04 | 25610.4 | 21.5%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | 172828.29 | 172828.29 | 64.4%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 50000 | 50000 | 40329.62 | 40329.62 | 26.2%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 10000 | 10000 | 33883.81 | 33883.81 | 68.1%
F812 | Supply of Piling - Plain Steel H-Pile (HP 310 x 79) (BCS 3.6.1) | metre | 295 | 350 | 103250 | 172.17 | 50790.15 | 37.1%
F816 | Pile Set-up (Driven Piles) (H-Pile) (BCS 3.6.1) | pile | 20 | 6000 | 120000 | 5536.77 | 110735.4 | 46%
F817 | Test Pile Driving (H-Pile) (BCS 3.6.1) | metre | 30 | 60 | 1800 | 37.6 | 1128 | 122.6%
F818 | Pile Driving (H-Pile) (BCS 3.6.1) | metre | 265 | 60 | 15900 | 32.09 | 8503.85 | 119.4%
F809 | Additional Pile Splicing (H-Pile) (BCS 3.6.1) | splice | 10 | 2000 | 20000 | 1312.7 | 13127 | 26.6%
F814 | Supply of Piling - Plain Steel Pipe Pile (HSS Round 610 x 12.7) (BCS 3.6.1) | metre | 115 | 500 | 57500 | 433.14 | 49811.1 | 40.4%
F815 | Supply of Piling - Galvanized Steel Pipe Pile (HSS Round 610 x 12.7) (BCS 3.6.1) | metre | 100 | 600 | 60000 | 631.15 | 63115 | 30.2%
F816 | Pile Set-up (Driven Piles) (Pipe Pile) (BCS 3.6.1) | pile | 16 | 6000 | 96000 | 7327.28 | 117236.48 | 19.1%
F817 | Test Pile Driving (Pipe Pile) (BCS 3.6.1) | metre | 27 | 250 | 6750 | 64.32 | 1736.64 | 130.4%
F818 | Pile Driving (Pipe Pile) (BCS 3.6.1) (Special Provisions) | metre | 188 | 250 | 47000 | 56.36 | 10595.68 | 128.9%
F809 | Additional Pile Splicing (Pipe Pile) (BCS 3.6.1) | splice | 8 | 2500 | 20000 | 1481.88 | 11855.04 | 16.1%
F820 | PDA Testing (BCS 3.6.4) | test | 8 | 3500 | 28000 | 2026.57 | 16212.56 | 22.9%
F018 | Pier Bracing (Special Provisions) | lump sum | 1 | 50000 | 50000 | 34450.18 | 34450.18 | 13%
F911 | Drain Troughs (BCS 9.7) | metre | 24 | 2500 | 60000 | 1040.17 | 24964.08 | 20.3%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 11700 | 4 | 46800 | 3.7 | 43290 | 31.8%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 24180 | 9 | 217620 | 11.12 | 268881.6 | 21%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 700 | 15 | 10500 | 15.48 | 10836 | 18.4%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 36580 | 3 | 109740 | 2.9 | 106082 | 28.3%
F021 | Concrete (Class Pile) - Supply and Place(BCS 4.27.1) | cubic metre | 90 | 1200 | 108000 | 1128.9 | 101601 | 13.8%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 61 | 3000 | 183000 | 5896.79 | 359704.19 | 20.2%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 130 | 3250 | 422500 | 3349.51 | 435436.3 | 11.9%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 475 | 325 | 154375 | 217.67 | 103393.25 | 12.4%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) | lump sum | 1 | 1100000 | 1100000 | 1017168.34 | 1017168.34 | 8.2%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 15000 | 15000 | 5353.89 | 5353.89 | 45.6%
F974 | Waterproofing (BCS 16.5) | square metre | 750 | 120 | 90000 | 58.93 | 44197.5 | 6%
F981 | Asphalt Concrete Pavement - Mix Type H2 (PG58-28) (Bridge) Mix Type H2 (PG 58-28) (BCS 17.7.1) | lump sum | 1 | 60000 | 60000 | 57676.7 | 57676.7 | 23.5%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 1000000 | 1000000 | 1036627.28 | 1036627.28 | 24.5%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 110000 | 110000 | 66149.71 | 66149.71 | 5.3%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 70000 | 70000 | 76173.85 | 76173.85 | 9.5%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 250 | 20 | 5000 | 15.33 | 3832.5 | 3.1%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 500 | 10 | 5000 | 5.72 | 2860 | 28.9%
|  | Bridge File Modified Tender Value |  |  | 5988735 |  | 5567186.01 | 2.5%
|  | Total Tender Value |  |  |  |  | 5788105.33 | 2.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 147 | 220500 | 13.4%
Tender: 12498 ¦ Bridge File: 72242-2 ¦ Tender Opening Date: 2026-01-21
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
25448 | Bridge High Load Damage Repair | Bridge | Single | Bridge Repair | 2025-2026 | 2026-02-03 | 5 | 2026-09-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75722-1 | 19 km Northwest of Wetaskiwin | Central | Local Road | Highway 2 | 6 x 1020 FC | 15 ¦ 26 ¦ 26 ¦ 15 | 82 | 10.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 50000 | 50000 | 89601.15 | 89601.15 | 37%
F750 | Traffic Accommodation for Bridge Construction (B.F. 75722) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 15000 | 15000 | 29023.18 | 29023.18 | 32.6%
F018 | Demolition and Disposal of Existing Bridge Structures (Special Provisions) | lump sum | 1 | 65000 | 65000 | 27225.87 | 27225.87 | 54.3%
F018 | Concrete Restoration (Special Provisions) | lump sum | 1 | 125000 | 125000 | 38844.7 | 38844.7 | 46.2%
F045 | Stirrup Repairs (Special Provisions) | stirrup | 20 | 700 | 14000 | 111.76 | 2235.2 | 94.6%
F018 | Girder Preloading (Special Provisions) | lump sum | 1 | 20000 | 20000 | 30203.99 | 30203.99 | 58.5%
F044 | Strand Repair, Splicing & Re-Tensioning (Special Provisions) | strand | 4 | 12500 | 50000 | 10895.23 | 43580.92 | 50.6%
F018 | Prestressing Strand Repositioning (Special Provisions) | lump sum | 1 | 25000 | 25000 | 20578.41 | 20578.41 | 83.4%
F020 | Epoxy Crack Injection Repairs (Special Provisions) | metre | 45 | 700 | 31500 | 297.36 | 13381.2 | 37.4%
F018 | Concrete Cleaning and Sealing (Special Provisions) | lump sum | 1 | 7500 | 7500 | 9520.13 | 9520.13 | 42.2%
F018 | Side Slope Restoration (Special Provisions) | lump sum | 1 | 6000 | 6000 | 8097.75 | 8097.75 | 48.6%
|  | Bridge File Modified Tender Value |  |  | 409000 |  | 312292.5 | 16.1%
|  | Total Tender Value |  |  |  |  | 375792.67 | 17.7%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) (Special Provisions) | day | 1500 | 30 | 45000 | 26 | 39000 | 24.9%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 5 | 7500 | 16 | 24000 | 82.7%
Tender: 25448 ¦ Bridge File: 75722-1 ¦ Tender Opening Date: 2026-02-03
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24294 | Construct Welded Steel Girder Bridge | Bridge | Complex | New Bridge | 2025-2026 | 2026-02-10 | 2 | 2028-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
85465N-1 | 35 km North of Fort McMurray | North Central | 63:12 | Haul Road | 5 x 2470 WG | 55 | 55 | 13.5
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 715705.18 | 715705.18 | 1758485.71 | 1758485.71 | -
X018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 8021.9 | 8021.9 | 536119.8 | 536119.8 | -
F190 | PRORATED - Backfill (BCS 2.4) (Special Provisions) | lump sum | 1 | 158025 | 158025 | 192000 | 192000 | -
F824 | Drill Rig Set-up (Drilled Piles) (BCS 3.6.2) | pile | 10 | 30000 | 300000 | 14789.68 | 147896.8 | -
F826 | Pile Installation (Drilled Piles) (BCS 3.6.2) | metre | 255 | 2200 | 561000 | 783.95 | 199907.25 | -
F822 | Pile Concrete (Class) - Supply and Place (BCS 4.27.1) | cubic metre | 170 | 1650 | 280500 | 2201.55 | 374263.5 | -
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 109.5 | 2800 | 306600 | 5755 | 630172.5 | -
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 357 | 3200 | 1142400 | 5310 | 1895670 | -
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 50956 | 3 | 152868 | 3.18 | 162040.08 | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 63462 | 9.5 | 602889 | 9.93 | 630177.66 | -
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 149 | 16 | 2384 | 15.3 | 2279.7 | -
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 114567 | 2.8 | 320787.6 | 2.97 | 340263.99 | -
F903 | PRORATED - Structural Steel - Supply and Fabrication, Delivery and Erection (BCS 6.4.1) | lump sum | 1 | 2332000 | 2332000 | 2795250 | 2795250 | -
F906 | PRORATED - Bearings - Supply and Fabrication, Delivery and Installation (BCS 8.5) | lump sum | 1 | 150000 | 150000 | 132750 | 132750 | -
F781 | PRORATED - Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 136325 | 136325 | 290750 | 290750 | -
F018 | PRORATED - Safety Barrier - Supply and Fabrication, Delivery and Installation (Special Provisions) | lump sum | 1 | 316125 | 316125 | 632250 | 632250 | -
F752 | PROATED - Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 30450 | 30450 | 72250 | 72250 | -
F974 | Waterproofing (BCS 16.5) | square metre | 919.5 | 138 | 126891 | 68.3 | 62801.85 | -
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 170 | 486 | 82620 | 878.31 | 149312.7 | -
F911 | Drain Troughs (BCS 9.7) | metre | 18 | 800 | 14400 | 3160 | 56880 | -
F970 | PRORATED - Miscellaneous Iron (BCS 13.5) (Special Provisions) | lump sum | 1 | 6000 | 6000 | 12650 | 12650 | -
G496 | New Fence - Supply and Install - Class H (HCS 2.12.5) | metre | 112.5 | 175 | 19687.5 | 2503.02 | 281589.75 | -
U018 | PRORATED - Under-bridge Luminaire - Supply and Install (Special Provisions) | lump sum | 1 | 7800 | 7800 | 8525 | 8525 | -
U102 | In-Ground Junction Boxes - Supply and Install (Special Provisions) | unit | 1 | 1220 | 1220 | 5820 | 5820 | -
U102 | Bridge Warning Alarm System - Supply and Install (Special Provisions) | unit | 0.5 | 20000 | 10000 | 41150 | 20575 | -
U100 | Trenching and Backfilling (HCS 2.25.8) | metre | 3 | 40 | 120 | 588 | 1764 | -
U105 | Secondary Cable - Supply and Install - Under-bridge Luminaire (HCS 2.25.8) | metre | 232 | 75 | 17400 | 41.15 | 9546.8 | -
X018 | PRORATED - Instrumentation Plan (Special Provisions) | lump sum | 1 | 3750 | 3750 | 6947.5 | 6947.5 | -
X018 | PRORATED - Non-settling Foundation Pile (Special Provisions) | lump sum | 1 | 5000 | 5000 | 25050 | 25050 | -
X018 | PRORATED - Instrumentation Readout Station - Supply and Install (Special Provisions) | lump sum | 1 | 12500 | 12500 | 16912.5 | 16912.5 | -
X018 | PRORATED - Steel Cabinet - Supply and Install (Special Provisions) | lump sum | 1 | 1000 | 1000 | 3035 | 3035 | -
X027 | Slope Inclinometers - Supply and Install (Special Provisions) | metre | 22.5 | 600 | 13500 | 657.5 | 14793.75 | -
X020 | Trenching and Backfilling of Instrument Leads (Special Provisions) | metre | 125 | 100 | 12500 | 140.5 | 17562.5 | -
X052 | Vibrating Wire Piezometers - Supply and Install (Special Provisions) | unit | 4 | 2100 | 8400 | 6820 | 27280 | -
X052 | Settlement Sensors - Supply and Install (Special Provisions) | unit | 5 | 11000 | 55000 | 7960 | 39800 | -
|  | Bridge File Modified Tender Value |  |  | 7913869.18 |  | 11553373.34 | -
|  | Total Tender Value |  |  |  |  | 110003396.89 | -
Tender: 24294 ¦ Bridge File: 85465-1 ¦ Tender Opening Date: 2026-02-10
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24294 | Construct Welded Steel Girder Bridge | Bridge | Complex | New Bridge | 2025-2026 | 2026-02-10 | 2 | 2028-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
85467S-2 | 35 km North of Fort McMurray | North Central | 63:12 | Haul Road | 5 x 2470 WG | 55 | 55 | 13.5
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 706289.69 | 706289.69 | 1739417.43 | 1739417.43 | -
X018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 7916.37 | 7916.37 | 530457.03 | 530457.03 | -
F190 | PRORATED - Backfill (BCS 2.4) (Special Provisions) | lump sum | 1 | 158025 | 158025 | 192000 | 192000 | -
F824 | Drill Rig Set-up (Drilled Piles) (BCS 3.6.2) | pile | 10 | 30000 | 300000 | 14789.68 | 147896.8 | -
F826 | Pile Installation (Drilled Piles) (BCS 3.6.2) | metre | 255 | 2200 | 561000 | 783.95 | 199907.25 | -
F822 | Pile Concrete (Class) - Supply and Place (BCS 4.27.1) | cubic metre | 170 | 1650 | 280500 | 2201.55 | 374263.5 | -
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 109.5 | 2800 | 306600 | 5755 | 630172.5 | -
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 357 | 3200 | 1142400 | 5310 | 1895670 | -
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 51299 | 3 | 153897 | 3.18 | 163130.82 | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 55610 | 9.5 | 528295 | 9.93 | 552207.3 | -
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 149 | 16 | 2384 | 15.3 | 2279.7 | -
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 107058 | 2.8 | 299762.4 | 2.97 | 317962.26 | -
F903 | PRORATED - Structural Steel - Supply and Fabrication, Delivery and Erection (BCS 6.4.1) | lump sum | 1 | 2332000 | 2332000 | 2795250 | 2795250 | -
F906 | PRORATED - Bearings - Supply and Fabrication, Delivery and Installation (BCS 8.5) | lump sum | 1 | 150000 | 150000 | 132750 | 132750 | -
F781 | PRORATED - Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 136325 | 136325 | 290750 | 290750 | -
F018 | PRORATED - Safety Barrier - Supply and Fabrication, Delivery and Installation (Special Provisions) | lump sum | 1 | 316125 | 316125 | 632250 | 632250 | -
F752 | PROATED - Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 30450 | 30450 | 72250 | 72250 | -
F974 | Waterproofing (BCS 16.5) | square metre | 919.5 | 138 | 126891 | 68.3 | 62801.85 | -
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 170 | 486 | 82620 | 878.31 | 149312.7 | -
F911 | Drain Troughs (BCS 9.7) | metre | 18 | 800 | 14400 | 3160 | 56880 | -
F970 | PRORATED - Miscellaneous Iron (BCS 13.5) (Special Provisions) | lump sum | 1 | 6000 | 6000 | 12650 | 12650 | -
G496 | New Fence - Supply and Install - Class H (HCS 2.12.5) | metre | 112.5 | 175 | 19687.5 | 2503.02 | 281589.75 | -
U018 | PRORATED - Under-bridge Luminaire - Supply and Install (Special Provisions) | lump sum | 1 | 7800 | 7800 | 8525 | 8525 | -
U102 | In-Ground Junction Boxes - Supply and Install (Special Provisions) | unit | 1 | 1220 | 1220 | 5820 | 5820 | -
U102 | Bridge Warning Alarm System - Supply and Install (Special Provisions) | unit | 0.5 | 20000 | 10000 | 41150 | 20575 | -
U100 | Trenching and Backfilling (HCS 2.25.8) | metre | 3 | 40 | 120 | 588 | 1764 | -
U105 | Secondary Cable - Supply and Install - Under-bridge Luminaire (HCS 2.25.8) | metre | 232 | 75 | 17400 | 41.15 | 9546.8 | -
X018 | PRORATED - Instrumentation Plan (Special Provisions) | lump sum | 1 | 3750 | 3750 | 6947.5 | 6947.5 | -
X018 | PRORATED - Non-settling Foundation Pile (Special Provisions) | lump sum | 1 | 5000 | 5000 | 25050 | 25050 | -
X018 | PRORATED - Instrumentation Readout Station - Supply and Install (Special Provisions) | lump sum | 1 | 12500 | 12500 | 16912.5 | 16912.5 | -
X018 | PRORATED - Steel Cabinet - Supply and Install (Special Provisions) | lump sum | 1 | 1000 | 1000 | 3035 | 3035 | -
X027 | Slope Inclinometers - Supply and Install (Special Provisions) | metre | 22.5 | 600 | 13500 | 657.5 | 14793.75 | -
X020 | Trenching and Backfilling of Instrument Leads (Special Provisions) | metre | 125 | 100 | 12500 | 140.5 | 17562.5 | -
X052 | Vibrating Wire Piezometers - Supply and Install (Special Provisions) | unit | 4 | 2100 | 8400 | 6820 | 27280 | -
X052 | Settlement Sensors - Supply and Install (Special Provisions) | unit | 5 | 11000 | 55000 | 7960 | 39800 | -
|  | Bridge File Modified Tender Value |  |  | 7809757.96 |  | 11429460.94 | -
|  | Total Tender Value |  |  |  |  | 110003396.89 | -
Tender: 24294 ¦ Bridge File: 85467-2 ¦ Tender Opening Date: 2026-02-10
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24468 | Bridge Rehabilitation | Bridge | Complex | Bridge Rehabilitation | 2025-2026 | 2026-02-12 | 2 | 2027-09-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75946E-1 | At Peace River | Peace | 2:62 | Peace River | Steel Arch | 20 ¦ 29 ¦ 29 ¦ 124 ¦ 125 ¦ 125 ¦ 92 ¦ 29 | 573 | 11.3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 2227632.23 | 2227632.23 | 4722253.43 | 4722253.43 | -
F750 | PRORATED - Traffic Accommodation for Bridge Construction (B.F. 75946E) (B.F. 76060E) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 425299.55 | 425299.55 | 671746.6 | 671746.6 | -
S038 | Construction Advisory Signs - Supply and Install (Special Provisions) | sign | 2 | 1800 | 3600 | 5105.47 | 10210.94 | -
X038 | Project Identification Signs - Supply and Install (Special Provisions) | sign | 2 | 2400 | 4800 | 9282.68 | 18565.36 | -
E018 | PRORATED - Environmental Management (Special Provisions) | lump sum | 1 | 534631.74 | 534631.74 | 408839.85 | 408839.85 | -
X002 | PRORATED - Extra Work - Contingency Allowance (Special Provisions) | Total Force Account | 1 | 445526.45 | 445526.45 | 437942.26 | 437942.26 | -
F018 | Arch Span - Super Structure and Floor System Access (Special Provisions) | lump sum | 1 | 2916000 | 2916000 | 4823696.09 | 4823696.09 | -
F018 | Arch Span - Arch Tie - Interior Access | lump sum | 1 | 776528 | 776528 | 3693339.91 | 3693339.91 | -
F018 | Headslope Grading Repairs (Special Provisions) | lump sum | 1 | 10000 | 10000 | 51783.05 | 51783.05 | -
F760 | Partial Depth Repair - Deck Underside (BCS 20.6.2) (Special Provisions) | square metre | 5 | 5000 | 25000 | 8852.78 | 44263.9 | -
F018 | Concrete Sealer - Barriers and Bridgerail Post Grout Pads (Special Provisions) | lump sum | 1 | 25000 | 25000 | 58361.02 | 58361.02 | -
F018 | Concrete Sealer - Bearing Grout Pads (Special Provisions) | lump sum | 1 | 7200 | 7200 | 19012.46 | 19012.46 | -
F018 | Bearing Grout Pad Repairs at Abutments 1 and 2 (Special Provisions) | lump sum | 1 | 10800 | 10800 | 50724.55 | 50724.55 | -
F018 | Pier 1 Bridge Jacking (Special Provisions) | lump sum | 1 | 8500 | 8500 | 96913.01 | 96913.01 | -
F018 | Pier 2 Bridge Jacking (Special Provisions) | lump sum | 1 | 8500 | 8500 | 96913.01 | 96913.01 | -
F018 | Pier 1 and Pier 2 Bearing Anchor Bolt Repairs (Special Provisions) | lump sum | 1 | 20200 | 20200 | 17680.39 | 17680.39 | -
F018 | Pier 3 and Pier 7 Rocker Bent Repairs (Special Provisions) | lump sum | 1 | 28700 | 28700 | 188479.23 | 188479.23 | -
F018 | East Approach Spans - Bottom Flange Repairs at Pier 1 and Pier 2 Bearing Sole Plates (Special Provisions) | lump sum | 1 | 153144 | 153144 | 247069.82 | 247069.82 | -
F018 | East Approach Spans - Girder Field Splice Repair (Special Provisions) | lump sum | 1 | 25000 | 25000 | 129243.41 | 129243.41 | -
F018 | Arch Spans - End Floor Beam Repairs (Special Provisions) | lump sum | 1 | 9000 | 9000 | 142188.4 | 142188.4 | -
F018 | Arch Spans - Arch Tie Corrosion Repairs - Cleaning (Special Provisions) | lump sum | 1 | 203680 | 203680 | 358572.62 | 358572.62 | -
F018 | Arch Spans - Lead Based Paint - Protection of Workers and the Environment (Special Provisions) | lump sum | 1 | 21600 | 21600 | 35515.56 | 35515.56 | -
F151 | Protection of the Environment - Arch Tie Interior Coating (B.F. 75946E) (BCS 22.25.1) (Special Provisions) | lump sum | 1 | 112000 | 112000 | 55115.56 | 55115.56 | -
F022 | Surface Preparation and Coating - Arch Tie Interior (Special Provisions) | square metre | 43.2 | 900 | 38880 | 3650.32 | 157693.82 | -
F053 | Arch Spans - Arch Tie Corrosion Repairs at Bearing Diaphragms (Special Provisions) | unit | 5 | 19560 | 97800 | 100645.69 | 503228.45 | -
F020 | Arch Spans - Arch Tie Corrosion Repairs at Hanger and Intermediate Diaphragms with Plates Thinner than or Equal to 16 mm (Special Provisions) | metre | 50 | 4020 | 201000 | 7808.56 | 390428 | -
F020 | Arch Spans - Arch Tie Corrosion Repairs at Hanger and Intermediate Diaphragms Plates Thicker than 16 mm (Special Provisions) | metre | 60 | 4432 | 265920 | 15327.62 | 919657.2 | -
F053 | Arch Spans - Arch Tie Access Hatch Repairs - Hatch - Supply, Fabrication and Delivery (Special Provisions) | unit | 12 | 5700 | 68400 | 2793.3 | 33519.6 | -
F053 | Arch Spans - Arch Tie Access Hatch Repairs - Framing Angles - Supply, Fabrication and Delivery (Special Provisions) | unit | 16 | 2000 | 32000 | 4281.31 | 68500.96 | -
F053 | Arch Spans - Arch Tie Access Hatch Repairs - Hatch - Installation (Special Provisions) | unit | 16 | 2400 | 38400 | 19784.95 | 316559.2 | -
F053 | Arch Spans - Arch Tie Access Hatch Repairs - Framing Angles - Installation (Special Provisions) | unit | 16 | 6400 | 102400 | 16024.43 | 256390.88 | -
F018 | Arch Spans Stringer to Floor Beam Joints High Strength Bolt Replacement (Special Provisions) | lump sum | 1 | 12300 | 12300 | 517160.21 | 517160.21 | -
F053 | Arch Spans Stringer to Floor Beam Joints - Plate Washer Replacement (Special Provisions) | unit | 14 | 220 | 3080 | 641.52 | 8981.28 | -
F019 | Stringer to Floor Beam Joint - Repair Type 1 (Special Provisions) | location | 82 | 650 | 53300 | 1559.65 | 127891.3 | -
F019 | Stringer to Floor Beam Joint - Repair Type 2 (Special Provisions) | location | 34 | 2350 | 79900 | 3707.54 | 126056.36 | -
F019 | Stringer to Floor Beam Joint - Repair Type 3 (Special Provisions) | location | 83 | 1025 | 85075 | 2378.9 | 197448.7 | -
F019 | Stringer to Floor Beam Joint - Repair Type 4 (Special Provisions) | location | 2 | 10500 | 21000 | 6549.11 | 13098.22 | -
F019 | Stringer to Floor Beam Joint - Repair Type 5 (Special Provisions) | location | 66 | 720 | 47520 | 2831.77 | 186896.82 | -
F019 | Stringer to Floor Beam Joint - Repair Type 6 (Special Provisions) | location | 19 | 5000 | 95000 | 2737.46 | 52011.74 | -
F019 | Stringer to Floor Beam Joint - Repair Type 7 (Special Provisions) | location | 1 | 255 | 255 | 7761.46 | 7761.46 | -
F019 | Stringer to Floor Beam Joint - Repair Type 8 (Special Provisions) | location | 4 | 3500 | 14000 | 3264.92 | 13059.68 | -
F018 | Arch Span Hangers - Survey (Special Provisions) | lump sum | 1 | 359200 | 359200 | 862051.69 | 862051.69 | -
F018 | Arch Span Hangers - Supply - New Material (Special Provisions) | lump sum | 1 | 844012.51 | 844012.51 | 428725.74 | 428725.74 | -
F018 | Arch Span Hangers - Supply - Fabrication (Special Provisions) | lump sum | 1 | 1969362.53 | 1969362.53 | 2725072.1 | 2725072.1 | -
F018 | Arch Span Hangers - Delivery (Special Provisions) | lump sum | 1 | 400000 | 400000 | 305491.79 | 305491.79 | -
F053 | Arch Span Hangers - Erection (Special Provisions) | unit | 90 | 25916.67 | 2332500.3 | 129264.84 | 11633835.6 | -
F151 | Protection of the Environment - Span 6 Repainting (B.F. 75946E) (BCS 22.25.1) (Special Provisions) | lump sum | 1 | 801992 | 801992 | 394971.29 | 394971.29 | -
F150 | Surface Preparation and Painting - Span 6 Repainting (B.F. 75946E) (BCS 22.25.2) (Special Provisions) | lump sum | 1 | 3313944 | 3313944 | 2814558.52 | 2814558.52 | -
F151 | Protection of the Environment - Rocker Bent and Girder Ends (B.F. 75946E) (BCS 22.25.1) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 49950.56 | 49950.56 | -
F053 | Surface Preparation and Painting - Rocker Bent and Girder Ends (Special Provisions) | unit | 50 | 2500 | 125000 | 963.61 | 48180.5 | -
F151 | Protection of the Environment - Arch Span Repairs <0.5m2 (B.F. 75946E) (BCS 22.25.1) (Special Provisions) | lump sum | 1 | 40000 | 40000 | 111851.68 | 111851.68 | -
F053 | Surface Preparation and Painting - Arch Span Repairs <0.5m2 (Special Provisions) | unit | 400 | 300 | 120000 | 940.04 | 376016 | -
F018 | Demolition and Disposal of Existing Finger Joints (Special Provisions) | lump sum | 1 | 137000 | 137000 | 441470.46 | 441470.46 | -
F841 | Concrete (Class HPC) - Supply and Place (B.F. 75946E) (BCS 4.27.1) | cubic metre | 32.78 | 4000 | 131120 | 18155.29 | 595130.41 | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 75946E) (BCS 5.6) | kilogram | 2473 | 7.69 | 19017.37 | 12.94 | 32000.62 | -
F853 | Stainless Reinforcing Steel - Supply (B.F. 75946E) (BCS 5.6) | kilogram | 5149 | 15.74 | 81045.26 | 18.32 | 94329.68 | -
F854 | Reinforcing Steel - Place (B.F. 75946E) (BCS 5.6) | kilogram | 7622 | 2.94 | 22408.68 | 3.41 | 25991.02 | -
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation - Type 1 Strip Seal (B.F. 75946E) (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 413323.3 | 413323.3 | -
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation - Finger Plate (B.F. 75946E) (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 835700 | 835700 | 2731331.54 | 2731331.54 | -
F018 | ACP Removal (B.F. 75946E) - Full Scale Demonstration (Special Provisions) | lump sum | 1 | 17500 | 17500 | 46504.37 | 46504.37 | -
F022 | Deck Surface Preparation for Waterproofing - New Concrete (Special Provisions) | square metre | 37.4 | 30 | 1122 | 561.04 | 20982.9 | -
F022 | Deck Surface Preparation for Waterproofing - Repair Area (Special Provisions) | square metre | 600 | 30 | 18000 | 54.91 | 32946 | -
F022 | Deck Waterproofing System - New and Repair (Special Provisions) | square metre | 637.4 | 300 | 191220 | 150.02 | 95622.75 | -
F022 | ACP Removal (B.F. 75946E) (Special Provisions) | square metre | 6350.51 | 12.5 | 79381.38 | 56.19 | 356835.16 | -
F022 | Deck Surface Preparation for Waterproofing - Replacement (Special Provisions) | square metre | 5936.11 | 20 | 118722.2 | 13.18 | 78237.93 | -
F022 | Deck Waterproofing System - Replacement - Micro-Milling (Special Provisions) | square metre | 5936.11 | 30 | 178083.3 | 44.53 | 264334.98 | -
F022 | Deck Waterproofing System - Replacement (Special Provisions) | square metre | 5936.11 | 240 | 1424666.4 | 103.73 | 615752.69 | -
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) (B.F. 75946E) Mix Type H2 (PG 58-28) (BCS 17.7.2) (Special Provisions) | tonne | 760.8 | 200 | 152160 | 354.42 | 269642.74 | -
F018 | SS-1 Liquid Asphalt Sealer (B.F. 75946E) (Special Provisions) | lump sum | 1 | 6876 | 6876 | 2838.33 | 2838.33 | -
F018 | PVC Deck Drains at Strip Seal Joints (Special Provisions) | lump sum | 1 | 11200 | 11200 | 39088.1 | 39088.1 | -
F018 | Barrier Cover Plate Repairs (Special Provisions) | lump sum | 1 | 2000 | 2000 | 13535.66 | 13535.66 | -
F018 | Thrie Beam to Bridge Barrier Repairs (Special Provisions) | lump sum | 1 | 2000 | 2000 | 4362.86 | 4362.86 | -
F018 | Bridgerail Reflector Installation (B.F. 75946E) (Special Provisions) | lump sum | 1 | 2000 | 2000 | 6476.36 | 6476.36 | -
F018 | Bridgerail and Guardrail Galvanizing Repairs (B.F. 75946E) (Special Provisions) | lump sum | 1 | 2500 | 2500 | 19697.62 | 19697.62 | -
|  | Bridge File Modified Tender Value |  |  | 23098305.9 |  | 46225915.26 | -
|  | Total Tender Value |  |  |  |  | 53620071.38 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | PRORATED - Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 404 | 606000 | -
F003 | Lane Closure for Bridge Construction - 94th Street (GCS 1.2.42.5) (Special Provisions) | day | 4000 | - | - | 20 | 80000 | -
F003 | Lane Closure for Bridge Construction - 90th Street (GCS 1.2.42.5) (Special Provisions) | day | 4000 | - | - | 12 | 48000 | -
Tender: 24468 ¦ Bridge File: 75946-1 ¦ Tender Opening Date: 2026-02-12
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24468 | Bridge Rehabilitation | Bridge | Complex | Bridge Rehabilitation | 2025-2026 | 2026-02-12 | 2 | 2027-09-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76060E-1 | At Peace River | Peace | 2:62 | CNR Railway | 13 x 1370 FM | 38 | 38 | 21.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 80688.17 | 80688.17 | 296785.41 | 296785.41 | -
F750 | PRORATED - Traffic Accommodation for Bridge Construction (B.F. 75946E) (B.F. 76060E) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 15404.99 | 15404.99 | 37546.85 | 37546.85 | -
E018 | PRORATED - Environmental Management (Special Provisions) | lump sum | 1 | 19365.16 | 19365.16 | 24236.81 | 24236.81 | -
X002 | PRORATED - Extra Work - Contingency Allowance (Special Provisions) | Total Force Account | 1 | 16137.63 | 16137.63 | 29493.62 | 29493.62 | -
X018 | Railway Flag Person (Special Provisions) | lump sum | 1 | 60000 | 60000 | 195030.96 | 195030.96 | -
F053 | Shear Block Replacement - Abutment 1 (Special Provisions) | unit | 5 | 17100 | 85500 | 98669.74 | 493348.7 | -
F053 | Shear Block Replacement - Abutment 2 (Special Provisions) | unit | 3 | 12200 | 36600 | 87218.17 | 261654.51 | -
F053 | Shear Block Rebar Dowels (Special Provisions) | unit | 112 | 275 | 30800 | 275.96 | 30907.52 | -
F053 | Bridgerail Anchorage Replacement - Abutment (Special Provisions) | unit | 2 | 27700 | 55400 | 24061.03 | 48122.06 | -
F053 | Bridgerail Anchorage Replacement - Diaphragm (Special Provisions) | unit | 11 | 8400 | 92400 | 8000.43 | 88004.73 | -
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (B.F. 76060E) (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 209300 | 209300 | 900950.72 | 900950.72 | -
F022 | ACP Removal (B.F. 76060E) (Special Provisions) | square metre | 1838.96 | 25 | 45974 | 21.23 | 39041.12 | -
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) (B.F. 76060E) Mix Type H2 (PG 58-28) (BCS 17.7.2) (Special Provisions) | tonne | 220.3 | 200 | 44060 | 341.21 | 75168.56 | -
F018 | SS-1 Liquid Asphalt (B.F. 76060E) (Special Provisions) | lump sum | 1 | 225.24 | 225.24 | 2968.04 | 2968.04 | -
F018 | Bridgerail Rail Sections and Fastener Hardware Replacement (Special Provisions) | lump sum | 1 | 20000 | 20000 | 23582.42 | 23582.42 | -
F018 | Bridgerail Reflector Installation (B.F. 76060E) (Special Provisions) | lump sum | 1 | 2000 | 2000 | 562.69 | 562.69 | -
F018 | Bridgerail, Handrail and Guardrail Galvanizing Repairs (B.F. 76060E) (Special Provisions) | lump sum | 1 | 2500 | 2500 | 13082.62 | 13082.62 | -
F018 | Drain Trough Repairs (Special Provisions) | lump sum | 1 | 12000 | 12000 | 7726.46 | 7726.46 | -
F018 | Northwest Drain Trough Removal (Special Provisions) | lump sum | 1 | 8300 | 8300 | 20325.26 | 20325.26 | -
|  | Bridge File Modified Tender Value |  |  | 836655.19 |  | 2588539.06 | -
|  | Total Tender Value |  |  |  |  | 53620071.38 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | PRORATED - Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 27 | 40500 | -
Tender: 24468 ¦ Bridge File: 76060-1 ¦ Tender Opening Date: 2026-02-12
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
19893 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2025-2026 | 2026-02-24 | 4 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
9309-1 | 7 km North of Sangudo | North Central | 757:04 | Paddle River | 5 x 800 WG | 16 ¦ 19 ¦ 16 | 51 | 10.5
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 186900 | 186900 | 273333.33 | 273333.33 | 19.5%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 100000 | 100000 | 86024.47 | 86024.47 | 68.1%
E018 | Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 10000 | 10000 | 26904 | 26904 | 62.4%
Q554 | Cold Milling Asphalt Pavement - 60 <mm Depth> (HCS 3.16.6) (Special Provisions) | square metre | 767 | 50 | 38350 | 28 | 21476 | 30.3%
F755 | Surface Removal (BCS 20.6.1) | square metre | 523 | 140 | 73220 | 79.73 | 41698.79 | 34.1%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 40000 | 40000 | 145843 | 145843 | 59.8%
F760 | Partial Depth Repair - Deck (BCS 20.6.2) | square metre | 70 | 1000 | 70000 | 1239.03 | 86732.1 | 42.2%
F760 | Partial Depth Repair - Curbs (BCS 20.6.2) | square metre | 10 | 2500 | 25000 | 4530 | 45300 | 71%
F760 | Partial Depth Repair - Deck Soffit (BCS 20.6.2) | square metre | 5 | 3500 | 17500 | 3887.67 | 19438.35 | 20.4%
F760 | Partial Depth Repair - Abutments (BCS 20.6.2) | square metre | 5 | 2300 | 11500 | 3378.33 | 16891.65 | 18.4%
F765 | Full Depth Repair - Deck (BCS 20.6.2) | square metre | 5 | 5500 | 27500 | 3415 | 17075 | 19%
F765 | Full Depth Repair - Abutments (BCS 20.6.2) | square metre | 5 | 3500 | 17500 | 3673.33 | 18366.65 | 27.3%
F020 | Concrete Crack Repair - Abutments (Special Provisions) | metre | 10 | 500 | 5000 | 1207 | 12070 | 57.5%
F018 | Deck and Abutment End Modification (Special Provisions) | lump sum | 1 | 60000 | 60000 | 108960 | 108960 | 39.6%
F993 | Galvanic Corrosion Protection - Supply and Install (Special Provisions) | anodes | 800 | 125 | 100000 | 47.88 | 38304 | 14.3%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (BCS 6.4.2) | lump sum | 1 | 111000 | 111000 | 205283.33 | 205283.33 | 42.4%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 7500 | 7500 | 13172 | 13172 | 42.9%
F974 | Waterproofing (BCS 16.5) | square metre | 456 | 140 | 63840 | 92.33 | 42102.48 | 12%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 280 | 450 | 126000 | 376.67 | 105467.6 | 16%
F018 | Concrete Cleaning and Sealing (Special Provisions) | lump sum | 1 | 20000 | 20000 | 44431 | 44431 | 68.3%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (Approach Rail Transitions) (BCS 12.4) | lump sum | 1 | 100000 | 100000 | 66660.67 | 66660.67 | 16.5%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 15000 | 15000 | 27471.67 | 27471.67 | 38.2%
F053 | End Treatment Type 1 - Supply and Install (Special Provisions) | unit | 2 | 6000 | 12000 | 9781.67 | 19563.34 | 8.1%
F018 | End Treatment Type 2 - Supply and Install (Special Provisions) | lump sum | 1 | 10000 | 10000 | 25831.67 | 25831.67 | 50.8%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 100000 | 100000 | 77873.33 | 77873.33 | 54.5%
B180 | Preparing Subgrade Surface (First Layer) (HCS 3.1.3) | square metre | 4300 | 5 | 21500 | 11.32 | 48676 | 48.8%
B152 | Granular Fill Des. 6 Class 80 (HCS 3.8.5) (Special Provisions) | tonne | 6780 | 40 | 271200 | 45.05 | 305439 | 26.7%
B153 | Granular Fill Des. 2 Class 25 (HCS 3.8.5) (Special Provisions) | tonne | 320 | 60 | 19200 | 61.43 | 19657.6 | 35.2%
B283 | Granular Base Course Des. 2 Class 40 (HCS 3.6.8) (Special Provisions) | tonne | 780 | 70 | 54600 | 56.33 | 43937.4 | 29.6%
Q185 | Gravel Surfacing Des. 4 Class 20 (HCS 3.3.4) (Special Provisions) | tonne | 340 | 70 | 23800 | 83.42 | 28362.8 | 26.3%
F018 | Headslope Repair (Special Provisions) | lump sum | 1 | 120000 | 120000 | 212505.67 | 212505.67 | 17.3%
F492 | Roadway Work (Special Provisions) | lump sum | 1 | 175000 | 175000 | 281096.67 | 281096.67 | 44%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 1500 | 10 | 15000 | 8.22 | 12330 | 52.8%
E020 | Erosion Control Barrier (Fibre Rolls) (Special Provisions) | metre | 500 | 15 | 7500 | 21.67 | 10835 | 23%
|  | Bridge File Modified Tender Value |  |  | 2055610 |  | 2549114.57 | 11.4%
|  | Total Tender Value |  |  |  |  | 2914101.33 | 13.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 120 | 180000 | 34%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | - | - | 123 | 184500 | 29.9%
Tender: 19893 ¦ Bridge File: 9309-1 ¦ Tender Opening Date: 2026-02-24
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24814 | Bridge Rehabilitation | Bridge | Multiple | Bridge Rehabilitation | 2025-2026 | 2026-02-25 | 3 | 2027-05-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
78895N-1 | At Calgary | Southern | 2:15 | Ogden Road ¦ CPR & CNR Railway | 3 x 1820 Welded Box Girder | 48 ¦ 54 ¦ 54 ¦ 54 ¦ 40 | 250 | 15.3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 539238.62 | 539238.62 | 569465.12 | 569465.12 | 16.4%
F750 | PRORATED - Traffic Accommodation for Bridge Construction (B.F. 78895) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 885538.65 | 885538.65 | 576530.74 | 576530.74 | 8.9%
X101 | PRORATED - Project Identification Sign - Supply and Install (Special Provisions) | sign | 5 | 1978.86 | 9894.3 | 7088.96 | 35444.8 | 85.9%
S241 | PRORATED - Construction Advisory Sign (Special Provisions) | sign | 4 | 29682.86 | 118731.44 | 14334.68 | 57338.72 | 29.1%
F018 | PRORATED - Temporary Access Equipment and Structures (Special Provisions) | lump sum | 1 | 281987.17 | 281987.17 | 821909.43 | 821909.43 | 114.3%
F018 | PRORATED - Curtain Wall Access (Special Provisions) | lump sum | 1 | 64312.86 | 64312.86 | 112057.27 | 112057.27 | 44.9%
F018 | PRORATED - Confined Space Management (Special Provisions) | lump sum | 1 | 183044.3 | 183044.3 | 248678.22 | 248678.22 | 44.4%
E018 | PRORATED - Bird Feces Cleanup (Special Provisions) | lump sum | 1 | 44524.29 | 44524.29 | 71955.93 | 71955.93 | 96.8%
F018 | PRORATED - Construction Debris Cleanup (Special Provisions) | lump sum | 1 | 84101.44 | 84101.44 | 234805.24 | 234805.24 | 47.6%
F019 | NB Bridge - Repair of Girder Web Cracks (Special Provisions) | location | 130 | 1300 | 169000 | 2565.44 | 333507.2 | 19.8%
F019 | NB Bridge - D1 - Stiffener to Bottom Flange (Special Provisions) | location | 198 | 4900 | 970200 | 2614.63 | 517696.74 | 56.4%
F019 | NB Bridge - D2 - Stiffener to Top Flange (Special Provisions) | location | 48 | 10000 | 480000 | 3708.25 | 177996 | 39.2%
|  | Bridge File Modified Tender Value |  |  | 3830573.07 |  | 3757385.41 | 33.2%
|  | Total Tender Value |  |  |  |  | 8719207.33 | 27.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | PRORATED - Site Occupancy (GCS 1.2.41.9) | day | 3000 | 64 | 192000 | 80 | 240000 | 19.1%
X055 | PRORATED - Misc. Occupancy - Lane Rental - CN Flagsperson (Special Provisions) | day | 1700 | 8 | 13600 | 10 | 17000 | 34%
X055 | PRORATED - Misc. Occupancy - Lane Rental - CPKC Flagsperson Single Shift (Special Provisions) | day | 1700 | 8 | 13600 | 18 | 30600 | 77.2%
X055 | PRORATED - Misc. Occupancy - Lane Rental - Optional CPKC Flagsperson Double Shift (Special Provisions) | day | 3400 | 8 | 27200 | 1 | 3400 | 94.3%
X055 | PRORATED - Misc. Occupancy - Lane Rental - CPKC Track Block (Special Provisions) | day | 5000 | 8 | 40000 | 3 | 15000 | 134.3%
X055 | PRORATED - Misc. Occupancy - Lane Rental - Western headworks Canal (Special Provisions) | day | 1000 | 13 | 13000 | 4 | 4000 | 73.6%
F003 | Lane Closure for Bridge Construction - Ogden Road Single NBL (GCS 1.2.42.5) (Special Provisions) | day | 1000 | 15 | 15000 | 47 | 47000 | 94.5%
F003 | Lane Closure for Bridge Construction - Hwy 2 Single NBL (GCS 1.2.42.5) (Special Provisions) | day | 3000 | 34 | 102000 | 18 | 54000 | 34.6%
F003 | Lane Closure for Bridge Construction - Hwy 2 Two NBL (GCS 1.2.42.5) (Special Provisions) | day | 7500 | 16 | 120000 | 13 | 97500 | 92.6%
F003 | Lane Closure for Bridge Construction - Hwy 2 All NBL (GCS 1.2.42.5) (Special Provisions) | day | 15000 | 8 | 120000 | 5 | 75000 | 49%
Tender: 24814 ¦ Bridge File: 78895-1 ¦ Tender Opening Date: 2026-02-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24814 | Bridge Rehabilitation | Bridge | Multiple | Bridge Rehabilitation | 2025-2026 | 2026-02-25 | 3 | 2027-05-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
78895S-2 | At Calgary | Southern | 2:15 | Ogden Road ¦ CPR & CNR Railway | 3 x 1820 Welded Box Girder | 48 ¦ 50 ¦ 54 ¦ 54 ¦ 40 | 246 | 15.3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 550761.38 | 550761.38 | 578844.85 | 578844.85 | 17%
F750 | PRORATED - Traffic Accommodation for Bridge Construction (B.F. 78895) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 904461.35 | 904461.35 | 585708.74 | 585708.74 | 9.4%
X101 | PRORATED - Project Identification Sign - Supply and Install (Special Provisions) | sign | 5 | 2021.14 | 10105.7 | 7247.06 | 36235.3 | 86.6%
S241 | PRORATED - Construction Advisory Sign (Special Provisions) | sign | 4 | 30317.14 | 121268.56 | 14523.82 | 58095.28 | 28.6%
F018 | PRORATED - Temporary Access Equipment and Structures (Special Provisions) | lump sum | 1 | 288012.83 | 288012.83 | 830659.88 | 830659.88 | 114.3%
F018 | PRORATED - Curtain Wall Access (Special Provisions) | lump sum | 1 | 65687.14 | 65687.14 | 113711.42 | 113711.42 | 44.6%
F018 | PRORATED - Confined Space Management (Special Provisions) | lump sum | 1 | 186955.7 | 186955.7 | 252044.88 | 252044.88 | 44%
E018 | PRORATED - Bird Feces Cleanup (Special Provisions) | lump sum | 1 | 45475.71 | 45475.71 | 72818.42 | 72818.42 | 96.5%
F018 | PRORATED - Construction Debris Cleanup (Special Provisions) | lump sum | 1 | 85898.56 | 85898.56 | 237603.27 | 237603.27 | 47.3%
F019 | SB Bridge - Repair of Girder Web Cracks (Special Provisions) | location | 134 | 1300 | 174200 | 2516.21 | 337172.14 | 19%
F019 | SB Bridge - D1 - Stiffener to Bottom Flange (Special Provisions) | location | 204 | 4900 | 999600 | 2607.83 | 531997.32 | 56.7%
F019 | SB Bridge - D2 - Stiffener to Top Flange (Special Provisions) | location | 48 | 10000 | 480000 | 3708.25 | 177996 | 39.2%
|  | Bridge File Modified Tender Value |  |  | 3912426.93 |  | 3812887.5 | 32.9%
|  | Total Tender Value |  |  |  |  | 8719207.33 | 27.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | PRORATED - Site Occupancy (GCS 1.2.41.9) | day | 3000 | 66 | 198000 | 81 | 243000 | 17.8%
X055 | PRORATED - Misc. Occupancy - Lane Rental - CN Flagsperson (Special Provisions) | day | 1700 | 8 | 13600 | 10 | 17000 | 34%
X055 | PRORATED - Misc. Occupancy - Lane Rental - CPKC Flagsperson Single Shift (Special Provisions) | day | 1700 | 8 | 13600 | 18 | 30600 | 77.2%
X055 | PRORATED - Misc. Occupancy - Lane Rental - Optional CPKC Flagsperson Double Shift (Special Provisions) | day | 3400 | 8 | 27200 | 2 | 6800 | 70.7%
X055 | PRORATED - Misc. Occupancy - Lane Rental - CPKC Track Block (Special Provisions) | day | 5000 | 8 | 40000 | 3 | 15000 | 134.3%
X055 | PRORATED - Misc. Occupancy - Lane Rental - Western headworks Canal (Special Provisions) | day | 1000 | 13 | 13000 | 4 | 4000 | 73.6%
F003 | Lane Closure for Bridge Construction - Ogden Road Single SBL (GCS 1.2.42.5) (Special Provisions) | day | 1000 | 15 | 15000 | 14 | 14000 | 30.9%
F003 | Lane Closure for Bridge Construction - Hwy 2 Single SBL (GCS 1.2.42.5) (Special Provisions) | day | 3000 | 34 | 102000 | 18 | 54000 | 34.6%
F003 | Lane Closure for Bridge Construction - Hwy 2 Two SBL (GCS 1.2.42.5) (Special Provisions) | day | 7500 | 16 | 120000 | 13 | 97500 | 92.6%
F003 | Lane Closure for Bridge Construction - Hwy 2 All SBL (GCS 1.2.42.5) (Special Provisions) | day | 15000 | 8 | 120000 | 5 | 75000 | 49%
Tender: 24814 ¦ Bridge File: 78895-2 ¦ Tender Opening Date: 2026-02-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23904 | Bridge Rehabilitation | Bridge | Multiple | Bridge Rehabilitation | 2025-2026 | 2026-02-26 | 6 | 2027-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74355W-1 | 16 km Southwest of Cochrane | Southern | 1:06 | Jumpingpound Creek | 6 x 2080 CT | 18 ¦ 25 ¦ 25 ¦ 18 | 86 | 16.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 295000 | 295000 | 317553.33 | 317553.33 | 29.5%
F750 | Traffic Accommodation for Bridge Construction (B.F. 74355W-1) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 300000 | 300000 | 199603.33 | 199603.33 | 49.1%
E018 | Nest Removal and/or Deterrence (B.F. 74255W-1) (Special Provisions) | lump sum | 1 | 20000 | 20000 | 21156.67 | 21156.67 | 65.8%
F018 | Bridge Washing (B.F. 74355W-1) (Special Provisions) | lump sum | 1 | 30000 | 30000 | 13601.33 | 13601.33 | 20.1%
F018 | Consultant's Level 1.5 Inspection Access (B.F. 74355W-1) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 19100 | 19100 | 51.8%
F755 | Surface Removal - Bridge Deck and Approach Slabs (incl. Hand Removals) (B.F. 74355W-1) (BCS 20.6.1) (Special Provisions) | square metre | 1375 | 200 | 275000 | 80.33 | 110453.75 | 51.5%
F760 | Partial Depth Repair - Deck and Approach Slabs (Type 1 - Driving Lanes) (B.F. 74355W-1) (BCS 20.6.2) | square metre | 142 | 1500 | 213000 | 2022 | 287124 | 51.2%
F760 | Partial Depth Repair - Deck and Approach Slabs (Type 2 - Shoulders) (B.F. 74355W-1) (BCS 20.6.2) | square metre | 18 | 1500 | 27000 | 1954.67 | 35184.06 | 43.1%
F053 | Partial Depth Repair - Grout Pockets (B.F. 74355W-1) (Special Provisions) | unit | 220 | 250 | 55000 | 106.33 | 23392.6 | 32.6%
F760 | Partial Depth Repair - Deck Joint End Dams (B.F. 74355W-1) (BCS 20.6.2) | square metre | 1 | 2000 | 2000 | 4332.67 | 4332.67 | 38.1%
F760 | Partial Depth Repair - Curbs (Top and Interior Face) (B.F. 74355W-1) (BCS 20.6.2) | square metre | 6 | 2750 | 16500 | 3184.33 | 19105.98 | 31.1%
F760 | Partial Depth Repair - Deck Soffits and Haunches (B.F. 74355W-1) (BCS 20.6.2) | square metre | 4.5 | 5000 | 22500 | 6771.33 | 30470.99 | 51%
F760 | Partial Depth Repair - Curb Fascia (B.F. 74355W-1) (BCS 20.6.2) | square metre | 8.5 | 5000 | 42500 | 5853.33 | 49753.31 | 51.8%
F760 | Partial Depth Repair - End Diaphragms, Parapets, Wingwalls, and Curtain Walls (B.F. 74355W-1) (BCS 20.6.2) | square metre | 15 | 2500 | 37500 | 2899.33 | 43489.95 | 10.1%
F765 | Full Depth Repair - Deck (B.F. 74355W-1) (BCS 20.6.2) | square metre | 10 | 3500 | 35000 | 4162 | 41620 | 16.6%
F765 | Full Depth Repair - End Diaphragms and Parapet End Connections (B.F. 74355W-1) (BCS 20.6.2) | square metre | 4 | 2500 | 10000 | 4332 | 17328 | 25.3%
F765 | Full Depth Repair - Curtain Wall - NW (B.F. 74355W-1) (BCS 20.6.2) | square metre | 1 | 3500 | 3500 | 5768.67 | 5768.67 | 33.2%
F765 | Full Depth Repair - Concrete Drain Trough - SW (B.F. 74355W-1) (BCS 20.6.2) | square metre | 1 | 3500 | 3500 | 4192 | 4192 | 18.5%
F020 | Crack Sealing - Gravity Fed Repair - Horizontal (Deck) (B.F. 74355W-1) (Special Provisions) | metre | 100 | 250 | 25000 | 149 | 14900 | 12.4%
F020 | Crack Sealing - Pressure Injection - Vertical or Overhead (Deck Soffits, Diaphragms, Parapets, and Abutments) (B.F. 74355W-1) (Special Provisions) | metre | 60 | 500 | 30000 | 372.67 | 22360.2 | 17.1%
F020 | Crack Sealing - Pressure Injection - Vertical or Overhead (Girders) (B.F. 74355W-1) (Special Provisions) | metre | 34 | 500 | 17000 | 386 | 13124 | 19%
F020 | Crack Sealing - Cracks Narrower than 0.2 mm - Type 1c Sealer (Girders) (B.F. 74355W-1) (Special Provisions) | metre | 50 | 50 | 2500 | 98.67 | 4933.5 | 38.8%
F018 | Deck Joint Maintenance (B.F. 74355W-1) (Special Provisions) | lump sum | 1 | 80000 | 80000 | 47092.33 | 47092.33 | 80.2%
F770 | Abrasive Blasting - Deck Surface - Bridge Deck and Approach Slabs (B.F. 74355W-1) (BCS 20.6.3) (Special Provisions) | square metre | 1375 | 75 | 103125 | 22.33 | 30703.75 | 40.1%
Q797 | Chip Seal Coat (CRS-2P) - Bridge Decks - Des. 3 Class 12.5AW (HCS 3.24.12) (Special Provisions) | square metre | 1375 | 100 | 137500 | 101.33 | 139328.75 | 13.1%
F018 | Bridgerail - Grout Pad Repairs and Baseplate Coating Repairs (B.F. 74355W-1) (Special Provisions) | lump sum | 1 | 15000 | 15000 | 10900 | 10900 | 37.7%
F018 | Girder - Strengthening System Repairs (B.F. 74355W-1) (Special Provisions) | lump sum | 1 | 15000 | 15000 | 20705.33 | 20705.33 | 25.5%
F151 | Protection of the Environment (B.F. 74355W-1) (BCS 22.25.1) (Special Provisions) | lump sum | 1 | 60000 | 60000 | 50790 | 50790 | 44.3%
F053 | Bearing - Abutments - Coating Repairs (B.F. 74355W-1) (Special Provisions) | unit | 12 | 20000 | 240000 | 5540 | 66480 | 9.5%
F018 | Bearing - Piers - Repairs (B.F. 74355W-1) (Special Provisions) | lump sum | 1 | 2000 | 2000 | 7520 | 7520 | 51.6%
F022 | Concrete Cleaning and Sealing - Type 1c - Curbs and Deck Joint End Dams (B.F. 74355W-1) (Special Provisions) | square metre | 205 | 100 | 20500 | 50.33 | 10317.65 | 27.7%
F022 | Concrete Cleaning and Sealing - Type 3 - Curb Fascia, Parapets, Wingwalls, and Curtain Walls (B.F. 74355W-1) (Special Provisions) | square metre | 140 | 150 | 21000 | 136 | 19040 | 59.3%
F022 | Concrete Cleaning and Sealing - Type 3 - Abutment Seats (B.F. 74355W-1) (Special Provisions) | square metre | 35 | 200 | 7000 | 173.67 | 6078.45 | 33.7%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) (Special Provisions) | metre | 9 | 850 | 7650 | 265.67 | 2391.03 | 13.8%
S040 | Wing End Treatment - Supply and Install - SW (B.F. 74355W-1) (Special Provisions) | each | 1 | 2500 | 2500 | 5901 | 5901 | 136.3%
Q018 | Approach Road Transitions - Milling and Pavement (B.F. 74355W-1) (Special Provisions) | lump sum | 1 | 125000 | 125000 | 124492 | 124492 | 17.4%
S351 | Roadway Lines - Supplying Paint and Painting (Lane Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.2 | 10000 | 2000 | 7010 | 1402 | 23.1%
X002 | Extra Work - Miscellaneous Repairs (B.F. 74355W-1) (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | 100000 | 100000 | 0%
|  | Bridge File Modified Tender Value |  |  | 2425775 |  | 1941690.63 | 3.2%
|  | Total Tender Value |  |  |  |  | 5324898 | 4.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 120 | 180000 | 117 | 175500 | 4%
F003 | Lane Closure for Bridge Construction - Hwy 1 WBL (B.F. 74355W-1) (GCS 1.2.42.5) (Special Provisions) | day | 3000 | 105 | 315000 | 138 | 414000 | 6.2%
F003 | Lane Closure for Bridge Construction - Hwy 1 Single WBL (B.F. 74355W-1) (GCS 1.2.42.5) (Special Provisions) | day | 2000 | 15 | 30000 | 22 | 44000 | 53.6%
Tender: 23904 ¦ Bridge File: 74355-1 ¦ Tender Opening Date: 2026-02-26
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23904 | Bridge Rehabilitation | Bridge | Multiple | Bridge Rehabilitation | 2025-2026 | 2026-02-26 | 6 | 2027-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74458S-1 | 1 km Southeast of Aldersyde | Southern | 2:12 | Highwood River | 6 x 2080 CT | 18 ¦ 25 ¦ 25 ¦ 18 | 86 | 16.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 316000 | 316000 | 317220 | 317220 | 29.4%
F750 | Traffic Accommodation for Bridge Construction (B.F. 74458S-1) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 300000 | 300000 | 196324.67 | 196324.67 | 52.4%
E018 | Nest Removal and/or Deterrence (B.F. 74458S-1) | lump sum | 1 | 20000 | 20000 | 20955.33 | 20955.33 | 62.4%
F018 | Bridge Washing (B.F. 74458S-1) (Special Provisions) | lump sum | 1 | 30000 | 30000 | 13634.67 | 13634.67 | 19.9%
F018 | Consultant's Level 1.5 Inspection Access (B.F. 74458S-1) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 23900 | 23900 | 39.7%
F755 | Surface Removal - Bridge Deck and Approach Slabs (incl. Hand Removals) (B.F. 74458S-1) (BCS 20.6.1) (Special Provisions) | square metre | 1355 | 150 | 203250 | 75.4 | 102167 | 63.9%
F760 | Partial Depth Repair - Deck and Approach Slabs (Type 1 - Driving Lanes) (B.F. 74458S-1) (BCS 20.6.2) | square metre | 204 | 1500 | 306000 | 1918.67 | 391408.68 | 47.4%
F760 | Partial Depth Repair - Deck and Approach Slabs (Type 2 - Shoulders) (B.F. 74458S-1) (BCS 20.6.2) | square metre | 9 | 1500 | 13500 | 2053 | 18477 | 38.9%
F053 | Partial Depth Repair - Grout Pockets (B.F. 74458S-1) (Special Provisions) | unit | 405 | 250 | 101250 | 98.33 | 39823.65 | 39.3%
F760 | Partial Depth Repair - Deck Joint End Dams (B.F. 74458S-1) (BCS 20.6.2) | square metre | 1 | 2000 | 2000 | 4779.33 | 4779.33 | 43.9%
F760 | Partial Depth Repair - Curbs (Top and Interior Face) (B.F. 74458S-1) (BCS 20.6.2) | square metre | 11 | 2750 | 30250 | 3374 | 37114 | 45.2%
F760 | Partial Depth Repair - Deck Soffits (B.F. 74458S-1) (BCS 20.6.2) | square metre | 9 | 5000 | 45000 | 6339.33 | 57053.97 | 45.1%
F760 | Partial Depth Repair - Curb Fascia (B.F. 74458S-1) (BCS 20.6.2) | square metre | 2.5 | 5000 | 12500 | 7625.33 | 19063.33 | 65.7%
F760 | Partial Depth Repair - Pier Diaphragm (B.F. 74458S-1) (BCS 20.6.2) | square metre | 3.5 | 5000 | 17500 | 6688 | 23408 | 58.7%
F760 | Partial Depth Repair - Parapets, Wingwalls, and Abutments (B.F. 74458S-1) (BCS 20.6.2) | square metre | 4 | 2500 | 10000 | 6227.67 | 24910.68 | 62.7%
F760 | Partial Depth Repair - Girders (B.F. 74458S-1) (BCS 20.6.2) (Special Provisions) | square metre | 1 | 3000 | 3000 | 8174.67 | 8174.67 | 49.9%
F765 | Full Depth Repair - Deck (B.F. 74458S-1) (BCS 20.6.2) | square metre | 5 | 3500 | 17500 | 4808.67 | 24043.35 | 27.5%
F765 | Full Depth Repair - Parapet End Connections - SW, SE (B.F. 74458S-1) (BCS 20.6.2) | square metre | 1 | 2500 | 2500 | 5505.33 | 5505.33 | 34.1%
F020 | Crack Sealing - Gravity Fed Repair - Horizontal (Deck) (B.F. 74458S-1) (Special Provisions) | metre | 155 | 250 | 38750 | 145.67 | 22578.85 | 10.3%
F020 | Crack Sealing - Pressure Injection - Vertical or Overhead (Deck Soffits, Diaphragms, Parapets, and Curtain Walls) (B.F. 74458S-1) (Special Provisions) | metre | 60 | 500 | 30000 | 372.67 | 22360.2 | 17.1%
F020 | Crack Sealing - Pressure Injection - Vertical or Overhead (Girders) (B.F. 74458S-1) (Special Provisions) | metre | 45 | 500 | 22500 | 392.67 | 17670.15 | 21%
F020 | Crack Sealing - Cracks Narrower than 0.2 mm - Type 1c Sealer (Girders) (B.F. 74458S-1) (Special Provisions) | metre | 40 | 50 | 2000 | 103.67 | 4146.8 | 33%
F018 | Deck Joint Sealing Gland Replacement (B.F. 74458S-1) (Special Provisions) | lump sum | 1 | 65000 | 65000 | 58182.33 | 58182.33 | 57.4%
F770 | Abrasive Blasting - Deck Surface - Bridge Deck and Approach Slabs (B.F. 74458S-1) (BCS 20.6.3) (Special Provisions) | square metre | 1355 | 75 | 101625 | 23 | 31165 | 35%
Q797 | Chip Seal Coat (CRS-2P) - Bridge Decks - Des. 3 Class 12.5AW (HCS 3.24.12) (Special Provisions) | square metre | 1355 | 100 | 135500 | 101.33 | 137302.15 | 13.1%
F018 | Bridgerail - Grout Pad Repairs and Baseplate Coating Repairs (B.F. 74458S-1) (Special Provisions) | lump sum | 1 | 15000 | 15000 | 9656.67 | 9656.67 | 41.8%
F018 | Girder - Strengthening System Repairs (B.F. 74458S-1) (Special Provisions) | lump sum | 1 | 15000 | 15000 | 31265.33 | 31265.33 | 34.6%
F151 | Protection of the Environment (B.F. 74458S-1) (BCS 22.25.1) (Special Provisions) | lump sum | 1 | 60000 | 60000 | 50790 | 50790 | 44.3%
F053 | Bearing - Abutments - Coating Repairs (B.F. 74458S-1) (Special Provisions) | unit | 12 | 20000 | 240000 | 5540 | 66480 | 9.5%
F018 | Bearing - Piers - Repairs (B.F. 74458S-1) (Special Provisions) | lump sum | 1 | 2000 | 2000 | 7520 | 7520 | 51.6%
F022 | Concrete Cleaning and Sealing - Type 1c - Curbs and Deck Joint End Dams (B.F. 74458S-1) (Special Provisions) | square metre | 215 | 100 | 21500 | 50 | 10750 | 28.5%
F022 | Concrete Cleaning and Sealing - Type 3 - Curb Fascia, Parapets, Wingwalls, and Curtain Walls (B.F. 74458S-1) (Special Provisions) | square metre | 160 | 150 | 24000 | 136 | 21760 | 59.3%
F022 | Concrete Cleaning and Sealing - Type 3 - Abutment Seats (B.F. 74458S-1) (Special Provisions) | square metre | 35 | 200 | 7000 | 173.33 | 6066.55 | 33.8%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) (Special Provisions) | metre | 131 | 75 | 9825 | 41 | 5371 | 50.5%
S020 | Strong Post W-Beam Guardrail - Supply and Install (Special Provisions) | metre | 122 | 400 | 48800 | 226.33 | 27612.26 | 24.8%
S018 | Thrie Beam Approach Rail Transitions - Supply and Install - West Approach (B.F. 74458S-1) (Special Provisions) | lump sum | 1 | 40000 | 40000 | 26427 | 26427 | 11.5%
S018 | TL-3 Rated FLEAT 350 End Treatment - Supply and Install - West Approach (B.F. 74458S-1) (Special Provisions) | lump sum | 1 | 16000 | 16000 | 11964.33 | 11964.33 | 11.3%
S040 | Wing End Treatment - Supply and Install - East Approach (B.F. 74458S-1) (Special Provisions) | each | 2 | 2500 | 5000 | 2863.33 | 5726.66 | 130.8%
Q018 | Approach Transitions - Milling and Pavement (B.F. 74458S-1) (Special Provisions) | lump sum | 1 | 175000 | 175000 | 147360.33 | 147360.33 | 41%
S351 | Roadway Lines - Supplying Paint and Painting (Lane Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.2 | 10000 | 2000 | 7010 | 1402 | 23.1%
X002 | Extra Work - Miscellaneous Repairs (B.F. 74458S-1) (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | 100000 | 100000 | 0%
|  | Bridge File Modified Tender Value |  |  | 2631750 |  | 2151521.27 | 5%
|  | Total Tender Value |  |  |  |  | 5324898 | 4.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 120 | 180000 | 110 | 165000 | 7.4%
F003 | Lane Closure for Bridge Construction - Hwy 2 SBL (B.F. 74458S-1) (GCS 1.2.42.5) (Special Provisions) | day | 3000 | 105 | 315000 | 130 | 390000 | 12.6%
F003 | Lane Closure for Bridge Construction - Hwy 2 Single SBL (B.F. 74458S-1) (GCS 1.2.42.5) (Special Provisions) | day | 2000 | 15 | 30000 | 22 | 44000 | 53.6%
Tender: 23904 ¦ Bridge File: 74458-1 ¦ Tender Opening Date: 2026-02-26
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23518 | Bridge Rehabilitation | Bridge | Multiple | Bridge Rehabilitation | 2025-2026 | 2026-02-27 | 3 | 2027-10-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75340N-1 | 3 km West of Lacombe | Central | 2:26 | Highway 12 | 10 x 1320 Type-O | 15 ¦ 29 ¦ 15 | 59 | 17.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 656286.31 | 656286.31 | 775877.34 | 775877.34 | 11.3%
F750 | PRORATED - Traffic Accommodation for Bridge Construction (B.F. 75340 N&S) (HCS 7.1.12) | lump sum | 1 | 200497.61 | 200497.61 | 1927829.86 | 1927829.86 | 3.4%
E018 | PRORATED - Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 12531.1 | 12531.1 | 15915.37 | 15915.37 | 35.3%
F170 | Demolition and Disposal of Bridge Structure (B.F. 75340N) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 60483.33 | 60483.33 | 15.2%
F018 | Temporary Access to Piers (Special Provisions) | lump sum | 1 | 70000 | 70000 | 37100 | 37100 | 15.2%
F841 | Concrete (Class HPC) - Supply and Place (B.F. 75340N) (BCS 4.27.1) | cubic metre | 57 | 3000 | 171000 | 2600 | 148200 | 5.4%
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 75340N) (BCS 5.6) | kilogram | 10745 | 12.5 | 134312.5 | 11.17 | 120021.65 | 20.1%
F854 | Reinforcing Steel - Place (B.F. 75340N) (BCS 5.6) | kilogram | 10745 | 3 | 32235 | 2.48 | 26647.6 | 19.2%
F018 | Deck Joint Assemblies - Remove and Replace (Special Provisions) | lump sum | 1 | 510000 | 510000 | 464633.33 | 464633.33 | 7.5%
F755 | Surface Removal (B.F. 75340N) (BCS 20.6.1) | square metre | 956 | 200 | 191200 | 190 | 181640 | 42.8%
F770 | Abrasive Blasting - Deck Surface (B.F. 75340N) (BCS 20.6.3) | square metre | 956 | 30 | 28680 | 21.67 | 20716.52 | 33.8%
F775 | Deck Overlay Concrete - Supply (B.F. 75340N) (BCS 20.6.4) | cubic metre | 83 | 2000 | 166000 | 2055 | 170565 | 8.4%
F776 | Deck Overlay Concrete - Place (B.F. 75340N) (BCS 20.6.4) | square metre | 956 | 175 | 167300 | 150 | 143400 | 4.7%
F760 | Partial Depth Repair - Deck Slab (BCS 20.6.2) | square metre | 98 | 2000 | 196000 | 893.33 | 87546.34 | 11.8%
F760 | Partial Depth Repair - Deck Soffit (BCS 20.6.2) | square metre | 8 | 3000 | 24000 | 4336.67 | 34693.36 | 58.3%
F765 | Full Depth Repair - Deck Slab (BCS 20.6.2) | square metre | 11 | 4000 | 44000 | 2330 | 25630 | 31.3%
F760 | Partial Depth Repair - Piers and Abutments (BCS 20.6.2) | square metre | 18 | 2400 | 43200 | 3970 | 71460 | 33.5%
F760 | Partial Depth Repair - Curbs and Deck End Beams (BCS 20.6.2) | square metre | 16 | 2400 | 38400 | 3033.33 | 48533.28 | 16.8%
F020 | Crack Repair - Gravity Fed (Special Provisions) | metre | 34 | 135 | 4590 | 223.33 | 7593.22 | 34%
F020 | Crack Repair - Epoxy Injection (Special Provisions) | metre | 8 | 395 | 3160 | 408.33 | 3266.64 | 40%
F993 | Galvanic Corrosion Protection - Supply and Install (Special Provisions) | anodes | 605 | 125 | 75625 | 93.33 | 56464.65 | 20.7%
F022 | Concrete Slope Protection - Remove and Replace (Special Provisions) | square metre | 77 | 650 | 50050 | 1080 | 83160 | 22.6%
F018 | External Shear Reinforcement (Special Provisions) | lump sum | 1 | 770000 | 770000 | 1199466.67 | 1199466.67 | 6.2%
F019 | Replacement of Vertical Clearance Sign (Special Provisions) | location | 1 | 7500 | 7500 | 783.33 | 783.33 | 40.9%
F019 | Girder End Repairs (Special Provisions) | location | 12 | 2500 | 30000 | 5460 | 65520 | 46.8%
F022 | Girder Repairs (Special Provisions) | square metre | 2 | 3000 | 6000 | 5240 | 10480 | 24.8%
F020 | Girder Crack Repairs (Special Provisions) | metre | 3 | 650 | 1950 | 838.33 | 2514.99 | 57.9%
F018 | Abutment Void Fill - Mobilization (Special Provisions) | lump sum | 1 | 10000 | 10000 | 1080 | 1080 | 32.6%
F021 | Abutment Void Fill - Install (Special Provisions) | cubic metre | 12 | 1100 | 13200 | 1570 | 18840 | 10%
F911 | Drain Troughs (B.F. 75340N) (BCS 9.7) | metre | 74.4 | 900 | 66960 | 1193.33 | 88783.75 | 23.3%
F018 | Surface Preparation and Coating - Diaphragms (Special Provisions) | lump sum | 1 | 290000 | 290000 | 192900 | 192900 | 46.2%
F151 | Protection of the Environment - Diaphragms (B.F. 75340N) (BCS 22.25.1) | lump sum | 1 | 70000 | 70000 | 80803.33 | 80803.33 | 121.9%
F151 | Protection of the Environment - Bearings (B.F. 75340N) (BCS 22.25.1) | lump sum | 1 | 20000 | 20000 | 69683.33 | 69683.33 | 10.5%
F019 | Bearing Replacement (Special Provisions) | location | 52 | 9000 | 468000 | 25341.67 | 1317766.84 | 30.3%
F018 | Seal Curb Surfaces (Special Provisions) | lump sum | 1 | 25000 | 25000 | 19283.33 | 19283.33 | 27.9%
F018 | Seal Exterior Girder Faces (Special Provisions) | lump sum | 1 | 80000 | 80000 | 25416.67 | 25416.67 | 46.6%
F018 | Seal Abutment and Pier Surfaces (Special Provisions) | lump sum | 1 | 20000 | 20000 | 32650 | 32650 | 34%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 5000 | 5000 | 3803.33 | 3803.33 | 26.1%
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 200000 | 200000 | 200000 | 200000 | 0%
Q554 | Cold Milling Asphalt Pavement - 50 <mm Depth> (Special Provisions) | square metre | 800 | 20 | 16000 | 55.67 | 44536 | 26.9%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 140 | 600 | 84000 | 420 | 58800 | 6.7%
S351 | Roadway Lines - Supplying Paint and Painting (Lane Dividing and 2 Edge Lines) (HCS 7.2.6) | kilometre | 0.11 | 35000 | 3850 | 30400 | 3344 | 68.6%
|  | Bridge File Modified Tender Value |  |  | 5031527.52 |  | 7947833.06 | 8.7%
|  | Total Tender Value |  |  |  |  | 16586209.17 | 8.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | PRORATED - Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 161 | 241500 | 7.2%
F003 | PRORATED - Lane Closure for Bridge Construction - Highway 2 (GCS 1.2.42.5) (Special Provisions) | day | 3000 | - | - | 22 | 66000 | 31.6%
F003 | PRORATED - Lane Closure for Bridge Construction - Highway 12 (GCS 1.2.42.5) (Special Provisions) | day | 1000 | - | - | 26 | 26000 | 68.3%
Tender: 23518 ¦ Bridge File: 75340-1 ¦ Tender Opening Date: 2026-02-27
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23518 | Bridge Rehabilitation | Bridge | Multiple | Bridge Rehabilitation | 2025-2026 | 2026-02-27 | 3 | 2027-10-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75340S-2 | 3 km West of Lacombe | Central | 2:26 | Highway 12 | 10 x 1320 Type-O | 15 ¦ 29 ¦ 15 | 59 | 17.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 653028.69 | 653028.69 | 777976 | 777976 | 11.7%
F750 | PRORATED - Traffic Accommodation for Bridge Construction (B.F. 75340 N&S) (HCS 7.1.12) | lump sum | 1 | 199502.39 | 199502.39 | 1931836.81 | 1931836.81 | 2.8%
E018 | PRORATED - Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 12468.9 | 12468.9 | 15967.96 | 15967.96 | 35.5%
F170 | Demolition and Disposal of Bridge Structure (B.F. 75340S) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 58383.33 | 58383.33 | 20.3%
F018 | Temporary Access to Piers (Special Provisions) | lump sum | 1 | 70000 | 70000 | 37100 | 37100 | 15.2%
F841 | Concrete (Class HPC) - Supply and Place (B.F. 75340S) (BCS 4.27.1) | cubic metre | 57 | 3000 | 171000 | 2633.33 | 150099.81 | 4.7%
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 75340S) (BCS 5.6) | kilogram | 10745 | 12.5 | 134312.5 | 11.17 | 120021.65 | 20.1%
F854 | Reinforcing Steel - Place (B.F. 75340S) (BCS 5.6) | kilogram | 10745 | 3 | 32235 | 2.48 | 26647.6 | 19.2%
F018 | Deck Joint Assemblies - Remove and Replace (Special Provisions) | lump sum | 1 | 510000 | 510000 | 461533.33 | 461533.33 | 8.3%
F755 | Surface Removal (B.F. 75340S) (BCS 20.6.1) | square metre | 956 | 200 | 191200 | 189 | 180684 | 49.6%
F770 | Abrasive Blasting - Deck Surface (B.F. 75340S) (BCS 20.6.3) | square metre | 956 | 30 | 28680 | 21.67 | 20716.52 | 33.8%
F775 | Deck Overlay Concrete - Supply (B.F. 75340S) (BCS 20.6.4) | cubic metre | 80 | 2000 | 160000 | 2080 | 166400 | 6.7%
F776 | Deck Overlay Concrete - Place (B.F. 75340S) (BCS 20.6.4) | square metre | 956 | 175 | 167300 | 150 | 143400 | 4.7%
F760 | Partial Depth Repair - Deck Slab (BCS 20.6.2) | square metre | 84 | 2000 | 168000 | 906.67 | 76160.28 | 12.3%
F760 | Partial Depth Repair - Deck Soffit (BCS 20.6.2) | square metre | 7 | 3000 | 21000 | 4323.33 | 30263.31 | 61.3%
F765 | Full Depth Repair - Deck Slab (BCS 20.6.2) | square metre | 7 | 4000 | 28000 | 2446.67 | 17126.69 | 33.2%
F760 | Partial Depth Repair - Piers and Abutments (BCS 20.6.2) | square metre | 18 | 2000 | 36000 | 3973.33 | 71519.94 | 33.5%
F760 | Partial Depth Repair - Curbs and Deck End Beams (BCS 20.6.2) | square metre | 20 | 2000 | 40000 | 3123.33 | 62466.6 | 14%
F020 | Crack Repair - Gravity Fed (Special Provisions) | metre | 34 | 135 | 4590 | 223.33 | 7593.22 | 34%
F020 | Crack Repair - Epoxy Injection (Special Provisions) | metre | 17 | 395 | 6715 | 363.33 | 6176.61 | 29.2%
F993 | Galvanic Corrosion Protection - Supply and Install (Special Provisions) | anodes | 540 | 125 | 67500 | 93.33 | 50398.2 | 20.7%
F022 | Concrete Slope Protection - Remove and Replace (Special Provisions) | square metre | 89 | 650 | 57850 | 993.33 | 88406.37 | 22.7%
F018 | External Shear Reinforcement (Special Provisions) | lump sum | 1 | 770000 | 770000 | 1206333.33 | 1206333.33 | 5.6%
F019 | Replacement of Vertical Clearance Sign (Special Provisions) | location | 1 | 7500 | 7500 | 783.33 | 783.33 | 40.9%
F019 | Girder End Repair (Special Provisions) | location | 14 | 2500 | 35000 | 5483.33 | 76766.62 | 46.6%
F022 | Girder Repairs (Special Provisions) | square metre | 4 | 3000 | 12000 | 4340 | 17360 | 47.3%
F020 | Girder Crack Repairs (Special Provisions) | metre | 7 | 650 | 4550 | 656.67 | 4596.69 | 33.3%
F018 | Abutment Void Fill - Mobilization (Special Provisions) | lump sum | 1 | 10000 | 10000 | 1063.33 | 1063.33 | 32.4%
F021 | Abutment Void Fill - Install (Special Provisions) | cubic metre | 8 | 1100 | 8800 | 1630 | 13040 | 10.2%
F911 | Drain Troughs (B.F. 75340S) (BCS 9.7) | metre | 89.1 | 900 | 80190 | 1106.67 | 98604.3 | 26.8%
F018 | Surface Preparation and Coating - Diaphragms (Special Provisions) | lump sum | 1 | 290000 | 290000 | 189833.33 | 189833.33 | 42.8%
F151 | Protection of the Environment - Diaphragms (B.F. 75340S) (BCS 22.25.1) | lump sum | 1 | 70000 | 70000 | 80803.33 | 80803.33 | 121.9%
F151 | Protection of the Environment - Bearings (B.F. 75340S) (BCS 22.25.1) | lump sum | 1 | 20000 | 20000 | 69683.33 | 69683.33 | 10.5%
F019 | Bearing Replacement (Special Provisions) | location | 52 | 9000 | 468000 | 25266.67 | 1313866.84 | 30.7%
F019 | Deck Drain Extension (Special Provisions) | location | 12 | 1000 | 12000 | 1006.67 | 12080.04 | 70.3%
F018 | Seal Curb Surfaces (Special Provisions) | lump sum | 1 | 25000 | 25000 | 13750 | 13750 | 61.4%
F018 | Seal Exterior Girder Faces (Special Provisions) | lump sum | 1 | 80000 | 80000 | 24916.67 | 24916.67 | 46.3%
F018 | Seal Abutment and Pier Surfaces (Special Provisions) | lump sum | 1 | 20000 | 20000 | 34216.67 | 34216.67 | 27.9%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 5000 | 5000 | 4053.33 | 4053.33 | 31.8%
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 200000 | 200000 | 200000 | 200000 | 0%
Q554 | Cold Milling Asphalt Pavement - 50 <mm Depth> (Special Provisions) | square metre | 779 | 20 | 15580 | 57.33 | 44660.07 | 27.6%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 140 | 600 | 84000 | 421.67 | 59033.8 | 7.3%
S351 | Roadway Lines - Supplying Paint and Painting (Lane Dividing and 2 Edge Lines) (HCS 7.2.6) | kilometre | 0.13 | 35000 | 4550 | 26066.67 | 3388.67 | 78.2%
|  | Bridge File Modified Tender Value |  |  | 5006552.48 |  | 7969711.91 | 9.3%
|  | Total Tender Value |  |  |  |  | 16586209.17 | 8.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | PRORATED - Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 162 | 243000 | 7.4%
F003 | PRORATED - Lane Closure for Bridge Construction - Highway 2 (GCS 1.2.42.5) (Special Provisions) | day | 3000 | - | - | 22 | 66000 | 31.7%
F003 | PRORATED - Lane Closure for Bridge Construction - Highway 12 (GCS 1.2.42.5) (Special Provisions) | day | 1000 | - | - | 26 | 26000 | 70.7%
Tender: 23518 ¦ Bridge File: 75340-2 ¦ Tender Opening Date: 2026-02-27
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22934 | Construct PBC Culvert | Culvert | Single | Replace Culvert with Culver | 2025-2026 | 2026-03-12 | 10 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
78177-2 | Near Millarville | Southern | 549:04 | Tributary to Pothole Creek | 1 x 3000 PBC | 41 | 41 | 3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 90090 | 90090 | 91533.33 | 91533.33 | 41.5%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 160000 | 160000 | 109050 | 109050 | 51.8%
X053 | Total Suspended Solids (TSS) Testing (Special Provisions) | person day | 4 | 1000 | 4000 | 1633.33 | 6533.32 | 72.8%
X053 | Fish Capture and Release (Special Provisions) | person day | 2 | 5000 | 10000 | 2850 | 5700 | 88.6%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 15000 | 15000 | 11643.33 | 11643.33 | 51.4%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 18566.67 | 18566.67 | 63.7%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 10000 | 10000 | 12433.33 | 12433.33 | 88.6%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 85000 | 85000 | 60166.67 | 60166.67 | 14.6%
F1001 | PBC - Supply (1.5m rise x 3.0m span) (BCS 26.4) | metre | 41 | 6500 | 266500 | 5473.33 | 224406.53 | 6.1%
F1002 | PBC - Install (1.5m rise x 3.0m span) (BCS 26.4) | metre | 41 | 2000 | 82000 | 1489.83 | 61083.03 | 29.7%
F974 | Waterproofing (BCS 16.5) | square metre | 200 | 110 | 22000 | 111 | 22200 | 39.8%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 150 | 350 | 52500 | 231.67 | 34750.5 | 14.4%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 1200 | 1200 | 2500 | 2500 | 74.8%
E020 | Erosion Control Barrier (Fibre Rolls) (Special Provisions) | metre | 200 | 25 | 5000 | 16.17 | 3234 | 5.3%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 310 | 10 | 3100 | 8.17 | 2532.7 | 38.8%
G452 | Remove and Dispose of Existing Fence (HCS 2.12.5) | kilometre | 0.25 | 7500 | 1875 | 10833.33 | 2708.33 | 27.8%
C248 | Temporary Fencing (Special Provisions) | metre | 220 | 40 | 8800 | 14 | 3080 | 20.2%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.21 | 20000 | 4200 | 28666.67 | 6020 | 31.4%
F492 | Roadway Work (Special Provisions) (BCS 18.7) | lump sum | 1 | 95000 | 95000 | 71333.33 | 71333.33 | 20.5%
F018 | High-Tension Cable Barrier (Removal/Installation) | lump sum | 1 | 50000 | 50000 | 54900 | 54900 | 46.4%
|  | Bridge File Modified Tender Value |  |  | 991265 |  | 804375.07 | 4.7%
|  | Total Tender Value |  |  |  |  | 849873.17 | 4.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 25 | 37500 | 30 | 45000 | 24.7%
Tender: 22934 ¦ Bridge File: 78177-2 ¦ Tender Opening Date: 2026-03-12

## FY 2024-2025
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20345 | Construct CSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2024-2025 | 2024-04-24 | 3 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76533-2 | 2 km North of Vegreville | Central | 857:04 | Tributary to Vermilion River | 1 x 1600 CSP | 31 | 31 | 1.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 50000 | 50000 | 36863.75 | 36863.75 | 18.9%
F750 | Traffic Accommodation for Bridge Construction (B.F. 76533) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 30000 | 30000 | 8843.83 | 8843.83 | 53.4%
F186 | Excavation - Structural (B.F. 76533) (BCS 1.6.1) | lump sum | 1 | 8000 | 8000 | 11527.92 | 11527.92 | 23.3%
F170 | Demolition and Disposal of Bridge Structure (B.F. 76533) (BCS 21.4.1) | lump sum | 1 | 8750 | 8750 | 18866 | 18866 | 116.8%
F495 | CSP with Couplers - Supply (B.F. 76533) (BCS 18.7) | metre | 30.5 | 2250 | 68625 | 1525.1 | 46515.55 | 8.1%
F496 | CSP - Assembly (B.F. 76533) (BCS 18.7) | metre | 30.5 | 1500 | 45750 | 131.28 | 4004.04 | 42.3%
F203 | Backfill - Crushed Aggregate (B.F. 76533) Des. 2 Class 25 (BCS 2.4) | cubic metre | 290 | 145 | 42050 | 120.78 | 35026.2 | 13.4%
F195 | Backfill - Non-Granular (B.F. 76533) (BCS 2.4) | cubic metre | 765 | 115 | 87975 | 36.02 | 27555.3 | 36.1%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 1500 | 1500 | 1799.33 | 1799.33 | 96.1%
F492 | Roadway Work (B.F. 76533) (BCS 18.7) (Special Provisions) | lump sum | 1 | 83000 | 83000 | 69676.95 | 69676.95 | 16%
Q992 | Asphalt Concrete Pavement - EPS Mix Type M1 (PG 52-34) (HCS 5.2.5) (HCS 3.50.7) (Special Provisions) | tonne | 84 | 115 | 9660 | 464.93 | 39054.12 | 22.6%
F500 | Heavy Rock Riprap (Class 1) (B.F. 76533) (BCS 10.7) | cubic metre | 32 | 400 | 12800 | 320.71 | 10262.72 | 6.7%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 500 | 15 | 7500 | 11.74 | 5870 | 26.3%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 100 | 25 | 2500 | 18.21 | 1821 | 31.3%
E052 | Total Suspended Solids (TSS) Testing (Special Provisions) | unit | 5 | 500 | 2500 | 1263.48 | 6317.4 | 70.2%
E052 | Fish Capture and Release (Special Provisions) | unit | 2 | 3750 | 7500 | 2136.16 | 4272.32 | 70.6%
|  | Bridge File Modified Tender Value |  |  | 468110 |  | 328276.43 | 7.5%
|  | Total Tender Value |  |  |  |  | 352275.85 | 7.6%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 40 | 60000 | 16 | 24000 | 23.4%
Tender: 20345 ¦ Bridge File: 76533-2 ¦ Tender Opening Date: 2024-04-24
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22587 | Bridge High Load Damage Repair | Bridge | Single | Bridge Repair | 2024-2025 | 2024-05-01 | 2 | 2024-12-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76848W-2 | At North Boundary of Airdrie | Southern | 567:05 | Highway 2 | 5 x 1900 WG | 46 ¦ 50 | 96 | 15.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 89450 | 89450 | 187658.36 | 187658.36 | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 76848) (HCS 7.1.12) (HCS 7.1.15) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 292820 | 292820 | 540991.2 | 540991.2 | -
F018 | Heat Straightening - Up to 50 Cycles (Special Provisions) | lump sum | 1 | 358800 | 358800 | 322541.76 | 322541.76 | -
F053 | Heat Straightening - Each Cycle Above 50 Cycles (Special Provisions) | unit | 10 | 7180 | 71800 | 7829.61 | 78296.1 | -
F018 | Intermediate Diaphragm Replacement (BCS - 6.4.1) (Special Provisions) | lump sum | 1 | 31990 | 31990 | 117514.59 | 117514.59 | -
F018 | Bottom Flange Reinforcement (BCS - 6.4.1) (Special Provisions) | lump sum | 1 | 9440 | 9440 | 46332.24 | 46332.24 | -
F053 | Misc. Bridge Work - Crack Repair (Special Provisions) | unit | 5 | 630 | 3150 | 3050.93 | 15254.65 | -
F053 | Misc. Bridge Work - Removal and Replacement of Stiffeners (Special Provisions) | unit | 1 | 9740 | 9740 | 23334.2 | 23334.2 | -
|  | Bridge File Modified Tender Value |  |  | 867190 |  | 1331923.1 | -
|  | Total Tender Value |  |  |  |  | 2391923 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 2000 | 45 | 90000 | 63 | 126000 | -
F003 | Lane Closure for Bridge Construction - Hwy 2 SB Two Lanes (GCS 1.2.42.5) (GCS 1.2.42.5) (Special Provisions) | day | 10000 | 45 | 450000 | 70 | 700000 | -
F003 | Lane Closure for Bridge Construction - Hwy 567 WB Single Lane (GCS 1.2.42.5) (GCS 1.2.42.5) (Special Provisions) | day | 5000 | 32 | 160000 | 47 | 235000 | -
Tender: 22587 ¦ Bridge File: 76848-2 ¦ Tender Opening Date: 2024-05-01
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22081 | Construct CSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2024-2025 | 2024-05-02 | 4 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
77520-2 | 43 km Southeast of Irvine | Southern | 515:02 | 2nd Order Tributary to Mackay Creek | 1 x 2100 CSP | 30 | 30 | 2.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 59160 | 59160 | 44472.67 | 44472.67 | 43%
F750 | Traffic Accommodation for Bridge Construction (B.F. 77520) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 125000 | 125000 | 52493 | 52493 | 111.9%
X053 | Total Suspended Solids (TSS) Testing (Special Provisions) | person day | 4 | 1250 | 5000 | 1457.33 | 5829.32 | 28.3%
X053 | Fish Capture & Release (Special Provisions) | person day | 1 | 3750 | 3750 | 2432 | 2432 | 50.5%
F170 | Demolition and Disposal of Bridge Structure (B.F. 77520) (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 10000 | 10000 | 5833.33 | 5833.33 | 50.6%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 14800 | 14800 | 40.5%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 10000 | 10000 | 13416.67 | 13416.67 | 67.6%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 85000 | 85000 | 40911.33 | 40911.33 | 33.8%
F495 | CSP with Couplers - Supply (2.1 m Diam.) (BCS 18.7) | metre | 30 | 1800 | 54000 | 995.33 | 29859.9 | 3.6%
F496 | CSP - Assembly (2.1 m Diam.) (BCS 18.7) | metre | 30 | 650 | 19500 | 238.33 | 7149.9 | 36.6%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 55 | 300 | 16500 | 211.08 | 11609.4 | 46.6%
E020 | Erosion Control Barrier (Fibre Rolls) (Special Provisions) | metre | 100 | 25 | 2500 | 23.67 | 2367 | 37.8%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 150 | 15 | 2250 | 38.67 | 5800.5 | 79.7%
G452 | Remove and Dispose of Existing Fence (HCS 2.12.5) | kilometre | 0.11 | 20000 | 2200 | 11666.67 | 1283.33 | 51.6%
C248 | Temporary Fencing (Special Provisions) | metre | 110 | 40 | 4400 | 24.33 | 2676.3 | 13.6%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.11 | 30000 | 3300 | 26000 | 2860 | 31.9%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 1000 | 1000 | 4246.67 | 4246.67 | 129.1%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 29355.33 | 29355.33 | 38.5%
|  | Bridge File Modified Tender Value |  |  | 453560 |  | 277396.65 | 22.4%
|  | Total Tender Value |  |  |  |  | 297396.58 | 21.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1250 | 25 | 31250 | 16 | 20000 | 17.7%
Tender: 22081 ¦ Bridge File: 77520-2 ¦ Tender Opening Date: 2024-05-02
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21534 | Construct CSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2024-2025 | 2024-05-28 | 2 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
721-2 | 4 km East of Carstairs | Central | 581:02 | Sheep Coulee | 2 x 2100 CSP | 46 - 46 | 92 | 2.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 94800 | 94800 | 83250 | 83250 | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 00721) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 200000 | 200000 | 137500 | 137500 | -
X018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 50000 | 50000 | 39500 | 39500 | -
E612 | Fish Capture, Salvage, and Release (Special Provisions) | day | 4 | 2500 | 10000 | 380 | 1520 | -
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 2500 | 15000 | 905 | 5430 | -
F186 | Excavation - Structural (B.F. 00721) (BCS 1.6.1) | lump sum | 1 | 100000 | 100000 | 155000 | 155000 | -
F170 | Demolition and Disposal of Bridge Structure (B.F. 00721) (BCS 21.4.1) | lump sum | 1 | 20000 | 20000 | 87500 | 87500 | -
F495 | CSP with Couplers - Supply (B.F. 00721) (2100 mm Dia.) (BCS 18.7) | metre | 92 | 1500 | 138000 | 950 | 87400 | -
F496 | CSP - Assembly (B.F. 00721)(2100 mm Dia.) (BCS 18.7) | metre | 92 | 600 | 55200 | 175 | 16100 | -
F190 | Backfill (B.F. 00721) (BCS 2.4) | lump sum | 1 | 175000 | 175000 | 155000 | 155000 | -
F500 | Heavy Rock Riprap (Class 1) (B.F. 00721) (BCS 10.7) | cubic metre | 70 | 400 | 28000 | 275 | 19250 | -
F492 | Roadway Work (B.F. 00721) (BCS 18.7) | lump sum | 1 | 140000 | 140000 | 150000 | 150000 | -
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 1000 | 10 | 10000 | 10.5 | 10500 | -
E020 | Erosion Control Barrier (Fibre Rolls) (Special Provisions) | metre | 300 | 20 | 6000 | 17.5 | 5250 | -
|  | Bridge File Modified Tender Value |  |  | 1042000 |  | 953200 | -
|  | Total Tender Value |  |  |  |  | 990700 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 40 | 60000 | 25 | 37500 | -
Tender: 21534 ¦ Bridge File: 721-2 ¦ Tender Opening Date: 2024-05-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21917 | Construct SLW Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2024-2025 | 2024-05-30 | 6 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
7892-2 | 15 km South of Consort | Central | 886:08 | Monitor Creek | 9 x 510 SLW | 10 ¦ 10 ¦ 10 | 30 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 250000 | 250000 | 308665 | 308665 | 39.5%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 250000 | 250000 | 191332.13 | 191332.13 | 33.9%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 30000 | 30000 | 8916.67 | 8916.67 | 109%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 1220.33 | 3660.99 | 113.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 1500 | 9000 | 693.33 | 4159.98 | 130.3%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | 177213 | 177213 | 52.3%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 40000 | 40000 | 25849.33 | 25849.33 | 105.3%
F813 | Supply of Piling - Galvanized Steel H-Pile (BCS 3.6.1) | metre | 240 | 350 | 84000 | 275.83 | 66199.2 | 39.4%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 448 | 250 | 112000 | 187.83 | 84147.84 | 41.2%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 36 | 5000 | 180000 | 4979.75 | 179271 | 42.8%
F818 | Pile Driving (BCS 3.6.1) | metre | 688 | 60 | 41280 | 6.67 | 4588.96 | 35.3%
F018 | Abutment Construction (Special Provisions) | lump sum | 1 | 180000 | 180000 | 172319.33 | 172319.33 | 7.1%
F018 | Pier Construction (Special Provisions) | lump sum | 1 | 100000 | 100000 | 102168.33 | 102168.33 | 21.2%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1702 | 8 | 13616 | 9.08 | 15454.16 | 9.1%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1702 | 2.5 | 4255 | 2.87 | 4884.74 | 52.8%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 15 | 2500 | 37500 | 2737.67 | 41065.05 | 48.4%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 200 | 300 | 60000 | 221.67 | 44334 | 31.6%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 10 m Type SLW 510 (21 Interior, 6 Exterior) (BCS 7.4) | lump sum | 1 | 600000 | 600000 | 440273.13 | 440273.13 | 20.6%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 5000 | 5000 | 5689 | 5689 | 104.4%
F974 | Waterproofing (BCS 16.5) | square metre | 370 | 90 | 33300 | 115.25 | 42642.5 | 31.8%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 70 | 450 | 31500 | 406.33 | 28443.1 | 22.7%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 250000 | 250000 | 134600.67 | 134600.67 | 14%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 40000 | 40000 | 42671.67 | 42671.67 | 34%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 40000 | 40000 | 42673.33 | 42673.33 | 17.8%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.5 | 20000 | 10000 | 14533.33 | 7266.67 | 15.9%
E020 | Straw Rolls (Special Provisions) | metre | 200 | 20 | 4000 | 13 | 2600 | 38.2%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 10 | 2000 | 7.17 | 1434 | 29.2%
|  | Bridge File Modified Tender Value |  |  | 2519451 |  | 2182523.78 | 8.4%
|  | Total Tender Value |  |  |  |  | 2274028.33 | 9.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 70 | 105000 | 61 | 91500 | 37%
Tender: 21917 ¦ Bridge File: 7892-2 ¦ Tender Opening Date: 2024-05-30
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20709 | Construct DCSP Arch Culvert | Culvert | Single | Replace Bridge with Culvert | 2024-2025 | 2024-06-06 | 4 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
248-2 | 18 km North of Lundbreck | Southern | 22:06 | Wildcat Creek | 1 x 7000 DCSP Arch | 28 | 28 | 7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 280000 | 280000 | 455434.3 | 455434.3 | 32.2%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 190000 | 190000 | 320918.75 | 320918.75 | 38.5%
F052 | Fish Capture and Release (HSC 6.15.6) | unit | 1 | 2875 | 2875 | 4693.21 | 4693.21 | 58.1%
F052 | Total Suspended Solids (TSS) Testing (Special Provisions) | unit | 10 | 2875 | 28750 | 302.25 | 3022.5 | 94.6%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 57000 | 57000 | 82141.63 | 82141.63 | 55.7%
F188 | Excavation - Structural (BCS 1.6.1) | cubic metre | 905 | 20 | 18100 | 26.15 | 23665.75 | 58.5%
F189 | Excavation - Channel (BCS 1.6.1) | cubic metre | 515 | 30 | 15450 | 34.3 | 17664.5 | 76.1%
F515 | Heavy Rock Riprap (Class 2) (BCS 10.7) | cubic metre | 540 | 425 | 229500 | 205.68 | 111067.2 | 22.5%
B153 | Granular Fill Des. 2 Class 40 (HCS 3.8.5) (HCS 5.2.5) | tonne | 1960 | 40 | 78400 | 49.38 | 96784.8 | 16.6%
F203 | Backfill - Crushed Aggregate Des. 2 Class 25 (BCS 2.4) | cubic metre | 805 | 90 | 72450 | 89.7 | 72208.5 | 23.9%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 912 | 345 | 314640 | 232.03 | 211611.36 | 13.4%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 46 | 3910 | 179860 | 3850.35 | 177116.1 | 28.5%
F818 | Pile Driving (BCS 3.6.1) | metre | 912 | 65 | 59280 | 26.35 | 24031.2 | 111.9%
F820 | PDA Testing - Pile Driving Analysis (BCS 3.6.4) | test | 8 | 2335 | 18680 | 1860.97 | 14887.76 | 31.5%
F819 | Pile Tip Reinforcement (BCS 3.6.1) | pile | 46 | 1500 | 69000 | 346.02 | 15916.92 | 18.8%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 115 | 1655 | 190325 | 1103 | 126845 | 28.3%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 6004 | 3 | 18012 | 4.8 | 28819.2 | 47.3%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 6004 | 2 | 12008 | 1.5 | 9006 | 23.9%
F017 | Steel Plate Arch Culvert - Supply and Installation (Special Provisions) (Special Provisions) | lump sum | 1 | 495000 | 495000 | 596496.88 | 596496.88 | 10.9%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 260 | 290 | 75400 | 277.14 | 72056.4 | 13.5%
F018 | Line Painting (Special Provisions) | lump sum | 1 | 18000 | 18000 | 4640.62 | 4640.62 | 40.2%
F018 | Rumble Strips (Special Provisions) | lump sum | 1 | 3000 | 3000 | 10265.74 | 10265.74 | 36.8%
G270 | Sideslope Improvement (HCS 3.60.4) | kilometre | 0.1 | 128075 | 12807.5 | 255455.03 | 25545.5 | 51.1%
C057 | Imported Topsoil Placement (HSC 3.60.4) | cubic metre | 35 | 15 | 525 | 107.53 | 3763.55 | 45%
C232 | Hydroseeding (HSC 2.20) | square metre | 350 | 5 | 1750 | 12.63 | 4420.5 | 56.4%
|  | Bridge File Modified Tender Value |  |  | 2440812.5 |  | 2513023.87 | 7.7%
|  | Total Tender Value |  |  |  |  | 2746971.08 | 7.6%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 82 | 123000 | 7.5%
F003 | Lane Closure for Bridge Construction (Special Provisions) | day | 1500 | - | - | 74 | 111000 | 16.4%
Tender: 20709 ¦ Bridge File: 248-2 ¦ Tender Opening Date: 2024-06-06
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24340 | Bridge High Load Damage Repair | Bridge | Single | Bridge Repair | 2024-2025 | 2024-06-14 | 5 | 2025-02-28
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
81157E-1 | At East Boundary of Edmonton | North Central | 628:04 | Highway 216 | 9 x 1700 Bulb-T (Modified) | 29 ¦ 37 ¦ 37 ¦ 29 | 132 | 17.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 750000 | 750000 | 236634.33 | 236634.33 | 5.3%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 500000 | 500000 | 189678.67 | 189678.67 | 29.5%
F018 | Post-Tensioning Tendon Impregnation (Special Provisions) | lump sum | 1 | 200000 | 200000 | 611528.67 | 611528.67 | 7.3%
F021 | Class SCC Concrete - Supply and Place (Special Provisions) | cubic metre | 20 | 5000 | 100000 | 7234.33 | 144686.6 | 45.2%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 3893 | 5 | 19465 | 7.92 | 30832.56 | 90.3%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 3893 | 5 | 19465 | 15.23 | 59290.39 | 60%
F022 | Girder Full Depth Repair (Special Provisions) | square metre | 20 | 7500 | 150000 | 8658.33 | 173166.6 | 84.8%
F018 | Concrete Deck and Top Flange Repair (Special Provisions) | lump sum | 1 | 175000 | 175000 | 109541.33 | 109541.33 | 66.1%
F053 | Prestressing Strand Repairs (Special Provisions) | unit | 25 | 35000 | 875000 | 3595 | 89875 | 34.5%
F018 | Girder Preloading (Special Provisions) | lump sum | 1 | 125000 | 125000 | 58238.33 | 58238.33 | 51.6%
F018 | Dismantle, Removal, and Salvage of Existing Bridge Materials - Rigid Frame Structure (Special Provisions) | lump sum | 1 | 75000 | 75000 | 22409.67 | 22409.67 | 47.8%
F020 | Concrete Crack Repair - Pressure Injected Epoxy (Special Provisions) | metre | 552 | 1500 | 828000 | 282.33 | 155846.16 | 24.9%
F018 | Longitudinal Post Tensioning (Special Provisions) | lump sum | 1 | 300000 | 300000 | 130364.67 | 130364.67 | 35%
F018 | Concrete Sealer - Type 3 Pigmented (Special Provisions) | lump sum | 1 | 60000 | 60000 | 3851.67 | 3851.67 | 36%
F018 | Concrete Sealer - Type 1c (Special Provisions) | lump sum | 1 | 60000 | 60000 | 9492.67 | 9492.67 | 31.7%
F018 | Replacement of Vertical Clearance Sign (Special Provisions) | lump sum | 1 | 25000 | 25000 | 2876.33 | 2876.33 | 90.5%
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 15000 | 15000 | 11667 | 11667 | 30.8%
X002 | Extra Work - Various Repairs (Special Provisions) | Total Force Account | 1 | 200000 | 200000 | 200000 | 200000 | 0%
|  | Bridge File Modified Tender Value |  |  | 4476930 |  | 2239980.65 | 5.6%
|  | Total Tender Value |  |  |  |  | 2444315.95 | 5.6%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 100 | 150000 | 104 | 156000 | 17.7%
F003 | Lane Closure for Bridge Construction - Ramp Road (GCS 1.2.42.5) (Special Provisions) | day | 2500 | 50 | 125000 | 19 | 47500 | 68.8%
Tender: 24340 ¦ Bridge File: 81157-1 ¦ Tender Opening Date: 2024-06-14
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20098 | Extend Cast-in-Place Concrete Box Culvert | Culvert | Single | Culvert Extension | 2024-2025 | 2024-06-18 | 4 | 2025-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74661-1 | 2 km South of Exshaw | Southern | 1:02 | Tributary to Bow River | 1 x 6100 CIP Box | 61 | 61 | 6.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 70000 | 70000 | 172009.33 | 172009.33 | 12.8%
F750 | Traffic Accommodation for Bridge Construction (B.F. 74661) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 105000 | 105000 | 135492 | 135492 | 54.8%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1000 | 10000 | 1765 | 17650 | 89%
E612 | Fish Capture and Release (Special Provisions) | day | 2 | 2000 | 4000 | 2443.33 | 4886.66 | 85.4%
F188 | Excavation - Structural (B.F. 74661) (BCS 1.6.1) | cubic metre | 270 | 25 | 6750 | 78.67 | 21240.9 | 53.4%
F189 | Excavation - Channel (B.F. 74661) (BCS 1.6.1) | cubic metre | 95 | 35 | 3325 | 258 | 24510 | 92%
F170 | Demolition and Disposal of Bridge Structure (B.F. 74661) (BCS 21.4.1) | lump sum | 1 | 35000 | 35000 | 229176.33 | 229176.33 | 84.8%
F812 | Supply of Piling - Plain Steel H-Pile (B.F. 74661) (BCS 3.6.1) | metre | 75 | 330 | 24750 | 244.67 | 18350.25 | 17.9%
F816 | Pile Set-up (Driven Piles) (B.F. 74661) (BCS 3.6.1) | pile | 6 | 4500 | 27000 | 10412 | 62472 | 32.4%
F818 | Pile Driving (B.F. 74661) (BCS 3.6.1) | metre | 75 | 100 | 7500 | 160.67 | 12050.25 | 73.9%
F820 | PDA Testing (B.F. 74661) (BCS 3.6.4) | test | 2 | 3600 | 7200 | 1881.67 | 3763.34 | 35%
F834 | Concrete (Class C) - Supply and Place (B.F. 74661) (BCS 4.27.1) | cubic metre | 7.5 | 3000 | 22500 | 6189.33 | 46419.98 | 13.6%
F841 | Concrete (Class HPC) - Supply and Place (B.F. 74661) (BCS 4.27.1) | cubic metre | 6 | 4000 | 24000 | 5945 | 35670 | 18.6%
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 74661) (BCS 5.6) | kilogram | 2083 | 8 | 16664 | 14.33 | 29849.39 | 25.7%
F854 | Reinforcing Steel - Place (B.F. 74661) (BCS 5.6) | kilogram | 2083 | 3 | 6249 | 4.23 | 8811.09 | 39.4%
F018 | Wingwall Modifications (Special Provisions) | lump sum | 1 | 35000 | 35000 | 19590 | 19590 | 73.8%
F018 | Transition Curbs (Special Provisions) | lump sum | 1 | 15000 | 15000 | 7611 | 7611 | 25.6%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (B.F. 74661) (BCS 7.4) | lump sum | 1 | 65000 | 65000 | 163567.33 | 163567.33 | 30.4%
F760 | Partial Depth Repair (BCS 20.6.2) | square metre | 35 | 3000 | 105000 | 1718 | 60130 | 41%
F974 | Waterproofing (BCS 16.5) | square metre | 34 | 120 | 4080 | 206 | 7004 | 36.4%
F203 | Backfill - Crushed Aggregate (B.F. 74661) Des. 2 Class 25 (BCS 2.4) | cubic metre | 195 | 160 | 31200 | 184.33 | 35944.35 | 40.6%
F515 | Heavy Rock Riprap (Class 2) (B.F. 74661) (BCS 10.7) | cubic metre | 95 | 420 | 39900 | 453 | 43035 | 24.4%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (B.F. 74661) (BCS 12.4) | lump sum | 1 | 20000 | 20000 | 35661.33 | 35661.33 | 14.3%
S820 | Remove, Salvage and Reinstall Existing Guardrail (HCS 2.19.4) | metre | 51.5 | 221 | 11381.5 | 627.67 | 32325.01 | 87.1%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 200 | 25 | 5000 | 66 | 13200 | 116.8%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 600 | 6 | 3600 | 11.67 | 7002 | 53.4%
F492 | Roadway Work (B.F. 74661) (BCS 18.7) | lump sum | 1 | 60000 | 60000 | 134115 | 134115 | 54.6%
|  | Bridge File Modified Tender Value |  |  | 765099.5 |  | 1381536.54 | 13.7%
|  | Total Tender Value |  |  |  |  | 1755047.53 | 8.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 71 | 106500 | 16.7%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 3000 | - | - | 89 | 267000 | 27.6%
Tender: 20098 ¦ Bridge File: 74661-1 ¦ Tender Opening Date: 2024-06-18
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21132 | Construct CSP Culvert | Culvert | Single | Replace Bridge with Culvert | 2024-2025 | 2024-06-20 | 2 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76415-2 | 2 km East of Enilda | Peace | 2:52 | Mud Creek | 1 x 2900 CSP | 42 | 42 | 2.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 71000 | 71000 | 305064.5 | 305064.5 | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 76415) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 215000 | 215000 | 256200 | 256200 | -
E052 | Care of Water (Special Provisions) | unit | 1 | 10000 | 10000 | 9000 | 9000 | -
F170 | Demolition and Disposal of Bridge Structure (B.F. 76415) (BCS 21.4.1) | lump sum | 1 | 35000 | 35000 | 81300 | 81300 | -
F186 | Excavation - Structural (B.F. 76415) (BCS 1.6.1) | lump sum | 1 | 18000 | 18000 | 50660 | 50660 | -
F490 | CSP with couplers - Supply (B.F. 76415) (BCS 18.7) | lump sum | 1 | 81000 | 81000 | 100740.5 | 100740.5 | -
F491 | CSP - Assembly (B.F. 76415) (BCS 18.7) | lump sum | 1 | 33000 | 33000 | 17416 | 17416 | -
F190 | Backfill (B.F. 76415) (BCS 2.4) | lump sum | 1 | 50000 | 50000 | 131366 | 131366 | -
F492 | Roadway Work (B.F. 76415) (BCS 18.7) | lump sum | 1 | 110000 | 110000 | 109500 | 109500 | -
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 80 | 500 | 40000 | 607 | 48560 | -
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 30000 | 30000 | 30000 | 30000 | -
F500 | Heavy Rock Riprap (Class 1) (B.F. 76415) (BCS 10.7) | cubic metre | 95 | 330 | 31350 | 225 | 21375 | -
F020 | Rock Lined Ditch Drains - Class 1M (Special Provisions) | metre | 20 | 500 | 10000 | 350 | 7000 | -
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 200 | 15 | 3000 | 5.5 | 1100 | -
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 200 | 10 | 2000 | 19.75 | 3950 | -
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 200 | 10 | 2000 | 5.5 | 1100 | -
|  | Bridge File Modified Tender Value |  |  | 741350 |  | 1174332 | -
|  | Total Tender Value |  |  |  |  | 1225332 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 30 | 45000 | 34 | 51000 | -
Tender: 21132 ¦ Bridge File: 76415-2 ¦ Tender Opening Date: 2024-06-20
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22184 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2024-2025 | 2024-06-26 | 5 | 2025-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74031N-1 | 7 km North of Aldersyde | Southern | 2:12 | Sheep River | 7 x 1200 WG | 32 ¦ 38 ¦ 38 ¦ 32 | 140 | 14
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 153000 | 153000 | 154494.24 | 154494.24 | 20.9%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 225000 | 225000 | 164592.62 | 164592.62 | 13.1%
F755 | Surface Removal - Deck (BCS 20.6.1) | square metre | 1750 | 114 | 199500 | 38.65 | 67637.5 | 47.1%
F022 | ACP Surface Removal - Approaches (Special Provisions) | square metre | 465 | 75 | 34875 | 41.48 | 19288.2 | 57.4%
F760 | Partial Depth Repair - Deck (BCS 20.6.2) | square metre | 50 | 1500 | 75000 | 1360.96 | 68048 | 44.7%
F760 | Partial Depth Repair - Curbs Face and Top (BCS 20.6.2) | square metre | 10 | 2000 | 20000 | 1568.62 | 15686.2 | 73%
F760 | Partial Depth Repair - Curbs Fascia and Soffit (BCS 20.6.2) | square metre | 10 | 2600 | 26000 | 3074.29 | 30742.9 | 47.9%
F760 | Partial Depth Repair - Abutments and Wingwalls (BCS 20.6.2) | square metre | 10 | 2900 | 29000 | 2117.82 | 21178.2 | 37.4%
F760 | Partial Depth Repair - Piers (BCS 20.6.2) | square metre | 10 | 3600 | 36000 | 3263.49 | 32634.9 | 51.8%
F018 | Abutment Bearing Stainless Steel Replacements (Special Provisions) | lump sum | 1 | 150000 | 150000 | 74678.77 | 74678.77 | 27.8%
F993 | Galvanic Corrosion Protection - Supply and Install (Special Provisions) | anodes | 252 | 110 | 27720 | 85.55 | 21558.6 | 14.4%
F018 | Deck Joint Replacements (Special Provisions) | lump sum | 1 | 161600 | 161600 | 255658.22 | 255658.22 | 24.5%
F974 | Waterproofing (BCS 16.5) | square metre | 1842 | 98 | 180516 | 50.67 | 93334.14 | 10.5%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 66 | 80 | 5280 | 59.96 | 3957.36 | 28.6%
F018 | Approach Rail Transitions Upgrading (Special Provisions) | lump sum | 1 | 28000 | 28000 | 45706.03 | 45706.03 | 6.8%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 85 | 230 | 19550 | 226.47 | 19249.95 | 38.9%
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 2 | 6000 | 12000 | 5908.65 | 11817.3 | 6.7%
S830 | Flexible Guide Post/Delineator - Round - Supply and Install (HCS 5.28.3) (HCS 2.19.4) | post | 6 | 200 | 1200 | 135.75 | 814.5 | 56.3%
C055 | Topsoil and Subsoil Stripping (Special Provisions) | cubic metre | 50 | 18 | 900 | 251.27 | 12563.5 | 58%
F203 | Backfill - Crushed Aggregate Des. 2 Class 25 (BCS 2.4) | cubic metre | 70 | 95 | 6650 | 267.28 | 18709.6 | 33%
F150 | Surface Preparation and Painting - Girder Ends and Diaphragms (BCS 22.25.2) | lump sum | 1 | 56000 | 56000 | 171069.85 | 171069.85 | 37.2%
F151 | Protection of the Environment (BCS 22.25.1) | lump sum | 1 | 25000 | 25000 | 47867.8 | 47867.8 | 48.9%
F018 | Drain Trough Modifications (Special Provisions) | lump sum | 1 | 16000 | 16000 | 23591.5 | 23591.5 | 64.6%
F018 | CSE Ground Connections (Special Provisions) | lump sum | 1 | 18000 | 18000 | 16768.05 | 16768.05 | 61.8%
F018 | Concrete Cleaning and Sealing (Special Provisions) | lump sum | 1 | 40000 | 40000 | 22530.83 | 22530.83 | 77.5%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 382 | 390 | 148980 | 469.82 | 179471.24 | 30.1%
|  | Bridge File Modified Tender Value |  |  | 1695771 |  | 1593650 | 13.7%
|  | Total Tender Value |  |  |  |  | 1909151.38 | 12.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy - Bridge Construction (GCS 1.2.41.9) | day | 1500 |  | 0 | 99 | 148500 | 11.5%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 |  | 0 | 111 | 166500 | 10.5%
Tender: 22184 ¦ Bridge File: 74031-1 ¦ Tender Opening Date: 2024-06-26
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23067 | Bridge Rehabilitation | Bridge | Multiple | Bridge Rehabilitation | 2024-2025 | 2024-07-09 | 4 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
9179-1 | 10 km North of Jenner | Central | 884:04 | Red Deer River | Through Truss | 61 ¦ 76 ¦ 61 | 198 | 7.3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 60000 | 60000 | 168456.13 | 168456.13 | 87.2%
F750 | Traffic Accommodation for Bridge Construction - BF 09179 (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 25000 | 25000 | 31982.43 | 31982.43 | 23.2%
F018 | Approach Rail Repairs (Special Provisions) | lump sum | 1 | 20000 | 20000 | 42324.69 | 42324.69 | 60.9%
F018 | Bridgerail Repairs (Special Provisions) | lump sum | 1 | 5000 | 5000 | 27181.17 | 27181.17 | 84.3%
F022 | Patch Timber Strip Deck (Special Provisions) | square metre | 20 | 500 | 10000 | 599.12 | 11982.4 | 19.3%
F018 | Heat Straighten Steel Members (Special Provisions) | lump sum | 1 | 75000 | 75000 | 43121.11 | 43121.11 | 8.1%
F018 | Replace Steel Members (Special Provisions) | lump sum | 1 | 175000 | 175000 | 82533.21 | 82533.21 | 16.9%
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 15000 | 15000 | 18605.94 | 18605.94 | 45.9%
|  | Bridge File Modified Tender Value |  |  | 385000 |  | 426187.08 | 29.3%
|  | Total Tender Value |  |  |  |  | 1574142.33 | 9.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 21 | 31500 | 30.2%
Tender: 23067 ¦ Bridge File: 9179-1 ¦ Tender Opening Date: 2024-07-09
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23067 | Bridge Rehabilitation | Bridge | Multiple | Bridge Rehabilitation | 2024-2025 | 2024-07-09 | 4 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
13170-1 | 5 km North of Buffalo | Central | 886:02 | Red Deer River | Through Truss | 9 ¦ 61 ¦ 61 ¦ 61 ¦ 61 ¦ 9 | 262 | 5.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 150000 | 150000 | 231806.68 | 231806.68 | 48.9%
F750 | Traffic Accommodation for Bridge Construction - BF 13170 (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 25000 | 25000 | 42308.12 | 42308.12 | 9.7%
F018 | Approach Rail Repairs (Special Provisions) | lump sum | 1 | 10000 | 10000 | 34810.6 | 34810.6 | 90.8%
F018 | Bridgerail Repairs (Special Provisions) | lump sum | 1 | 10000 | 10000 | 40858.55 | 40858.55 | 77.8%
F022 | Patch Timber Strip Deck (Special Provisions) | square metre | 25 | 500 | 12500 | 565.48 | 14137 | 11.2%
F018 | Replace Steel Members (Special Provisions) | lump sum | 1 | 175000 | 175000 | 220375.91 | 220375.91 | 46.7%
F906 | Bearings - Supply and Fabrication, Delivery and Installation (BCS 8.5) (Special Provisions) | lump sum | 1 | 250000 | 250000 | 269107.98 | 269107.98 | 9.8%
F018 | Floor Beam Strengthening (Special Provisions) | lump sum | 1 | 160000 | 160000 | 112328.3 | 112328.3 | 36.2%
F020 | Concrete Crack Repairs (Special Provisions) | metre | 60 | 400 | 24000 | 498.61 | 29916.6 | 21.5%
F760 | Partial Depth Repair (BCS 20.6.2) | square metre | 15 | 4000 | 60000 | 2694.94 | 40424.1 | 22.9%
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 15000 | 15000 | 16881.4 | 16881.4 | 33.1%
|  | Bridge File Modified Tender Value |  |  | 891500 |  | 1052955.24 | 15%
|  | Total Tender Value |  |  |  |  | 1574142.33 | 9.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 42 | 63000 | 37.2%
Tender: 23067 ¦ Bridge File: 13170-1 ¦ Tender Opening Date: 2024-07-09
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21891 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Culvert with Bridge | 2024-2025 | 2024-07-11 | 6 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75962-2 | 39 km Southwest of Nordegg | Central | 11:04 | Tributary to North Saskatchewan River | 12 x 510 SLC | 12 ¦ 14 ¦ 12 | 38 | 14.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 450000 | 450000 | 399791 | 399791 | 24%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 300000 | 300000 | 398621.67 | 398621.67 | 27.2%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 30000 | 30000 | 122508.33 | 122508.33 | 102.9%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 1500 | 9000 | 994.33 | 5965.98 | 98.9%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | 212182.67 | 212182.67 | 53.5%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 80000 | 80000 | 438342.67 | 438342.67 | 19%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 250 | 300 | 75000 | 165.33 | 41332.5 | 37%
F819 | Pile Tip Reinforcement (BCS 3.6.1) | pile | 20 | 700 | 14000 | 450.23 | 9004.6 | 59.5%
F816 | Pile Set-up (Driven Piles) - H-Piles (BCS 3.6.1) | pile | 20 | 5000 | 100000 | 3923.67 | 78473.4 | 27%
F818 | Pile Driving - H-Piles (BCS 3.6.1) | metre | 250 | 65 | 16250 | 46.27 | 11567.5 | 116.8%
F815 | Supply of Piling - Galvanized Steel Pipe Pile (BCS 3.6.1) | metre | 144 | 600 | 86400 | 425 | 61200 | 10.7%
F814 | Supply of Piling - Plain Steel Pipe Pile (BCS 3.6.1) | metre | 128 | 500 | 64000 | 341 | 43648 | 5.9%
F824 | Drill Rig Set-up (Drilled Piles) - Pipe Piles (BCS 3.6.2) | pile | 16 | 10000 | 160000 | 13567.67 | 217082.72 | 45.1%
F826 | Pile Installation (Drilled Piles) - Pipe Piles (BCS 3.6.2) | metre | 272 | 400 | 108800 | 85.39 | 23226.08 | 97.2%
F833 | Concrete (Class Tremie) - Supply and Place (B.F.75962) (BCS 4.27.1) (Special Provisions) | cubic metre | 92 | 1000 | 92000 | 1324 | 121808 | 9.4%
F018 | Pier Pipe Pile Bracing (Special Provisions) | lump sum | 1 | 50000 | 50000 | 55103.33 | 55103.33 | 32.5%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 12190 | 3.5 | 42665 | 3.49 | 42543.1 | 24.3%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 22350 | 8 | 178800 | 7.88 | 176118 | 7.3%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 790 | 13 | 10270 | 12.65 | 9993.5 | 2.1%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 35330 | 2.5 | 88325 | 2.51 | 88678.3 | 36.2%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 66 | 2500 | 165000 | 2477.33 | 163503.78 | 18.7%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 105 | 3200 | 336000 | 2837.5 | 297937.5 | 5.8%
F515 | Heavy Rock Riprap (Class 2) (BCS 10.7) | cubic metre | 750 | 250 | 187500 | 318.52 | 238890 | 44%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 12m Type SLC 510 (20 Interior, 4 Exterior) (BCS 7.4) | lump sum | 1 | 720000 | 720000 | 574558.28 | 574558.28 | 31%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 14 m Type SLC 510 (10 Interior, 2 Exterior) (BCS 7.4) | lump sum | 1 | 420000 | 420000 | 389764 | 389764 | 10.3%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 5000 | 5000 | 6166.67 | 6166.67 | 58.4%
F974 | Waterproofing (BCS 16.5) | square metre | 700 | 90 | 63000 | 85.87 | 60109 | 16.1%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) (Bridge) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 135 | 400 | 54000 | 387.42 | 52301.7 | 25.5%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 300000 | 300000 | 539099.67 | 539099.67 | 46.6%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 130000 | 130000 | 75174 | 75174 | 27.8%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 40000 | 40000 | 63710 | 63710 | 25.9%
E020 | Erosion Control Barrier - Straw Rolls (Special Provisions) | metre | 200 | 20 | 4000 | 37.7 | 7540 | 92.8%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 10 | 2000 | 27.68 | 5536 | 79.8%
|  | Bridge File Modified Tender Value |  |  | 4482010 |  | 5031481.95 | 13.7%
|  | Total Tender Value |  |  |  |  | 5199056.31 | 13.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 90 | 135000 | 112 | 168000 | 33.9%
Tender: 21891 ¦ Bridge File: 75962-2 ¦ Tender Opening Date: 2024-07-11
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23808 | Construct CSP Culvert | Culvert | Single | Replace Bridge with Culvert | 2024-2025 | 2024-07-19 | 3 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75540-2 | 1 km Southwest of Acadia Valley | Central | 41:10 | Kennedy Coulee | 3 x 1800 CSP | 32 - 32 - 32 | 96 | 1.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 80000 | 80000 | 180935.25 | 180935.25 | 31.2%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 25000 | 25000 | 89010 | 89010 | 34.7%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 20000 | 20000 | 21508.33 | 21508.33 | 54.3%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 75000 | 75000 | 33970.63 | 33970.63 | 30.5%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 50000 | 50000 | 87605.42 | 87605.42 | 80.6%
F495 | CSP with Couplers - Supply (1.8 m Dia.) (BCS 18.7) | metre | 96 | 900 | 86400 | 821.75 | 78888 | 4.8%
F496 | CSP - Assembly (1.8 m Dia.) (BCS 18.7) | metre | 96 | 300 | 28800 | 284.48 | 27310.08 | 15.3%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 100000 | 100000 | 212828.33 | 212828.33 | 18.5%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 90 | 300 | 27000 | 232.43 | 20918.7 | 10.7%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 250000 | 250000 | 206320.83 | 206320.83 | 33.6%
F018 | Removal and Transport Detour Bridge (Special Provisions) | lump sum | 1 | 20000 | 20000 | 32436.67 | 32436.67 | 55.2%
F018 | Removal of Detour Road and Site Restoration (Special Provisions) | lump sum | 1 | 60000 | 60000 | 116425.83 | 116425.83 | 5.6%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 200 | 20 | 4000 | 25.94 | 5188 | 21.9%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 10 | 2000 | 31.73 | 6346 | 47.1%
|  | Bridge File Modified Tender Value |  |  | 828200 |  | 1119692.07 | 6.3%
|  | Total Tender Value |  |  |  |  | 1174693.43 | 4.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 45 | 67500 | 37 | 55500 | 39.7%
Tender: 23808 ¦ Bridge File: 75540-2 ¦ Tender Opening Date: 2024-07-19
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22126 | Construct CSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2024-2025 | 2024-08-28 | 4 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76979-2 | 42 km South of Irvine | Southern | 514:02 | Gros Ventre Creek | 2 x 1400 CSP | 27 - 27 | 54 | 1.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 32000 | 32000 | 58208.33 | 58208.33 | 15.8%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 40000 | 40000 | 52435 | 52435 | 92.1%
E612 | Fish Capture and Release (Special Provisions) | day | 1 | 3500 | 3500 | 1366.67 | 1366.67 | 111%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 650 | 3900 | 833.33 | 4999.98 | 102%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 20000 | 20000 | 30800 | 30800 | 45.1%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 48123.33 | 48123.33 | 57%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 2000 | 2000 | 7900 | 7900 | 85.9%
F495 | CSP with Couplers - Supply (BCS 18.7) | metre | 54 | 1400 | 75600 | 674.09 | 36400.86 | 24.6%
F496 | CSP - Assembly (BCS 18.7) | metre | 54 | 600 | 32400 | 503.33 | 27179.82 | 97.4%
F204 | Backfill - Crushed Aggregate (BCS 2.4) | lump sum | 1 | 35000 | 35000 | 60866.67 | 60866.67 | 37.1%
F196 | Backfill - Non-Granular (BCS 2.4) | lump sum | 1 | 27500 | 27500 | 20466.67 | 20466.67 | 27.1%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 50 | 320 | 16000 | 284.33 | 14216.5 | 17.1%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 30000 | 30000 | 39500 | 39500 | 32.6%
|  | Bridge File Modified Tender Value |  |  | 342900 |  | 402463.83 | 21.1%
|  | Total Tender Value |  |  |  |  | 456964.01 | 17.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 16 | 24000 | 19 | 28500 | 9.9%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 20 | 30000 | 18 | 27000 | 11.4%
Tender: 22126 ¦ Bridge File: 76979-2 ¦ Tender Opening Date: 2024-08-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22021 | Replace Bridge Approach Slabs | Bridge | Highway | Bridge Maintenance | 2024-2025 | 2024-09-05 | 2 | 2025-11-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
1980-1 | At Sundre | Central | 27:06 | Red Deer River | 7 x 1550 Type-O | 31 ¦ 31 ¦ 31 ¦ 31 | 124 | 12.2
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 17237.25 | 17237.25 | 24441.17 | 24441.17 | -
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 14501.06 | 14501.06 | 15897.97 | 15897.97 | -
F022 | Bridge Approach Slab - Remove and Dispose (Special Provisions) | square metre | 17 | 3000 | 51000 | 2900.67 | 49311.39 | -
F853 | Stainless Reinforcing Steel - Supply (B.F.1980) (BCS 5.6) | kilogram | 340 | 18 | 6120 | 20.67 | 7027.8 | -
F854 | Reinforcing Steel - Place (B.F. 1980) (BCS 5.6) | kilogram | 340 | 20 | 6800 | 13.92 | 4732.8 | -
F841 | Concrete (Class HPC) - Supply and Place (B.F. 1980) (BCS 4.27.1) | cubic metre | 3.5 | 10000 | 35000 | 11676.27 | 40866.95 | -
F018 | Bridge Rail to Guardrail Connection (Special Provisions) | lump sum | 1 | 30000 | 30000 | 15019.18 | 15019.18 | -
|  | Bridge File Modified Tender Value |  |  | 160658.31 |  | 157297.26 | -
|  | Total Tender Value |  |  |  |  | 9118024.64 | -
Tender: 22021 ¦ Bridge File: 1980-1 ¦ Tender Opening Date: 2024-09-05
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23103 | Construct WSP Culvert - Install WSP Culvert Liner | Culvert | Single | New and Lined Culverts | 2024-2025 | 2024-09-05 | 2 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
70872-2 | 31 km Northeast of Hinton | North Central | 16:04 | Rooster Creek | 1 x 2430 WSP - 1 x 1220 WSP Liner | 143 - 136 | 279 | 1.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 375000 | 375000 | 494000 | 494000 | -
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 30000 | 30000 | 32500 | 32500 | -
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 15 | 1000 | 15000 | 1300 | 19500 | -
F018 | Silt, Debris and Ice Removal (Special Provisions) | lump sum | 1 | 20000 | 20000 | 22500 | 22500 | -
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 30000 | 30000 | 55000 | 55000 | -
F018 | Shoring and Boring Pit Preparation (Special Provisions) | lump sum | 1 | 125000 | 125000 | 40000 | 40000 | -
F027 | Welded Steel Pipe - Supply (Special Provisions) | metre | 143 | 7500 | 1072500 | 9500 | 1358500 | -
F027 | Welded Steel Pipe - Install (Special Provisions) | metre | 143 | 10000 | 1430000 | 9500 | 1358500 | -
F018 | Culvert Liner - Supply (Special Provisions) | lump sum | 1 | 220000 | 220000 | 97500 | 97500 | -
F018 | Culvert Liner - Install (Special Provisions) | lump sum | 1 | 50000 | 50000 | 258250 | 258250 | -
F021 | Concrete - Class S Modified (Special Provisions) | cubic metre | 140 | 2000 | 280000 | 1350 | 189000 | -
F190 | Backfill (BCS 2.4) | lump sum | 1 | 35000 | 35000 | 90000 | 90000 | -
F018 | Supply and Install Substrate and Substrate Holders (Special Provisions) | lump sum | 1 | 100000 | 100000 | 80000 | 80000 | -
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 130 | 300 | 39000 | 400 | 52000 | -
F515 | Heavy Rock Riprap (Class 2) (BCS 10.7) | cubic metre | 235 | 350 | 82250 | 450 | 105750 | -
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 30000 | 30000 | 32500 | 32500 | -
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 250 | 15 | 3750 | 17.5 | 4375 | -
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 150 | 15 | 2250 | 22.5 | 3375 | -
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 60 | 15 | 900 | 12.5 | 750 | -
E020 | Rock Ditch Drains - Class 1M (Special Provisions) | metre | 125 | 400 | 50000 | 700 | 87500 | -
E018 | Miscellaneous Environmental Work (Special Provisions) | lump sum | 1 | 50000 | 50000 | 87500 | 87500 | -
|  | Bridge File Modified Tender Value |  |  | 4040650 |  | 4469000 | -
|  | Total Tender Value |  |  |  |  | 4596500 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 85 | 127500 | -
Tender: 23103 ¦ Bridge File: 70872-2 ¦ Tender Opening Date: 2024-09-05
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22337 | Construct SWSP Culvert | Culvert | Single | Replace Bridge with Culvert | 2024-2025 | 2024-09-19 | 4 | 2025-03-14
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76641-2 | 43 km Northeast of Swan Hills | Peace | 33:14 | Tributary to Swan River | 1 x 2130 SWSP | 146 | 146 | 2.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 236000 | 236000 | 328333.33 | 328333.33 | 28.5%
F750 | Traffic Accommodation for Bridge Construction (B.F. 76641) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 20000 | 20000 | 50000 | 50000 | 77.9%
X041 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1500 | 15000 | 900 | 9000 | 125.7%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 50000 | 50000 | 99333.33 | 99333.33 | 40.3%
E018 | Fish Capture and Release (Special Provisions) | lump sum | 1 | 5000 | 5000 | 2500 | 2500 | 71.2%
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) (Special Provisions) | cubic metre | 365 | 800 | 292000 | 582.67 | 212674.55 | 20.3%
F187 | Excavation - Channel (B.F. 76641) (BCS 1.6.1) (Special Provisions) | lump sum | 1 | 45000 | 45000 | 67500 | 67500 | 34.1%
F196 | Backfill - Non-Granular (B.F. 76641) (BCS 2.4) (Special Provisions) | lump sum | 1 | 35000 | 35000 | 44833.33 | 44833.33 | 87.2%
F027 | Smooth Wall Steel Pipe - Supply (2134 mm dia.) (Special Provisions) | metre | 146 | 5000 | 730000 | 7039.67 | 1027791.82 | 19.7%
F020 | Smooth Wall Steel Pipe - Install (2134 mm dia.) (Special Provisions) | metre | 146 | 5200 | 759200 | 10720 | 1565120 | 13.3%
F715 | Substrate Holders - Steel (B.F.76641) (BCS 18.7) (BCS 18.7) (Special Provisions) | unit | 25 | 1800 | 45000 | 1450 | 36250 | 77.8%
F021 | Substrate (Class 1M) (Special Provisions) | cubic metre | 30 | 420 | 12600 | 828.67 | 24860.1 | 36.8%
F500 | Heavy Rock Riprap (Class 1) (B.F. 76641) (BCS 10.7) (BCS 10.7) (Special Provisions) | cubic metre | 250 | 450 | 112500 | 330 | 82500 | 15.1%
F018 | Culvert Embankment and Berm Construction (Special Provisions) | lump sum | 1 | 20000 | 20000 | 52666.67 | 52666.67 | 22%
F492 | Roadway Work - Channel Restoration (B.F. 76641) (BCS 18.7) (Special Provisions) | lump sum | 1 | 95000 | 95000 | 36000 | 36000 | 37.1%
F515 | Heavy Rock Riprap (Class 2) - Removal, Salvage and Placement of Class 2 Heavy Rock Riprap (BCS 10.7) (Special Provisions) | cubic metre | 50 | 150 | 7500 | 241.67 | 12083.5 | 27.2%
E052 | Willow Plantings - Supply and Plant (Special Provisions) | unit | 150 | 75 | 11250 | 80 | 12000 | 62.1%
F970 | Miscellaneous Iron (BCS 13.5) (Special Provisions) | lump sum | 1 | 2500 | 2500 | 5500 | 5500 | 63.4%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 450 | 20 | 9000 | 36.67 | 16501.5 | 34%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 380 | 120 | 45600 | 191.67 | 72834.6 | 22.2%
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 4 | 5170 | 20680 | 6166.67 | 24666.68 | 16.7%
S830 | Flexible Guide Post/Delineator - Round - Supply and Install (HCS 5.28.3) (HCS 2.19.4) | post | 12 | 60 | 720 | 121.67 | 1460.04 | 40.6%
E018 | Clearing, Topsoil and Seeding (Special Provisions) | lump sum | 1 | 20000 | 20000 | 37666.67 | 37666.67 | 27.1%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 300 | 20 | 6000 | 20.5 | 6150 | 17%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) (Special Provisions) | square metre | 400 | 19 | 7600 | 13.33 | 5332 | 17.7%
|  | Bridge File Modified Tender Value |  |  | 2603150 |  | 3833558.12 | 4.9%
|  | Total Tender Value |  |  |  |  | 3978554.67 | 5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 45 | 67500 | 97 | 145500 | 8.8%
Tender: 22337 ¦ Bridge File: 76641-2 ¦ Tender Opening Date: 2024-09-19
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22124 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2024-2025 | 2024-09-24 | 5 | 2025-06-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
6780E-3 | Near Coaldale | Southern | 3:10 | SMRID Canal | 11 x 510 SLC | 12 ¦ 14 ¦ 12 | 38 | 13.5
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 305000 | 305000 | 304081.4 | 304081.4 | 41.4%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 75000 | 75000 | 325264.84 | 325264.84 | 30.7%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 225000 | 225000 | 376004.61 | 376004.61 | 65%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 10000 | 10000 | 90082.43 | 90082.43 | 124%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 50000 | 50000 | 50530.4 | 50530.4 | 31.4%
F196 | Backfill - Non-Granular (BCS 2.4) | lump sum | 1 | 5000 | 5000 | 7974.78 | 7974.78 | 28.9%
F204 | Backfill - Crushed Aggregate (BCS 2.4) | lump sum | 1 | 10000 | 10000 | 29875.29 | 29875.29 | 46.8%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 457 | 185 | 84545 | 129.87 | 59350.59 | 48.1%
F815 | Supply of Piling - Galvanized Steel Pipe Pile (BCS 3.6.1) | metre | 350 | 532 | 186200 | 264.7 | 92645 | 56.3%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 32 | 4500 | 144000 | 8337.11 | 266787.52 | 39.1%
F818 | Pile Driving (BCS 3.6.1) | metre | 807 | 60 | 48420 | 26.3 | 21224.1 | 67.6%
F819 | Pile Tip Reinforcement (BCS 3.6.1) | pile | 32 | 300 | 9600 | 503.18 | 16101.76 | 33.7%
F820 | PDA Testing (BCS 3.6.4) | test | 6 | 2000 | 12000 | 2466.81 | 14800.86 | 56.6%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 10826 | 2.75 | 29771.5 | 2.4 | 25982.4 | 10.8%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 18195 | 6.8 | 123726 | 7.04 | 128092.8 | 8.8%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 564 | 13.25 | 7473 | 16.44 | 9272.16 | 9.7%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 29585 | 2.5 | 73962.5 | 2.18 | 64495.3 | 7.1%
F822 | Pile Concrete (Class) - Supply and Place (BCS 4.27.1) | cubic metre | 103 | 850 | 87550 | 770.55 | 79366.65 | 19.8%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 55 | 1775 | 97625 | 4975.76 | 273666.8 | 26.2%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 106 | 2100 | 222600 | 2836.2 | 300637.2 | 16.6%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) | lump sum | 1 | 950000 | 950000 | 767763.52 | 767763.52 | 6.3%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 30000 | 30000 | 48687.75 | 48687.75 | 48.7%
F906 | Bearings - Supply and Fabrication, Delivery and Installation (BCS 8.5) | lump sum | 1 | 20000 | 20000 | 29792.23 | 29792.23 | 21%
F974 | Waterproofing (BCS 16.5) | square metre | 639 | 65 | 41535 | 81.64 | 52167.96 | 16.6%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 524 | 250 | 131000 | 195.73 | 102562.52 | 8.4%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 75000 | 75000 | 91065.86 | 91065.86 | 11.6%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 207 | 175 | 36225 | 205 | 42435 | 25.7%
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 2 | 6250 | 12500 | 5801.46 | 11602.92 | 16.7%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 227 | 37 | 8399 | 36.93 | 8383.11 | 29.9%
G270 | Sideslope Improvement (HCS 3.60.4) | kilometre | 0.2 | 200000 | 40000 | 75852.78 | 15170.56 | 64.7%
S830 | Flexible Guide Post/Delineator - Round - Supply and Install (HCS 5.28.3) (HCS 2.19.4) | post | 8 | 60 | 480 | 164.89 | 1319.12 | 68.2%
X510 | Cutting of Pavement (HCS 3.40.3) | metre | 32 | 100 | 3200 | 52.58 | 1682.56 | 31%
Q565 | Cold Milling Asphalt Pavement (HCS 3.16.6) | square metre | 1895 | 9 | 17055 | 14.86 | 28159.7 | 29.4%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 350 | 400 | 140000 | 238.72 | 83552 | 12.9%
S350 | Roadway Lines - Supplying Paint and Painting (Directional Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.2 | 50000 | 10000 | 31812.9 | 6362.58 | 62%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 180 | 30 | 5400 | 26.05 | 4689 | 38.7%
G300 | Topsoil Placement (HCS 2.6.4) | square metre | 3000 | 2.75 | 8250 | 3.07 | 9210 | 57.5%
C232 | Hydroseeding (HCS 2.20.4) | square metre | 3000 | 5.25 | 15750 | 3.31 | 9930 | 47.6%
|  | Bridge File Modified Tender Value |  |  | 3352267 |  | 3850773.28 | 8.4%
|  | Total Tender Value |  |  |  |  | 4390837.33 | 6.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 90 | 135000 | 155 | 232500 | 7.2%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 105 | 157500 | 205 | 307500 | 9.1%
Tender: 22124 ¦ Bridge File: 6780-3 ¦ Tender Opening Date: 2024-09-24
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
19889 | Replace Superstructure Welded Steel Girder Bridge | Bridge | Multiple | Bridge Rehabilitation | 2024-2025 | 2024-10-16 | 2 | 2026-08-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75195E-1 | 2 km North of Carvel | North Central | 16:12 | Highway 43 | 8 x 600 WG | 14 ¦ 24 ¦ 17 | 55 | 13.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 750000 | 750000 | 579500 | 579500 | -
F750 | PRORATED - Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 1250000 | 1250000 | 1000000 | 1000000 | -
F018 | PRORATED - Care of Birds (Special Provisions) | lump sum | 1 | 25000 | 25000 | 14615 | 14615 | -
F018 | PRORATED - Demolition and Disposal of Bridge Structures - Stage 2 (Special Provisions) | lump sum | 1 | 1000000 | 1000000 | 487700 | 487700 | -
F018 | PRORATED - Headslope Modifications (Special Provisions) | lump sum | 1 | 250000 | 250000 | 353500 | 353500 | -
F595 | Concrete Slope Protection (BCS 4.27.2) | square metre | 690 | 475 | 327750 | 227.5 | 156975 | -
F020 | Epoxy Crack Injection (Special Provisions) | metre | 40 | 500 | 20000 | 311 | 12440 | -
F760 | Partial Depth Repair - Piers (BCS 20.6.2) | square metre | 7.5 | 1500 | 11250 | 2050 | 15375 | -
F018 | PRORATED - Pier Modifications (Special Provisions) | lump sum | 1 | 200000 | 200000 | 200450 | 200450 | -
F022 | Galvanic Corrosion Protection (Special Provisions) | square metre | 53.5 | 420 | 22470 | 317.5 | 16986.25 | -
F190 | PRORATED - Backfill - Des 2 Class 25 (BCS 2.4) | lump sum | 1 | 150000 | 150000 | 137962.5 | 137962.5 | -
F186 | PRORATED - Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 300000 | 300000 | 68747.5 | 68747.5 | -
F834 | Concrete (Class C) - Supply and Place - Modified (BCS 4.27.1) | cubic metre | 41.5 | 2200 | 91300 | 3400 | 141100 | -
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 83.5 | 1500 | 125250 | 2300 | 192050 | -
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 256.5 | 2500 | 641250 | 3350 | 859275 | -
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 9919 | 4 | 39676 | 2.7 | 26781.3 | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 43725 | 9 | 393525 | 8.2 | 358545 | -
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1183.5 | 12 | 14202 | 14.5 | 17160.75 | -
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 54827.5 | 2.5 | 137068.75 | 2 | 109655 | -
F906 | PRORATED - Bearings - Supply and Fabrication, Delivery and Installation (BCS 8.5) | lump sum | 1 | 105000 | 105000 | 338125 | 338125 | -
F903 | PRORATED - Structural Steel - Supply and Fabrication, Delivery and Erection (BCS 6.4.1) | lump sum | 1 | 1200000 | 1200000 | 1801250 | 1801250 | -
F781 | PRORATED - Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 110000 | 110000 | 135212.5 | 135212.5 | -
F022 | Deck Surface Preparation (Special Provisions) | square metre | 856 | 25 | 21400 | 15.25 | 13054 | -
F018 | PRORATED - Deck Surface Testing and Inspection (Special Provisions) | lump sum | 1 | 5000 | 5000 | 4162.5 | 4162.5 | -
F974 | Waterproofing (BCS 16.5) | square metre | 856 | 320 | 273920 | 247.5 | 211860 | -
F911 | Drain Troughs (BCS 9.7) (Special Provisions) | metre | 19 | 700 | 13300 | 837.5 | 15912.5 | -
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 127 | 350 | 44450 | 442.5 | 56197.5 | -
F970 | PRORATED - Miscellaneous Iron (BCS 13.5) (Special Provisions) | lump sum | 1 | 3000 | 3000 | 14457.5 | 14457.5 | -
F020 | Hwy 43 Concrete Gutters (Special Provisions) | metre | 80 | 200 | 16000 | 661.5 | 52920 | -
Q554 | Cold Milling Asphalt Pavement - 65 <mm Depth> (HCS 3.16.6) (Special Provisions) | square metre | 4395 | 5 | 21975 | 10 | 43950 | -
Q991 | Asphalt Concrete Pavement - EPS Mix Type H2 (PG 58-28) (HCS 5.2.5) (HCS 3.50.7) | tonne | 1447.5 | 120 | 173700 | 240 | 347400 | -
X020 | Granular Base Course Widening to Accommodate Pavement Overlay (GBC Des 2 Class 25) (Special Provisions) | metre | 567.5 | 50 | 28375 | 187.5 | 106406.25 | -
S820 | Remove, Salvage and Reinstall Existing Guardrail (HCS 2.19.4) (Special Provisions) | metre | 302.5 | 85 | 25712.5 | 128.5 | 38871.25 | -
S822 | Supply of Guardrail Posts (HCS 2.19.4) (Special Provisions) | post | 15 | 185 | 2775 | 204.5 | 3067.5 | -
X020 | Remove, Salvage and Reinstall Existing Guardrail - Median (Special Provisions) | metre | 71 | 150 | 10650 | 335 | 23785 | -
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) (Special Provisions) | metre | 100 | 20 | 2000 | 48.85 | 4885 | -
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) (Special Provisions) | metre | 170.5 | 130 | 22165 | 260 | 44330 | -
X020 | Roadway Lines - Supplying Paint and Painting Type III (Single Solid Yellow) (HCS 7.2.6) | metre | 442.5 | 2 | 885 | 3.5 | 1548.75 | -
X020 | Roadway Lines - Supplying Paint and Painting Type V (Single Solid White) (HCS 7.2.6) | metre | 437.5 | 2 | 875 | 3.5 | 1531.25 | -
X020 | Roadway Lines - Supplying Paint and Painting Type VIII (Single Broken White (3:3) Continuity Lines Right and Left Turn) (HCS 7.2.6) | metre | 477.5 | 2 | 955 | 3.5 | 1671.25 | -
D020 | Smooth Wall Steel Pipe - Supply and Install (400 mm dia.) (HCS 5.22.4) (Special Provisions) | metre | 13 | 1300 | 16900 | 1535 | 19955 | -
D020 | Smooth Wall Steel Pipe - Supply and Install (450 mm dia.) (HCS 5.22.4) (Special Provisions) | metre | 15 | 1350 | 20250 | 1585 | 23775 | -
D505 | Smooth Wall Steel Pipe - Supply and Install (500 mm dia.) (Special Provisions) | metre | 22.5 | 1400 | 31500 | 1585 | 35662.5 | -
D510 | Smooth Wall Steel Pipe - Supply and Install (600 mm dia.) (HCS 5.22.4) (Special Provisions) | metre | 34.5 | 1750 | 60375 | 1747.5 | 60288.75 | -
D430 | Culverts - Supply and Install (900 mm dia. C.S.P.) (HCS 2.4.4) (HCS 5.23.4) (Special Provisions) | metre | 57.5 | 805 | 46287.5 | 1097.5 | 63106.25 | -
D110 | Culverts - Remove and Dispose (HCS 2.4.4) | metre | 47.5 | 160 | 7600 | 125 | 5937.5 | -
D435 | Culverts - Supply and Install (1 200 mm dia. C.S.P.) (HCS 2.4.4) (HCS 5.23.4) (Special Provisions) | metre | 47.5 | 1150 | 54625 | 1500 | 71250 | -
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 22.5 | 760 | 17100 | 666 | 14985 | -
D100 | Culverts - Remove and Dispose (C.S.P.) (up to 700 mm dia.) (HCS 2.4.4) | metre | 15 | 120 | 1800 | 319.5 | 4792.5 | -
D105 | Culverts - Remove and Dispose (C.S.P.) (over 700 mm dia.) (HCS 2.4.4) | metre | 45 | 182 | 8190 | 128 | 5760 | -
D020 | Ditch Re-grading (Special Provisions) | metre | 485 | 100 | 48500 | 65.75 | 31888.75 | -
D022 | Slope Improvement and Erosion Repair (Special Provisions) | square metre | 350 | 50 | 17500 | 63.75 | 22312.5 | -
|  | Bridge File Modified Tender Value |  |  | 8161506.75 |  | 8369129.8 | -
|  | Total Tender Value |  |  |  |  | 18374409.6 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy - Bridge Construction (GCS 1.2.41.9) (Special Provisions) | day | 1500 | - | - | 189 | 283500 | -
F003 | Lane Closure for Bridge Construction - Hwy 16 (GCS 1.2.42.5) (Special Provisions) | day | 2000 | - | - | 260 | 520000 | -
F003 | Lane Closure for Bridge Construction - Hwy 43 (GCS 1.2.42.5) (Special Provisions) | day | 2000 | - | - | 9 | 18000 | -
Tender: 19889 ¦ Bridge File: 75195-1 ¦ Tender Opening Date: 2024-10-16
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
19889 | Replace Superstructure Welded Steel Girder Bridge | Bridge | Multiple | Bridge Rehabilitation | 2024-2025 | 2024-10-16 | 2 | 2026-08-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75195W-2 | 2 km North of Carvel | North Central | 16:12 | Highway 43 | 8 x 600 WG | 14 ¦ 24 ¦ 17 | 55 | 13.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 750000 | 750000 | 579500 | 579500 | -
F750 | PRORATED - Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 1250000 | 1250000 | 1000000 | 1000000 | -
F018 | PRORATED - Care of Birds (Special Provisions) | lump sum | 1 | 25000 | 25000 | 14615 | 14615 | -
F018 | Demolition and Disposal of Bridge Structures - Stage 1 (Special Provisions) | lump sum | 1 | 1000000 | 1000000 | 482600 | 482600 | -
F018 | PRORATED - Headslope Modifications (Special Provisions) | lump sum | 1 | 250000 | 250000 | 353500 | 353500 | -
F595 | Concrete Slope Protection (BCS 4.27.2) | square metre | 690 | 475 | 327750 | 227.5 | 156975 | -
F020 | Epoxy Crack Injection (Special Provisions) | metre | 40 | 500 | 20000 | 311 | 12440 | -
F760 | Partial Depth Repair - Piers (BCS 20.6.2) | square metre | 7.5 | 1500 | 11250 | 2050 | 15375 | -
F018 | PRORATED - Pier Modifications (Special Provisions) | lump sum | 1 | 200000 | 200000 | 200450 | 200450 | -
F022 | Galvanic Corrosion Protection (Special Provisions) | square metre | 53.5 | 420 | 22470 | 317.5 | 16986.25 | -
F190 | PRORATED - Backfill - Des 2 Class 25 (BCS 2.4) | lump sum | 1 | 150000 | 150000 | 137962.5 | 137962.5 | -
F186 | PRORATED - Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 300000 | 300000 | 68747.5 | 68747.5 | -
F834 | Concrete (Class C) - Supply and Place - Modified (BCS 4.27.1) | cubic metre | 41.5 | 2200 | 91300 | 3400 | 141100 | -
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 83.5 | 1500 | 125250 | 2300 | 192050 | -
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 256.5 | 2500 | 641250 | 3350 | 859275 | -
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 9919 | 4 | 39676 | 2.7 | 26781.3 | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 43725 | 9 | 393525 | 8.2 | 358545 | -
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1183.5 | 12 | 14202 | 14.5 | 17160.75 | -
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 54827.5 | 2.5 | 137068.75 | 2 | 109655 | -
F906 | PRORATED - Bearings - Supply and Fabrication, Delivery and Installation (BCS 8.5) | lump sum | 1 | 105000 | 105000 | 338125 | 338125 | -
F903 | PRORATED - Structural Steel - Supply and Fabrication, Delivery and Erection (BCS 6.4.1) | lump sum | 1 | 1200000 | 1200000 | 1801250 | 1801250 | -
F781 | PRORATED - Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 110000 | 110000 | 135212.5 | 135212.5 | -
F022 | Deck Surface Preparation (Special Provisions) | square metre | 856 | 25 | 21400 | 15.25 | 13054 | -
F018 | PRORATED - Deck Surface Testing and Inspection (Special Provisions) | lump sum | 1 | 5000 | 5000 | 4162.5 | 4162.5 | -
F974 | Waterproofing (BCS 16.5) | square metre | 856 | 320 | 273920 | 247.5 | 211860 | -
F911 | Drain Troughs (BCS 9.7) (Special Provisions) | metre | 19 | 700 | 13300 | 837.5 | 15912.5 | -
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 127 | 350 | 44450 | 442.5 | 56197.5 | -
F970 | PRORATED - Miscellaneous Iron (BCS 13.5) (Special Provisions) | lump sum | 1 | 3000 | 3000 | 14457.5 | 14457.5 | -
F020 | Hwy 43 Concrete Gutters (Special Provisions) | metre | 80 | 200 | 16000 | 661.5 | 52920 | -
Q554 | Cold Milling Asphalt Pavement - 65 <mm Depth> (HCS 3.16.6) (Special Provisions) | square metre | 4395 | 5 | 21975 | 10 | 43950 | -
Q991 | Asphalt Concrete Pavement - EPS Mix Type H2 (PG 58-28) (HCS 5.2.5) (HCS 3.50.7) | tonne | 1447.5 | 120 | 173700 | 240 | 347400 | -
X020 | Granular Base Course Widening to Accommodate Pavement Overlay (GBC Des 2 Class 25) (Special Provisions) | metre | 567.5 | 50 | 28375 | 187.5 | 106406.25 | -
S820 | Remove, Salvage and Reinstall Existing Guardrail (HCS 2.19.4) (Special Provisions) | metre | 302.5 | 85 | 25712.5 | 128.5 | 38871.25 | -
S822 | Supply of Guardrail Posts (HCS 2.19.4) (Special Provisions) | post | 15 | 185 | 2775 | 204.5 | 3067.5 | -
X020 | Remove, Salvage and Reinstall Existing Guardrail - Median (Special Provisions) | metre | 71 | 150 | 10650 | 335 | 23785 | -
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) (Special Provisions) | metre | 100 | 20 | 2000 | 48.85 | 4885 | -
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) (Special Provisions) | metre | 170.5 | 130 | 22165 | 260 | 44330 | -
X020 | Roadway Lines - Supplying Paint and Painting Type III (Single Solid Yellow) (HCS 7.2.6) | metre | 442.5 | 2 | 885 | 3.5 | 1548.75 | -
X020 | Roadway Lines - Supplying Paint and Painting Type V (Single Solid White) (HCS 7.2.6) | metre | 437.5 | 2 | 875 | 3.5 | 1531.25 | -
X020 | Roadway Lines - Supplying Paint and Painting Type VIII (Single Broken White (3:3) Continuity Lines Right and Left Turn) (HCS 7.2.6) | metre | 477.5 | 2 | 955 | 3.5 | 1671.25 | -
D020 | Smooth Wall Steel Pipe - Supply and Install (400 mm dia.) (HCS 5.22.4) (Special Provisions) | metre | 13 | 1300 | 16900 | 1535 | 19955 | -
D020 | Smooth Wall Steel Pipe - Supply and Install (450 mm dia.) (HCS 5.22.4) (Special Provisions) | metre | 15 | 1350 | 20250 | 1585 | 23775 | -
D505 | Smooth Wall Steel Pipe - Supply and Install (500 mm dia.) (Special Provisions) | metre | 22.5 | 1400 | 31500 | 1585 | 35662.5 | -
D510 | Smooth Wall Steel Pipe - Supply and Install (600 mm dia.) (HCS 5.22.4) (Special Provisions) | metre | 34.5 | 1750 | 60375 | 1747.5 | 60288.75 | -
D430 | Culverts - Supply and Install (900 mm dia. C.S.P.) (HCS 2.4.4) (HCS 5.23.4) (Special Provisions) | metre | 57.5 | 805 | 46287.5 | 1097.5 | 63106.25 | -
D110 | Culverts - Remove and Dispose (HCS 2.4.4) | metre | 47.5 | 160 | 7600 | 125 | 5937.5 | -
D435 | Culverts - Supply and Install (1 200 mm dia. C.S.P.) (HCS 2.4.4) (HCS 5.23.4) (Special Provisions) | metre | 47.5 | 1150 | 54625 | 1500 | 71250 | -
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 22.5 | 760 | 17100 | 666 | 14985 | -
D100 | Culverts - Remove and Dispose (C.S.P.) (up to 700 mm dia.) (HCS 2.4.4) | metre | 15 | 120 | 1800 | 319.5 | 4792.5 | -
D105 | Culverts - Remove and Dispose (C.S.P.) (over 700 mm dia.) (HCS 2.4.4) | metre | 45 | 182 | 8190 | 128 | 5760 | -
D020 | Ditch Re-grading (Special Provisions) | metre | 485 | 100 | 48500 | 65.75 | 31888.75 | -
D022 | Slope Improvement and Erosion Repair (Special Provisions) | square metre | 350 | 50 | 17500 | 63.75 | 22312.5 | -
|  | Bridge File Modified Tender Value |  |  | 8161506.75 |  | 8364029.8 | -
|  | Total Tender Value |  |  |  |  | 18374409.6 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy - Bridge Construction (GCS 1.2.41.9) (Special Provisions) | day | 1500 | - | - | 189 | 283500 | -
F003 | Lane Closure for Bridge Construction - Hwy 16 (GCS 1.2.42.5) (Special Provisions) | day | 2000 | - | - | 260 | 520000 | -
F003 | Lane Closure for Bridge Construction - Hwy 43 (GCS 1.2.42.5) (Special Provisions) | day | 2000 | - | - | 9 | 18000 | -
Tender: 19889 ¦ Bridge File: 75195-2 ¦ Tender Opening Date: 2024-10-16
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22843 | Construct WSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2024-2025 | 2024-11-28 | 8 | 2025-10-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
73852-2 | 8 km Southwest of Onoway | North Central | 43:22 | Tributary to Kilini Creek | 1 x 2130 WSP | 78 | 78 | 2.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 120000 | 120000 | 136951.67 | 136951.67 | 7.3%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 25000 | 25000 | 23431.67 | 23431.67 | 41.7%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1000 | 10000 | 1390.5 | 13905 | 65.7%
F018 | Silt, Debris and Ice Removal (Special Provisions) | lump sum | 1 | 35000 | 35000 | 11998.33 | 11998.33 | 39.3%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 35000 | 35000 | 13572.67 | 13572.67 | 21.9%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 10000 | 10000 | 15102.33 | 15102.33 | 48.9%
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 174 | 800 | 139200 | 555.23 | 96610.02 | 3.2%
F027 | Welded Steel Pipe - Supply (Special Provisions) | metre | 78 | 5500 | 429000 | 3414.8 | 266354.4 | 17.4%
F027 | Welded Steel Pipe - Install (Special Provisions) | metre | 78 | 5500 | 429000 | 5385.81 | 420093.18 | 14.9%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 15000 | 15000 | 51508 | 51508 | 58.9%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 75 | 400 | 30000 | 578.9 | 43417.5 | 47.9%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 25000 | 25000 | 36369.33 | 36369.33 | 51.5%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 300 | 15 | 4500 | 22.63 | 6789 | 81%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 130 | 15 | 1950 | 39.3 | 5109 | 113.6%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 325 | 15 | 4875 | 13.49 | 4384.25 | 74.4%
E020 | Rock Ditch Drains - Class 1m (Special Provisions) | metre | 5 | 400 | 2000 | 2290.4 | 11452 | 77%
|  | Bridge File Modified Tender Value |  |  | 1315525 |  | 1157048.35 | 9.6%
|  | Total Tender Value |  |  |  |  | 1245045.83 | 11.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 59 | 88500 | 37.6%
Tender: 22843 ¦ Bridge File: 73852-2 ¦ Tender Opening Date: 2024-11-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24780 | Construct SWSP Culvert - Install SWSP Culvert Liner | Culvert | Single | New and Lined Culverts | 2024-2025 | 2024-12-06 | 5 | 2025-06-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
8519-2 | Near Sexsmith | Peace | 59:02 | Niobe Creek | 1 x 3050 SWSP - 1 x 2440 SWSP Liner | 47 - 43 | 90 | 2.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 220000 | 220000 | 185278 | 185278 | 15.1%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 30000 | 30000 | 40397.33 | 40397.33 | 60.2%
E018 | Site Isolation, Water & Fish Accommodation, Turbidity Monitoring (Special Provisions) | lump sum | 1 | 80000 | 80000 | 40150.67 | 40150.67 | 69.9%
F186 | Excavation - Structural (BCS 1.6.1) (Special Provisions) | lump sum | 1 | 75000 | 75000 | 30866.67 | 30866.67 | 44.9%
F020 | SWSP (3050mm O.D. x 12.7mm thickness) - Supply (Special Provisions) | metre | 47 | 7000 | 329000 | 9581.31 | 450321.57 | 6.2%
F020 | SWSP (3050mm O.D. x 12.7mm thickness) - Install (Special Provisions) | metre | 47 | 16800 | 789600 | 10718.79 | 503783.13 | 11.8%
D850 | Culvert Liner - Supply and Install (S.W.S.P.) (2400 mm dia.) (HCS 2.23.4) (HCS 5.22.4) (Special Provisions) | metre | 47 | 5000 | 235000 | 6997.02 | 328859.94 | 15.9%
D546 | Grouting Liners (S.W.S.P) (HCS 2.23.4) (Special Provisions) | cubic metre | 70 | 850 | 59500 | 837.33 | 58613.1 | 19.1%
F190 | Backfill (BCS 2.4) (Special Provisions) | lump sum | 1 | 130000 | 130000 | 57675.67 | 57675.67 | 9.1%
X040 | Heavy Rock Riprap (Class 1) (Special Provisions) | tonne | 400 | 500 | 200000 | 330.13 | 132052 | 17.9%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) (Special Provisions) | metre | 83 | 140 | 11620 | 256.38 | 21279.54 | 13%
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 1 | 5000 | 5000 | 8073.33 | 8073.33 | 10%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 52000 | 52000 | 24268 | 24268 | 75.1%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) (Special Provisions) | kilometre | 0.1 | 30000 | 3000 | 115546.67 | 11554.67 | 46.6%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 200 | 20 | 4000 | 16.81 | 3362 | 36.2%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) (Special Provisions) | square metre | 400 | 10 | 4000 | 8.9 | 3560 | 48.5%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) (Special Provisions) | metre | 200 | 20 | 4000 | 15.36 | 3072 | 50.3%
|  | Bridge File Modified Tender Value |  |  | 2231720 |  | 1903167.62 | 7.4%
|  | Total Tender Value |  |  |  |  | 1993166.28 | 7.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 50 | 75000 | 60 | 90000 | 17%
Tender: 24780 ¦ Bridge File: 8519-2 ¦ Tender Opening Date: 2024-12-06
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
24012 | Bridge Rehabilitation | Bridge | Combined | Bridge Rehabilitation | 2024-2025 | 2025-01-16 | 9 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
72633-2 | 7 km North of Penhold | Central | 2A:16 | Waskasoo Creek | 11 x 510 SCC | 14 | 14 | 13.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 11383.09 | 11383.09 | 26615.53 | 26615.53 | 33.8%
E612 | Total Suspended Solids (TSS) testing (Special Provisions) | day | 6 | 1500 | 9000 | 1466.67 | 8800.02 | 50.5%
F018 | Waterproofing at Deck Drains (Special Provisions) | lump sum | 1 | 5000 | 5000 | 15766.67 | 15766.67 | 34%
F020 | Crack Repair (Special Provisions) | metre | 23 | 370 | 8510 | 620 | 14260 | 43.1%
F022 | Finish & Seal Curb Surfaces (Special Provisions) | square metre | 47 | 100 | 4700 | 217.67 | 10230.49 | 61.4%
F022 | Finish & Seal Wingwall & Abutment Surfaces (Special Provisions) | square metre | 100 | 109 | 10900 | 148.33 | 14833 | 72.9%
F022 | Finish & Seal Exterior Girder Faces (Special Provisions) | square metre | 14 | 105 | 1470 | 607.67 | 8507.38 | 94.1%
F018 | Girder Soffit Repairs (Special Provisions) | lump sum | 1 | 6500 | 6500 | 11176.67 | 11176.67 | 75%
F018 | Abutment Void Fill (Special Provisions) | lump sum | 1 | 2000 | 2000 | 39166.67 | 39166.67 | 22.7%
S018 | Supply and Install Upgraded Approach Rail Transitions (BF#72633-2) (Special Provisions) | lump sum | 1 | 75000 | 75000 | 62666.67 | 62666.67 | 15.3%
|  | Bridge File Modified Tender Value |  |  | 134463.09 |  | 212023.1 | 23.7%
|  | Total Tender Value |  |  |  |  | 4237788.09 | 7.6%
Tender: 24012 ¦ Bridge File: 72633-2 ¦ Tender Opening Date: 2025-01-16
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23517 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2024-2025 | 2025-01-29 | 5 | 2025-10-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76089-2 | 82 km Southwest of Nordegg | Central | 11:02 | Tributary to North Saskatchewan River | 12 x 510 SCC | 12 | 12 | 14.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 150555 | 150555 | 128739.92 | 128739.92 | 17.6%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 150000 | 150000 | 94492 | 94492 | 6.5%
F486 | Demolition, Disposal and Salvage of Existing Structure (BCS 18.7) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 201993.67 | 201993.67 | 38.3%
F755 | Surface Removal (BCS 20.6.1) | square metre | 270 | 200 | 54000 | 225.42 | 60863.4 | 35.9%
Q565 | Cold Milling Asphalt Pavement (HCS 3.16.6) (Special Provisions) | square metre | 650 | 20 | 13000 | 41.48 | 26962 | 94.1%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) | lump sum | 1 | 135000 | 135000 | 167691.67 | 167691.67 | 29.9%
F993 | Galvanic Corrosion Protection - Supply and Install (Special Provisions) | anodes | 80 | 100 | 8000 | 78.03 | 6242.4 | 24.5%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 2003 | 9 | 18027 | 12.49 | 25017.47 | 16.3%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 2003 | 6 | 12018 | 4.12 | 8252.36 | 49.8%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 37 | 4000 | 148000 | 2632.38 | 97398.06 | 43.9%
F974 | Waterproofing (BCS 16.5) | square metre | 270 | 150 | 40500 | 103 | 27810 | 11.7%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 2500 | 2500 | 1676 | 1676 | 14.2%
F018 | Approach Slab Jacking (Special Provisions) | lump sum | 1 | 6000 | 6000 | 24597.33 | 24597.33 | 31.6%
F018 | Adjust Approach Guardrail Transition Height (Special Provisions) | lump sum | 1 | 12500 | 12500 | 21087.67 | 21087.67 | 23.6%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 140 | 1200 | 168000 | 861.6 | 120624 | 28%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) (Special Provisions) | metre | 200 | 30 | 6000 | 40.7 | 8140 | 24%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) (Special Provisions) | metre | 200 | 200 | 40000 | 165.12 | 33024 | 6%
F020 | W-Beam Guardrail Sections - Supply (Special Provisions) | metre | 50 | 50 | 2500 | 83.42 | 4171 | 50%
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 4 | 8500 | 34000 | 6566.48 | 26265.92 | 16.2%
S350 | Roadway Lines - Supplying Paint and Painting (Directional Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.1 | 65000 | 6500 | 50446.27 | 5044.63 | 5.4%
F018 | Water Body Identification Signs (Special Provisions) | lump sum | 1 | 3000 | 3000 | 2745.67 | 2745.67 | 43.8%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 10000 | 10000 | 13981.33 | 13981.33 | 49.2%
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 75000 | 75000 | 75000 | 75000 | 0%
|  | Bridge File Modified Tender Value |  |  | 1145100 |  | 1181820.5 | 11%
|  | Total Tender Value |  |  |  |  | 1279334.16 | 10.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Quantity Std Dev (Low 3 Bids)
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 65 | 97500 | 12.6%
Tender: 23517 ¦ Bridge File: 76089-2 ¦ Tender Opening Date: 2025-01-29
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21131 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2024-2025 | 2025-02-04 | 6 | 2025-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74853-2 | Near La Crete | Peace | 697:04 | Teepee Creek | 9 x 510 SLC | 16 | 16 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 230000 | 230000 | 269000 | 269000 | 12.6%
F750 | Traffic Accommodation for Bridge Construction (B.F. 74853) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 200000 | 200000 | 241333.33 | 241333.33 | 5.1%
F170 | Demolition and Disposal of Bridge Structure (B.F. 74853) (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | 255000 | 255000 | 18.5%
F018 | Headslope Preparation and Backfill (Special Provisions) | lump sum | 1 | 150000 | 150000 | 66666.67 | 66666.67 | 30.2%
F812 | Supply of Piling - Plain Steel H-Pile (B.F. 74853) (BCS 3.6.1) | metre | 487 | 450 | 219150 | 143.33 | 69801.71 | 17.4%
F816 | Pile Set-up (Driven Piles) (B.F. 74853) (BCS 3.6.1) | pile | 16 | 6000 | 96000 | 8516.67 | 136266.72 | 18.3%
F818 | Pile Driving (B.F. 74853) (BCS 3.6.1) | metre | 487 | 137 | 66719 | 27.67 | 13475.29 | 56.5%
F820 | PDA Testing (B.F. 74853) (BCS 3.6.4) | test | 8 | 2300 | 18400 | 5016.67 | 40133.36 | 92.2%
F850 | Plain Reinforcing Steel - Supply (B.F. 74853) (BCS 5.6) | kilogram | 3916 | 3.5 | 13706 | 3.08 | 12061.28 | 3.8%
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 74853) (BCS 5.6) | kilogram | 7347 | 8.5 | 62449.5 | 10.67 | 78392.49 | 4.4%
F853 | Stainless Reinforcing Steel - Supply (B.F. 74853) (BCS 5.6) | kilogram | 471 | 11 | 5181 | 16.33 | 7691.43 | 16.1%
F854 | Reinforcing Steel - Place (B.F. 74853) (BCS 5.6) | kilogram | 11734 | 2.5 | 29335 | 3.67 | 43063.78 | 12.8%
F834 | Concrete (Class C) - Supply and Place (B.F. 74853) (BCS 4.27.1) | cubic metre | 27.5 | 3200 | 88000 | 2546.67 | 70033.43 | 49.2%
F841 | Concrete (Class HPC) - Supply and Place (B.F. 74853) (BCS 4.27.1) | cubic metre | 55.2 | 4600 | 253920 | 2883.33 | 159159.82 | 38.9%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 16 m SLC-510 (B.F. 74853) (BCS 7.4) | lump sum | 1 | 400000 | 400000 | 526868.33 | 526868.33 | 23.6%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 2500 | 2500 | 8000 | 8000 | 65.2%
F974 | Waterproofing (BCS 16.5) | square metre | 286.8 | 100 | 28680 | 178.33 | 51145.04 | 68.2%
F780 | Bridgerail - Supply and Install (B.F. 74853) | lump sum | 1 | 40000 | 40000 | 48333.33 | 48333.33 | 27.2%
F752 | Guardrail - Supply and Install (B.F. 74853) (BCS 14.5) | lump sum | 1 | 45000 | 45000 | 70000 | 70000 | 15.7%
F492 | Roadway Work (B.F. 74853) (BCS 18.7) (Special Provisions) | lump sum | 1 | 150000 | 150000 | 200166.67 | 200166.67 | 62.1%
F983 | Asphalt Concrete Pavement - Mix Type M1 (PG52-34) Mix Type M1 (PG 52-34) (BCS 17.7.1) | lump sum | 1 | 60000 | 60000 | 205000 | 205000 | 19.2%
F500 | Heavy Rock Riprap (Class 1) (B.F. 74853) (BCS 10.7) | cubic metre | 120 | 350 | 42000 | 291.67 | 35000.4 | 28.8%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 50 | 15 | 750 | 36.83 | 1841.5 | 36.3%
E020 | Erosion Control Barrier (Straw Fibre Roll) (Special Provisions) | metre | 80 | 15 | 1200 | 38.67 | 3093.6 | 48.2%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 150 | 15 | 2250 | 31.67 | 4750.5 | 32.4%
|  | Bridge File Modified Tender Value |  |  | 2305240.5 |  | 2616278.68 | 11.8%
|  | Total Tender Value |  |  |  |  | 2716729.67 | 11.6%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 65 | 97500 | 67 | 100500 | 30.8%
Tender: 21131 ¦ Bridge File: 74853-2 ¦ Tender Opening Date: 2025-02-04
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22685 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2024-2025 | 2025-02-21 | 7 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
2401-1 | 6 km North of Islay | Central | 893:04 | Vermilion River | 4 x 1520 Type-O | 24 ¦ 24 | 48 | 9.5
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 196000 | 196000 | 161036.33 | 161036.33 | 12.1%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 85000 | 85000 | 109842 | 109842 | 16.1%
E018 | Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 15000 | 15000 | 37329 | 37329 | 51.6%
F018 | Pier Access (Special Provisions) | lump sum | 1 | 150000 | 150000 | 51785.33 | 51785.33 | 40.5%
F018 | Pier Modifications - Concrete Corbels (Special Provisions) | lump sum | 1 | 225000 | 225000 | 138850 | 138850 | 13.7%
F906 | Bearings - Supply and Fabrication, Delivery and Installation (BCS 8.5) | lump sum | 1 | 191600 | 191600 | 245238.67 | 245238.67 | 17.4%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation - Pier and Abutment Joints - Type 1 Strip Seals (BCS 6.4.2) | lump sum | 1 | 144000 | 144000 | 243658.67 | 243658.67 | 6.8%
F018 | Refurbish Abutment Bearings (Special Provisions) | lump sum | 1 | 41600 | 41600 | 135221.67 | 135221.67 | 58%
F760 | Partial Depth Repair - Pier Seats (BCS 20.6.2) | square metre | 4 | 2200 | 8800 | 2444.33 | 9777.32 | 43.1%
F760 | Partial Depth Repair - Pier Vertical Faces (BCS 20.6.2) | square metre | 12 | 2000 | 24000 | 2277.67 | 27332.04 | 7.3%
F760 | Partial Depth Repair - Abutment Seats (BCS 20.6.2) | square metre | 8 | 2000 | 16000 | 2580.33 | 20642.64 | 37.3%
F760 | Partial Depth Repair - Abutment Curtainwalls (BCS 20.6.2) | square metre | 6 | 2300 | 13800 | 3212.33 | 19273.98 | 27.4%
F760 | Partial Depth Repair - Abutment Backwalls (BCS 20.6.2) | square metre | 6 | 2300 | 13800 | 3275.67 | 19654.02 | 28.7%
F760 | Partial Depth Repair - Deck Undersides and Soffit (BCS 20.6.2) | square metre | 8 | 4500 | 36000 | 4403 | 35224 | 14.1%
F760 | Partial Depth Repair - Deck, Overlay and Curbs (BCS 20.6.2) | square metre | 70 | 2700 | 189000 | 1766 | 123620 | 29.5%
F760 | Partial Depth Repair - Girder Ends at Bearing Locations (BCS 20.6.2) | square metre | 8 | 2100 | 16800 | 2339.67 | 18717.36 | 4.2%
F018 | Removal Deck Drains (Special Provisions) | lump sum | 1 | 12000 | 12000 | 21294.33 | 21294.33 | 26.7%
F018 | Concrete Cleaning and Finishing at Pier (Special Provisions) | lump sum | 1 | 25000 | 25000 | 24283.33 | 24283.33 | 27.3%
F018 | Concrete Cleaning and Finishing at Abutments (Special Provisions) | lump sum | 1 | 15000 | 15000 | 15361.33 | 15361.33 | 8.4%
F911 | Drain Troughs (BCS 9.7) | metre | 70 | 800 | 56000 | 782.67 | 54786.9 | 30.7%
G018 | Erosion Gully Repairs and Other Work (Special Provisions) | lump sum | 1 | 25000 | 25000 | 16486.33 | 16486.33 | 22.1%
F018 | River Identification Signs (Special Provisions) | lump sum | 1 | 3000 | 3000 | 1257.33 | 1257.33 | 43.5%
|  | Bridge File Modified Tender Value |  |  | 1502400 |  | 1530672.58 | 10.7%
|  | Total Tender Value |  |  |  |  | 1668172.33 | 11.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 70 | 105000 | 92 | 138000 | 20%
Tender: 22685 ¦ Bridge File: 2401-1 ¦ Tender Opening Date: 2025-02-21
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21768 | Construct WSP/CSP Culvert - Install CPCSP Culvert Liner | Culvert | Single | New and Lined Culverts | 2024-2025 | 2025-02-25 | 7 | 2026-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75700-2 | 23 km South of Wanham | Peace | 733:04 | Bad Heart River | 1 x 2430 WSP ¦ 2700 CSP - 1 x 3360 SPCSP Liner - 1 x 3050 SPCSP Liner | 90 ¦ 51 - 83 - 82 | 306 | 2.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 500000 | 500000 | 346250 | 346250 | 42.2%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 25000 | 25000 | 53333.33 | 53333.33 | 68.6%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 15 | 1500 | 22500 | 586.67 | 8800.05 | 128.3%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 65000 | 65000 | 65000 | 65000 | 27.4%
F018 | Silt, Concrete Floor, Debris and Ice Removal (Special Provisions) | lump sum | 1 | 40000 | 40000 | 36650 | 36650 | 51.5%
F018 | Shoring and Boring Pit Preparation (Special Provisions) | lump sum | 1 | 60000 | 60000 | 111000 | 111000 | 54.9%
F027 | Welded Steel Pipe - Supply (Special Provisions) | metre | 90 | 9000 | 810000 | 7586.67 | 682800.3 | 36.8%
F027 | Welded Steel Pipe - Install (Special Provisions) | metre | 90 | 9000 | 810000 | 8666.67 | 780000.3 | 49%
F018 | 2700 mm CSP Extension - Supply (Special Provisions) | lump sum | 1 | 75000 | 75000 | 114266.67 | 114266.67 | 34.3%
F018 | 2700 mm CSP Extension - Install (Special Provisions) | lump sum | 1 | 32000 | 32000 | 96900 | 96900 | 19%
F018 | 3050 mm SPCSP Culvert Liner - Supply (Special Provisions) | lump sum | 1 | 335000 | 335000 | 246044.67 | 246044.67 | 4.8%
F018 | 3050 mm SPCSP Culvert Liner - Install (Special Provisions) | lump sum | 1 | 135000 | 135000 | 143333.33 | 143333.33 | 51.4%
F018 | 3360 mm SPCSP Culvert Liner - Supply (Special Provisions) | lump sum | 1 | 365000 | 365000 | 274300 | 274300 | 7.7%
F018 | 3360 mm SPCSP Culvert Liner - Install (Special Provisions) | lump sum | 1 | 145000 | 145000 | 149333.33 | 149333.33 | 54.1%
F018 | Concrete - Class S Modified (Liners) (Special Provisions) | lump sum | 1 | 680000 | 680000 | 437802 | 437802 | 12.2%
F018 | Concrete - Class S (Thrust Blocks) (Special Provisions) | lump sum | 1 | 90000 | 90000 | 65015 | 65015 | 34%
F021 | Concrete - Class S (Void Under Outlets) (Special Provisions) | cubic metre | 5 | 800 | 4000 | 1333.33 | 6666.65 | 35.4%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 25000 | 25000 | 48333.33 | 48333.33 | 21.3%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 57500 | 57500 | 73333.33 | 73333.33 | 75.8%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 125000 | 125000 | 113333.33 | 113333.33 | 39.7%
F515 | Heavy Rock Riprap (Class 2) (BCS 10.7) | cubic metre | 1405 | 345 | 484725 | 356.67 | 501121.35 | 24%
F525 | Heavy Rock Riprap (Class 3) (BCS 10.7) | cubic metre | 1265 | 350 | 442750 | 366.67 | 463837.55 | 22%
E020 | Rock Ditch Drains - Class 1M (Special Provisions) | metre | 18 | 400 | 7200 | 533.33 | 9599.94 | 29%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 250 | 15 | 3750 | 23.33 | 5832.5 | 10.1%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 50 | 15 | 750 | 36.67 | 1833.5 | 54.9%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 120 | 15 | 1800 | 22.5 | 2700 | 63.5%
F018 | Drift Removal (Special Provisions) | lump sum | 1 | 10000 | 10000 | 14916.67 | 14916.67 | 48.2%
F018 | Drift Catcher - Berm Construction (Special Provisions) | lump sum | 1 | 160000 | 160000 | 60666.67 | 60666.67 | 47.4%
F009 | Drift Catcher - Weld Repair (Special Provisions) | hour | 20 | 300 | 6000 | 275 | 5500 | 58.9%
|  | Bridge File Modified Tender Value |  |  | 5517975 |  | 4918503.8 | 9.5%
|  | Total Tender Value |  |  |  |  | 5070995 | 9.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 102 | 153000 | 2.3%
Tender: 21768 ¦ Bridge File: 75700-2 ¦ Tender Opening Date: 2025-02-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22809 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2024-2025 | 2025-02-27 | 6 | 2025-10-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
70063N-1 | 5 km North of Nisku | North Central | 2:32 | Blackmud Creek | 1 x 1220 CIP Frame | 22 | 22 | 18.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 250000 | 250000 | 296000 | 296000 | 11.7%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 375000 | 375000 | 193333.33 | 193333.33 | 48%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 150000 | 150000 | 320000 | 320000 | 35.9%
F755 | Surface Removal - ACP Wearing Surface (BCS 20.6.1) | square metre | 380 | 60 | 22800 | 109 | 41420 | 21.1%
F755 | Surface Removal - Concrete Deck (BCS 20.6.1) | square metre | 380 | 200 | 76000 | 106.67 | 40534.6 | 36.8%
Q565 | Cold Milling Asphalt Pavement (HCS 3.16.6) | square metre | 590 | 30 | 17700 | 40.33 | 23794.7 | 17%
F760 | Partial Depth Repair - Deck (BCS 20.6.2) | square metre | 25 | 2000 | 50000 | 1293.33 | 32333.25 | 55.3%
F770 | Abrasive Blasting - Deck Surface (BCS 20.6.3) | square metre | 380 | 125 | 47500 | 30 | 11400 | 13.6%
F053 | Dowelling Using Hilti HIT-HY 200 - Supply and Install (Special Provisions) | unit | 1248 | 75 | 93600 | 60 | 74880 | 20.4%
F775 | Deck Overlay Concrete - Supply - Fibre-Reinforced HPC Concrete (BCS 20.6.4) | cubic metre | 75 | 3250 | 243750 | 1078.33 | 80874.75 | 16.1%
F776 | Deck Overlay Concrete - Place (BCS 20.6.4) | square metre | 380 | 200 | 76000 | 366.67 | 139334.6 | 34%
F203 | Backfill - Crushed Aggregate Des. 2 Class 25 (BCS 2.4) | cubic metre | 90 | 100 | 9000 | 476.67 | 42900.3 | 53.1%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 82 | 2600 | 213200 | 2400 | 196800 | 20.4%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 24 | 2000 | 48000 | 3260 | 78240 | 14%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation - Double Tube (BCS 12.4) | lump sum | 1 | 45000 | 45000 | 71666.67 | 71666.67 | 1.7%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 2885 | 6 | 17310 | 3 | 8655 | 0%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 12012 | 17 | 204204 | 12 | 144144 | 6.8%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 14897 | 4 | 59588 | 3.17 | 47223.49 | 19.7%
F974 | Waterproofing (BCS 16.5) | square metre | 589 | 100 | 58900 | 65 | 38285 | 16.6%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 150 | 650 | 97500 | 558.33 | 83749.5 | 10.6%
S806 | Thrie Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 240 | 500 | 120000 | 320 | 76800 | 6.8%
F018 | Approach Rail Transition - Supply and Install (Special Provisions) | lump sum | 1 | 75000 | 75000 | 31000 | 31000 | 20.9%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 77 | 350 | 26950 | 281.67 | 21688.59 | 42.3%
F824 | Drill Rig Set-up (Drilled Piles) (BCS 3.6.2) | pile | 8 | 10000 | 80000 | 14000 | 112000 | 26.7%
F826 | Pile Installation (Drilled Piles) (BCS 3.6.2) | metre | 77 | 500 | 38500 | 796.67 | 61343.59 | 21%
F822 | Pile Concrete (Class) - Supply and Place (BCS 4.27.1) | cubic metre | 18 | 1750 | 31500 | 628.33 | 11309.94 | 14.3%
F911 | Drain Troughs (BCS 9.7) | metre | 59 | 1250 | 73750 | 1100 | 64900 | 26.8%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 10 | 350 | 3500 | 893.33 | 8933.3 | 34%
X002 | Extra Work - Various Repairs (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | 100000 | 100000 | 0%
F186 | Excavation - Structural - Approach Slabs (BCS 1.6.1) | lump sum | 1 | 90000 | 90000 | 101500 | 101500 | 80.2%
|  | Bridge File Modified Tender Value |  |  | 2794252 |  | 2555044.61 | 12.2%
|  | Total Tender Value |  |  |  |  | 2977494.5 | 12.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 140 | 210000 | 130 | 195000 | 12.6%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 100 | 150000 | 152 | 228000 | 17.5%
Tender: 22809 ¦ Bridge File: 70063-1 ¦ Tender Opening Date: 2025-02-27
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23181 | Mill and Pave Bridges | Bridge | Highway | Bridge Maintenance | 2024-2025 | 2025-02-27 | 4 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
Multiple | Hwy 2 North of Calgary | Southern | - | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 16378.58 | 16378.58 | 17252.01 | 17252.01 | 22.2%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 6985.85 | 6985.85 | 12495.51 | 12495.51 | 56.3%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 1000 | 140 | 140000 | 137.33 | 137330 | 19.5%
X020 | Bridge Tie-Ins - Saw-Cutting and Supply of Sealant Materials (Special Provisions) | metre | 560 | 30 | 16800 | 60.33 | 33784.8 | 25.2%
|  | Bridge File Modified Tender Value |  |  | 180164.43 |  | 200862.32 | 11.4%
|  | Total Tender Value |  |  |  |  | 15366665.92 | 7.2%
Tender: 23181 ¦ Bridge File: Multiple ¦ Tender Opening Date: 2025-02-27
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23855 | Mill and Pave Bridges | Bridge | Highway | Bridge Maintenance | 2024-2025 | 2025-02-28 | 4 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
Multiple | Stoney Trail | Southern | - | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 60502.34 | 60502.34 | 58983.38 | 58983.38 | 23.2%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 25523.42 | 25523.42 | 49129.01 | 49129.01 | 71.3%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 3700 | 140 | 518000 | 138.67 | 513079 | 15.2%
X020 | Bridge Tie-ins - Saw-cutting and Supply of Sealant Materials (Special Provisions) | metre | 820 | 75 | 61500 | 56.67 | 46469.4 | 11%
|  | Bridge File Modified Tender Value |  |  | 665525.76 |  | 667660.79 | 14.6%
|  | Total Tender Value |  |  |  |  | 16722901.49 | 5%
Tender: 23855 ¦ Bridge File: Multiple ¦ Tender Opening Date: 2025-02-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22642 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2024-2025 | 2025-03-04 | 3 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
7855-2 | 5 km Northwest of Bruderheim | North Central | 830:4 | Astotin Creek | 9 x 700 SLC | 20 | 20 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 385000 | 385000 | 345923.51 | 345923.51 | 22.6%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 650000 | 650000 | 418333.33 | 418333.33 | 45.6%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 60000 | 60000 | 57666.67 | 57666.67 | 47.7%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 2000 | 20000 | 1503.33 | 15033.3 | 81.2%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 220000 | 220000 | 241000 | 241000 | 24.6%
F190 | Backfill (BCS 2.4) (Special Provisions) | lump sum | 1 | 80000 | 80000 | 124500 | 124500 | 43.6%
F812 | Supply of Piling - Plain Steel H-Pile - HP310X94 (BCS 3.6.1) | metre | 368 | 280 | 103040 | 235 | 86480 | 12.2%
F816 | Pile Set-up (Driven Piles) - HP310X94 (BCS 3.6.1) | pile | 16 | 5000 | 80000 | 6666.67 | 106666.72 | 19.7%
F818 | Pile Driving - HP310X94 (BCS 3.6.1) | metre | 368 | 60 | 22080 | 66.67 | 24534.56 | 90.3%
F820 | PDA Testing (BCS 3.6.4) | test | 2 | 3000 | 6000 | 3766.67 | 7533.34 | 70.6%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 180 | 350 | 63000 | 345.33 | 62159.4 | 17.4%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 5425 | 5 | 27125 | 3.12 | 16926 | 5.3%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 10302 | 8 | 82416 | 10.08 | 103844.16 | 20.7%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 702 | 17 | 11934 | 15 | 10530 | 0%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 16429 | 3 | 49287 | 2.55 | 41893.95 | 26.5%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 40 | 2500 | 100000 | 2733.33 | 109333.2 | 27.8%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) (Special Provisions) | lump sum | 1 | 750000 | 750000 | 510305.73 | 510305.73 | 22.3%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 68 | 3000 | 204000 | 2783.33 | 189266.44 | 18.3%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 2000 | 2000 | 4133.33 | 4133.33 | 29.7%
F974 | Waterproofing (BCS 16.5) | square metre | 325 | 125 | 40625 | 170 | 55250 | 85.5%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 1385 | 450 | 623250 | 218.33 | 302387.05 | 2.9%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 100000 | 100000 | 215000 | 215000 | 88%
F911 | Drain Troughs (BCS 9.7) | metre | 40 | 500 | 20000 | 693.33 | 27733.2 | 10.6%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 50000 | 50000 | 48000 | 48000 | 29.1%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 25000 | 25000 | 60000 | 60000 | 0%
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 3 | 6000 | 18000 | 4833.33 | 14499.99 | 27.2%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 300 | 30 | 9000 | 25.67 | 7701 | 56.6%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 800 | 15 | 12000 | 23.33 | 18664 | 36.4%
|  | Bridge File Modified Tender Value |  |  | 3813757 |  | 3225298.88 | 22.9%
|  | Total Tender Value |  |  |  |  | 3486321.28 | 21.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 120 | 180000 | 88 | 132000 | 30.4%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 160 | 240000 | 86 | 129000 | 29.1%
Tender: 22642 ¦ Bridge File: 7855-2 ¦ Tender Opening Date: 2025-03-04
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21867 | Construct SLW Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2024-2025 | 2025-03-05 | 7 | 2025-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
73534-2 | 1 km North of Falher | Peace | Local Road | Winagami / Girouxville Canal | 9 x 510 SLW | 14 | 14 | 11
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 200000 | 200000 | 201306 | 201306 | 43.8%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 50000 | 50000 | 16739 | 16739 | 14.7%
E018 | Water Management (Special Provisions) | lump sum | 1 | 40000 | 40000 | 10333.67 | 10333.67 | 134.6%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 20 | 1000 | 20000 | 37 | 740 | 120.8%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 50000 | 50000 | 64351.67 | 64351.67 | 66.6%
F018 | Headslope Preparation and Backfill (Special Provisions) | lump sum | 1 | 80000 | 80000 | 84484.33 | 84484.33 | 17.2%
F812 | Supply of Piling - Plain Steel H-Pile - 310 x 94 mm (BCS 3.6.1) | metre | 300 | 340 | 102000 | 237.33 | 71199 | 3.2%
F813 | Supply of Piling - Galvanized Steel H-Pile - 310 x 94 mm (BCS 3.6.1) | metre | 36 | 350 | 12600 | 326.33 | 11747.88 | 11.5%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 22 | 5000 | 110000 | 5038.33 | 110843.26 | 30.3%
F818 | Pile Driving (BCS 3.6.1) | metre | 336 | 61 | 20496 | 6.67 | 2241.12 | 35.3%
F820 | PDA Testing (BCS 3.6.4) | test | 4 | 2000 | 8000 | 1716.67 | 6866.68 | 73.5%
F018 | Abutment and Wingwall Construction (Special Provisions) | lump sum | 1 | 210000 | 210000 | 150337.67 | 150337.67 | 13.3%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (9-14 m SLW-510) (BCS 7.4) | lump sum | 1 | 315000 | 315000 | 310183.33 | 310183.33 | 3.5%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 6000 | 6000 | 1308.67 | 1308.67 | 74.9%
F018 | Approach Slabs (Special Provisions) | lump sum | 1 | 40000 | 40000 | 43711.67 | 43711.67 | 30.5%
F974 | Waterproofing (BCS 16.5) | square metre | 205 | 100 | 20500 | 105 | 21525 | 14%
F780 | Bridgerail - Supply and Install (Special Provisions) | lump sum | 1 | 25000 | 25000 | 23196 | 23196 | 11%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 30000 | 30000 | 31817.33 | 31817.33 | 15.2%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 140000 | 140000 | 91006.67 | 91006.67 | 42.6%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 240 | 450 | 108000 | 411.67 | 98800.8 | 7.1%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 175 | 375 | 65625 | 215 | 37625 | 24.7%
E020 | Rock Ditch Drains - Class 1M (Special Provisions) | metre | 15 | 450 | 6750 | 503.33 | 7549.95 | 57.6%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 50 | 15 | 750 | 36.67 | 1833.5 | 64.3%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 80 | 15 | 1200 | 18.33 | 1466.4 | 68%
|  | Bridge File Modified Tender Value |  |  | 1661921 |  | 1401214.6 | 1.5%
|  | Total Tender Value |  |  |  |  | 1463214 | 1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 41 | 61500 | 32.4%
Tender: 21867 ¦ Bridge File: 73534-2 ¦ Tender Opening Date: 2025-03-05
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23732 | Remove CSP Culvert | Culvert | Highway | Remove Culvert | 2024-2025 | 2025-03-07 | 9 | 2025-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
77415-1 | Near Meeting Creek | Central | 56:16 | Cattlepass | 1 x 1800 CSP | 29 | 29 | 1.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 6541.95 | 6541.95 | 4568.17 | 4568.17 | 64.9%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 1259.47 | 1259.47 | 715.83 | 715.83 | 102.4%
F186 | Excavation - Structural (B.F. 77415-1) (BCS 1.6.1) | lump sum | 1 | 3000 | 3000 | 8572 | 8572 | 44.9%
F170 | Demolition and Disposal of Bridge Structure (B.F. 77415-1) (BCS 21.4.1) | lump sum | 1 | 10000 | 10000 | 6015.67 | 6015.67 | 26.5%
F492 | Roadway Work - Sideslope Improvement (B.F. 77415-1) (BCS 18.7) | lump sum | 1 | 20000 | 20000 | 13653 | 13653 | 7.5%
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 41 | 760 | 31160 | 594.45 | 24372.45 | 3.9%
|  | Bridge File Modified Tender Value |  |  | 71961.42 |  | 57897.12 | 17.2%
|  | Total Tender Value |  |  |  |  | 16135808.42 | 1.2%
Tender: 23732 ¦ Bridge File: 77415-1 ¦ Tender Opening Date: 2025-03-07
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22362 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2024-2025 | 2025-03-20 | 4 | 2026-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75059-1 | 6 km East of Beaver Mines | Southern | 507:02 | Mill Creek | 5 x 910 RB | 21 ¦ 29 ¦ 22 ¦ 12 | 84 | 9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 307000 | 307000 | 249000 | 249000 | 8.9%
F750 | Traffic Accommodation for Bridge Construction (B.F. 75059) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 400000 | 400000 | 238333.33 | 238333.33 | 15.7%
F018 | Bridge Washing (Special Provisions) | lump sum | 1 | 20000 | 20000 | 32000 | 32000 | 40.8%
F018 | Remove and Dispose of Existing Deck Joint Assemblies and Isolated Approach Slab and Concrete Parapet Removals (Special Provisions) | lump sum | 1 | 60000 | 60000 | 74433.33 | 74433.33 | 50.5%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (B.F. 75059) Type 1 Strip Seal (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 120000 | 120000 | 165485.67 | 165485.67 | 23.6%
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 75059) Parapet Modifications (BCS 5.6) (Special Provisions) | kilogram | 600 | 15 | 9000 | 19 | 11400 | 11.4%
F853 | Stainless Reinforcing Steel - Supply (B.F. 75059) Deck Joint End Dams (BCS 5.6) (Special Provisions) | kilogram | 1000 | 25 | 25000 | 20.33 | 20330 | 12.9%
F854 | Reinforcing Steel - Place (B.F. 75059) Deck Joint End Dams / Parapet Modifications (BCS 5.6) (Special Provisions) | kilogram | 1600 | 10 | 16000 | 4.3 | 6880 | 23%
F053 | Reinforcing Steel - Dowel Install (B.F. 75059) Deck Joint End Dams / Parapet Modifications (Special Provisions) | unit | 650 | 50 | 32500 | 39.33 | 25564.5 | 43.6%
F841 | Concrete (Class HPC) - Supply and Place (B.F. 75059) Deck Joint End Dams / Parapet Modifications (BCS 4.27.1) (Special Provisions) | cubic metre | 9 | 2750 | 24750 | 4718.67 | 42468.03 | 16.5%
F024 | Structural Steel - Supply, Delivery and Installation - Deck Drain Extensions (Special Provisions) | drain | 6 | 6500 | 39000 | 4829 | 28974 | 32.1%
F755 | Surface Removal (B.F. 75059) Bridge Deck and Approach Slabs (BCS 20.6.1) (Special Provisions) | square metre | 720 | 150 | 108000 | 185.33 | 133437.6 | 9.7%
F760 | Partial Depth Repair - Deck (Top) (BCS 20.6.2) (Special Provisions) | square metre | 30 | 1500 | 45000 | 1241.67 | 37250.1 | 32.6%
F760 | Partial Depth Repair - Pier (Pier 1 & Pier 2) (BCS 20.6.2) (Special Provisions) | square metre | 4 | 3500 | 14000 | 2977 | 11908 | 29.3%
F760 | Partial Depth Repair - Pier (Pier 3) (BCS 20.6.2) (Special Provisions) | square metre | 15 | 2500 | 37500 | 2563.33 | 38449.95 | 22.1%
F760 | Partial Depth Repair - Deck Soffit (Within 2 m of Deck Joints) (BCS 20.6.2) (Special Provisions) | square metre | 2 | 2500 | 5000 | 4906.33 | 9812.66 | 23.7%
F760 | Partial Depth Repair - Curb (Top and Front Face) (BCS 20.6.2) (Special Provisions) | square metre | 7 | 2500 | 17500 | 1929.67 | 13507.69 | 21.3%
F760 | Partial Depth Repair - Curb (Fascia and Overhang) (BCS 20.6.2) (Special Provisions) | square metre | 6 | 3500 | 21000 | 3256.67 | 19540.02 | 32.8%
F765 | Full Depth Repair - Deck (BCS 20.6.2) (Special Provisions) | square metre | 2 | 7500 | 15000 | 3963.33 | 7926.66 | 21.5%
F020 | Full Depth Repair - Isolated Disintegrated Curb (Special Provisions) | metre | 5 | 3000 | 15000 | 2658.33 | 13291.65 | 36.3%
F020 | Crack Sealing - Gravity Fed Repair (Special Provisions) | metre | 90 | 200 | 18000 | 206.33 | 18569.7 | 38.9%
F770 | Abrasive Blasting - Deck Surface (B.F. 75059) Bridge Deck and Approach Slabs (BCS 20.6.3) (Special Provisions) | square metre | 720 | 50 | 36000 | 19.33 | 13917.6 | 4.9%
F974 | Waterproofing - Deck (BCS 16.5) (Special Provisions) | square metre | 720 | 125 | 90000 | 59.67 | 42962.4 | 7.5%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) (Special Provisions) | tonne | 180 | 600 | 108000 | 451 | 81180 | 13%
F019 | Drain Trough Collector Replacement (Special Provisions) | location | 2 | 4000 | 8000 | 11168.67 | 22337.34 | 55.9%
F022 | Concrete Cleaning and Sealing - Type 1c - Curbs (Special Provisions) | square metre | 130 | 100 | 13000 | 71 | 9230 | 27.6%
F053 | Ultrasonic Impact Treatment - Isolated Bottom Flange Cover Plate End Termination Welds (Special Provisions) | unit | 10 | 10000 | 100000 | 4319.33 | 43193.3 | 27.6%
F151 | Protection of the Environment (B.F. 75059) Isolated Steel Girder Overcoating Repairs (BCS 22.25.1) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 3928.33 | 3928.33 | 21.1%
F151 | Protection of the Environment (B.F. 75059) Bearing Recoating (BCS 22.25.1) (Special Provisions) | lump sum | 1 | 100000 | 100000 | 64656.33 | 64656.33 | 10.8%
F150 | Surface Preparation and Painting (B.F. 75059) Isolated Steel Girder Overcoating Repairs (BCS 22.25.2) (Special Provisions) | lump sum | 1 | 250000 | 250000 | 60753.67 | 60753.67 | 57.3%
F150 | Surface Preparation and Painting (B.F. 75059) Bearing Recoating (BCS 22.25.2) (Special Provisions) | lump sum | 1 | 250000 | 250000 | 316346.33 | 316346.33 | 26.5%
Q018 | Approach Road Transitions - Milling and Pavement (Special Provisions) | lump sum | 1 | 100000 | 100000 | 78079 | 78079 | 11.9%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) (Special Provisions) | metre | 220 | 35 | 7700 | 46.33 | 10192.6 | 21%
S034 | Rock Drilling and Backfill - East Approach (Special Provisions) | post | 55 | 1000 | 55000 | 831 | 45705 | 51.5%
S020 | Strong Post W-Beam Guardrail - Supply and Install (Special Provisions) | metre | 180 | 200 | 36000 | 354.33 | 63779.4 | 9.5%
S018 | Thrie Beam Approach Rail Transitions - Supply and Install (Special Provisions) | lump sum | 1 | 40000 | 40000 | 51000 | 51000 | 13.1%
S018 | TL-3 Rated SKT 350 End Treatment - Supply and Install (Special Provisions) | lump sum | 1 | 32000 | 32000 | 38465.33 | 38465.33 | 21.8%
S350 | Roadway Lines - Supplying Paint and Painting (Directional Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) (Special Provisions) | kilometre | 0.2 | 40000 | 8000 | 38833.33 | 7766.67 | 41.8%
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | 100000 | 100000 | 0%
|  | Bridge File Modified Tender Value |  |  | 2732950 |  | 2252056.19 | 12%
|  | Total Tender Value |  |  |  |  | 2519815.67 | 12%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 150 | 225000 | 112 | 168000 | 11.2%
F003 | Lane Closure for Bridge Construction - Hwy 507 (GCS 1.2.42.5) (Special Provisions) | day | 750 | 150 | 112500 | 133 | 99750 | 9.6%
Tender: 22362 ¦ Bridge File: 75059-1 ¦ Tender Opening Date: 2025-03-20

## FY 2023-2024
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23525 | Construct Sign Structures | Sign Structure | Highway | New Sign Structures | 2023-2024 | 2023-04-13 | 3 | 2024-07-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
Multiple | Deerfoot Trail | Southern | - | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 71837.03 | 71837.03 | 71308.32 | 71308.32 | 16.2%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 9063.18 | 9063.18 | 33326.81 | 33326.81 | 47.1%
X038 | Overhead Bridge Sign Structure and Sign Panels - Remove and Dispose (Special Provisions) | sign | 1 | 35000 | 35000 | 22912.53 | 22912.53 | 0.1%
X038 | Overhead Cantilever Sign Structure and Sign Panels - Remove and Dispose (Special Provisions) | sign | 1 | 28000 | 28000 | 20413.65 | 20413.65 | 0.1%
X011 | Overhead Sign Structure - Foundation Demolition and Disposal (Special Provisions) | bases | 3 | 9000 | 27000 | 6314.09 | 18942.27 | 32.5%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 82005ZN4) (BCS 24.5) | lump sum | 1 | 225000 | 225000 | 284333.4 | 284333.4 | 1.4%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 82005ZN5) (BCS 24.5) | lump sum | 1 | 295000 | 295000 | 433263.66 | 433263.66 | 1.5%
F992 | Sign Panels - Extruded Aluminum - Supply and Install (BCS 24.5) | square metre | 91 | 825 | 75075 | 472.89 | 43032.99 | 0.1%
|  | Bridge File Modified Tender Value |  |  | 765975.21 |  | 927533.63 | 3.6%
|  | Total Tender Value |  |  |  |  | 21073126.55 | 7.4%
Tender: 23525 ¦ Bridge File: Multiple ¦ Tender Opening Date: 2023-04-13
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23533 | Bridge High Load Damage Repair | Bridge | Single | Bridge Repair | 2023-2024 | 2023-04-18 | 1 | 2023-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
78151-1 | At Ft McMurray | North Central | Local Road | Highway 63 | 16 x 1170 FM | 28 ¦ 26 | 54 | 27
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 150000 | 150000 | - | - | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 78151) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 150000 | 150000 | - | - | -
F170 | Demolition and Disposal of Bridge Structure (B.F. 78151) (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | - | - | -
F169 | Salvage of Existing Bridge Materials (B.F. 78151) (BCS 21.4.2) | lump sum | 1 | 20000 | 20000 | - | - | -
F906 | Bearings - Supply and Fabrication, Delivery and Installation (B.F. 78151) Pier 1 and Abutment 2 (BCS 8.5) | lump sum | 1 | 80000 | 80000 | - | - | -
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (B.F. 78151) (BCS 7.4) | lump sum | 1 | 250000 | 250000 | - | - | -
F018 | Lateral Connection (Special Provisions) | lump sum | 1 | 50000 | 50000 | - | - | -
F018 | Lateral Post Tensioning (Special Provisions) | lump sum | 1 | 40000 | 40000 | - | - | -
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (B.F. 78151)- Pier 1 and Abutment 2 (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 120000 | 120000 | - | - | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 78151) (BCS 5.6) | kilogram | 1754 | 8 | 14032 | - | - | -
F854 | Reinforcing Steel - Place (B.F. 78151) (BCS 5.6) | kilogram | 1754 | 5 | 8770 | - | - | -
F841 | Concrete (Class HPC) - Supply and Place (B.F. 78151) (BCS 4.27.1) | cubic metre | 16 | 10000 | 160000 | - | - | -
F770 | Abrasive Blasting - Deck Surface (B.F. 78151) (BCS 20.6.3) | square metre | 9 | 300 | 2700 | - | - | -
F775 | Deck Overlay Concrete - Supply (B.F. 78151) (BCS 20.6.4) | cubic metre | 1 | 30000 | 30000 | - | - | -
F776 | Deck Overlay Concrete - Place (B.F. 78151) (BCS 20.6.4) | square metre | 9 | 8000 | 72000 | - | - | -
F018 | Bridgerail Reinstallation (Special Provisions) | lump sum | 1 | 35000 | 35000 | - | - | -
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 20000 | 20000 | - | - | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 78151) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 20000 | 20000 | - | - | -
F020 | Epoxy Concrete Crack Injection (Special Provisions) | metre | 3 | 1500 | 4500 | - | - | -
F018 | Partial Depth Repair (Special Provisions) | lump sum | 1 | 15000 | 15000 | - | - | -
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (B.F. 78151) Abutment 1 (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 60000 | 60000 | - | - | -
F018 | Replacement of Vertical Clearance Signs (Special Provisions) | lump sum | 1 | 2000 | 2000 | - | - | -
|  | Bridge File Modified Tender Value |  |  | 1404002 |  | - | -
|  | Total Tender Value |  |  |  |  | - | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy - Girder S2G1 (GCS 1.2.41.9) | day | 1500 | 75 | 112500 | - | - | -
F003 | Lane Closure for Bridge Construction - Girder S2G1 (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 65 | 97500 | - | - | -
X004 | Site Occupancy - Girder S2G16 (GCS 1.2.41.9) (Special Provisions) | day | 1500 | 20 | 30000 | - | - | -
F003 | Lane Closure for Bridge Construction - Girder S2G16 (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 20 | 30000 | - | - | -
Tender: 23533 ¦ Bridge File: 78151-1 ¦ Tender Opening Date: 2023-04-18
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
18129 | Remove Timber Bridge | Bridge | Highway | Remove Bridge | 2023-2024 | 2023-04-20 | 3 | 2024-07-28
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
78321-1 | 80 km East of Red Earth Creek | Peace | 686:12 | Tributary to Trout River | Treated Timber Beam | 6 ¦ 9 ¦ 6 | 21 | 7.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 8029.11 | 8029.11 | 178780.33 | 178780.33 | 127.8%
F170 | Demolition and Disposal of Bridge Structure (B.F. 78321-1) (BCS 21.4.1) | lump sum | 1 | 65000 | 65000 | 738333.33 | 738333.33 | 116.1%
F500 | Heavy Rock Riprap (Class 1) (B.F. 78321) (BCS 10.7) | cubic metre | 40 | 350 | 14000 | 557.33 | 22293.2 | 14.1%
|  | Bridge File Modified Tender Value |  |  | 87029.11 |  | 939406.86 | 115.8%
|  | Total Tender Value |  |  |  |  | 31273326.52 | 1.1%
Tender: 18129 ¦ Bridge File: 78321-1 ¦ Tender Opening Date: 2023-04-20
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22729 | Ferry Rehabilitation | Ferry | Single | Ferry Rehabilitation | 2023-2024 | 2023-05-10 | 4 | 2024-04-19
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
9125-1 | 10 km West of Munson | Central | 838:02 | Red Deer River | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 321122 | 321122 | 280941.36 | 280941.36 | 59.9%
F750 | Traffic Accommodation for Bridge Construction (B.F. 9125) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 30000 | 30000 | 19340.18 | 19340.18 | 39.3%
G018 | Site Preparation for Rehabilitation Work Area (Special Provisions) | lump sum | 1 | 70000 | 70000 | 66292.45 | 66292.45 | 81.6%
X018 | Ferry Relocation and Jacking Operations - Dry Dock to and from Vessel Rehabilitation Staging Area (Special Provisions) | lump sum | 1 | 160000 | 160000 | 333458.37 | 333458.37 | 76.2%
X018 | Temporary Hoarding Enclosure (Special Provisions) | lump sum | 1 | 500000 | 500000 | 519716.15 | 519716.15 | 57.7%
X018 | Vessel Condition Survey (Special Provisions) | lump sum | 1 | 30000 | 30000 | 44648.21 | 44648.21 | 37.4%
X018 | Structural Repair Type A - Hull Shell Plate Deformation in Way of Frames (Special Provisions) | lump sum | 1 | 30000 | 30000 | 79910.74 | 79910.74 | 38.5%
X022 | Structural Repair Type B - Hull or Bulkhead Plate Deformation Between Frames (Special Provisions) | square metre | 2.5 | 24000 | 60000 | 56667.59 | 141668.98 | 77.3%
X020 | Structural Repair Type C - Steel Framing Member Deformations (Special Provisions) | metre | 2 | 7500 | 15000 | 11883.92 | 23767.84 | 44.9%
X019 | Structural Repair Type D - Triangular Bracket Deformations (Special Provisions) | repair | 13 | 2500 | 32500 | 2333.69 | 30337.97 | 18.2%
X018 | Structural Repairs - Leak Tests (Special Provisions) | lump sum | 1 | 50000 | 50000 | 36355.73 | 36355.73 | 85.3%
F151 | Protection of the Environment (B.F. 9125) (BCS 22.25.1) (Special Provisions) | lump sum | 1 | 75000 | 75000 | 133337.38 | 133337.38 | 92.8%
X018 | Coating Replacement 1A - Hull Exterior (Deck) (Special Provisions) | lump sum | 1 | 203000 | 203000 | 114908.85 | 114908.85 | 59.4%
X018 | Coating Replacement 1P - Hull Exterior (Sides, Upper Chine to Dividing Line, Incl. Jacking Points) (Special Provisions) | lump sum | 1 | 48750 | 48750 | 37794.2 | 37794.2 | 45.1%
X018 | Coating Replacement 1R - Hull Exterior (Sides and Bottom, Keel to Dividing Line) (Special Provisions) | lump sum | 1 | 162500 | 162500 | 133540.25 | 133540.25 | 52.7%
X018 | Coating Replacement 1W - Hull Exterior (Sides, Upper Chine to Deck) (Special Provisions) | lump sum | 1 | 13750 | 13750 | 21275.12 | 21275.12 | 62.8%
X018 | Coating Replacement 2A - Hinged Ramps (Deck) (Special Provisions) | lump sum | 1 | 70000 | 70000 | 53333.37 | 53333.37 | 49.4%
X018 | Coating Replacement 2B - Hinged Ramps (Underside and Interior Surfaces) (Special Provisions) | lump sum | 1 | 153000 | 153000 | 77954.21 | 77954.21 | 65.5%
X018 | Coating Replacement 2P - Hinged Ramps (Ramp Ends) (Special Provisions) | lump sum | 1 | 52000 | 52000 | 38098.82 | 38098.82 | 43.6%
X018 | Coating Replacement 2W - Hinged Ramps (Exterior Side Surfaces) (Special Provisions) | lump sum | 1 | 12000 | 12000 | 18637.16 | 18637.16 | 74.9%
X018 | Coating Replacement 3C - Hull Interior (Floor, Stiffeners, Beams, 150 mm up all Vertical Surfaces, Maintenance Hole Covers and Access Frames) (Special Provisions) | lump sum | 1 | 445000 | 445000 | 242920.77 | 242920.77 | 44.8%
X018 | Coating Replacement 4B - Bolster Arms (Special Provisions) | lump sum | 1 | 35000 | 35000 | 30464.87 | 30464.87 | 50.6%
X018 | Coating Replacement 5A - Deck Houses and Boarding Platforms (Walking Surfaces) (Special Provisions) | lump sum | 1 | 14000 | 14000 | 36792.81 | 36792.81 | 89.5%
X018 | Coating Replacement 5W - Deck Houses and Boarding Platforms (Steel Framing) (Special Provisions) | lump sum | 1 | 27000 | 27000 | 30160.26 | 30160.26 | 52.5%
X018 | Coating Replacement 6B - Railings (Rails, Posts, Gates, Pike Pole Brackets) (Special Provisions) | lump sum | 1 | 21000 | 21000 | 27884.35 | 27884.35 | 54.6%
X018 | Coating Replacement 6G - Railings (Expanded Mesh Panels) (Special Provisions) | lump sum | 1 | 30000 | 30000 | 69466.67 | 69466.67 | 61.6%
X018 | Coating Replacement 7B - Deck Attachments (Wheel Fenders, Bollards, Davits, Vents) (Special Provisions) | lump sum | 1 | 15000 | 15000 | 27275.12 | 27275.12 | 59%
X018 | Coating Replacement 7O - Overcoating (Deck Houses - Window Frames and Door Frames; Drag House Steel Framing, Drag Cable Frame, Drag Wheel, Brochure Boxes, Life Jacket Boxes) (Special Provisions) | lump sum | 1 | 15000 | 15000 | 24246.4 | 24246.4 | 54.4%
X018 | Coating Replacement 7W - Deck Attachments (Flag Masts, Warping Cable/Drag Cable/Traction Cable Connections, Towing Lugs, Apron Hooks, Drag Cable Frame, Drag Wheel, Pike Poles) (Special Provisions) | lump sum | 1 | 10000 | 10000 | 16361.26 | 16361.26 | 92.6%
X018 | Coating Replacement 8A - Steel Shore Ramps (Deck) (Special Provisions) | lump sum | 1 | 70000 | 70000 | 56666.7 | 56666.7 | 48.6%
X018 | Coating Replacement 8R - Steel Shore Ramps (All Other Surfaces) (Special Provisions) | lump sum | 1 | 279500 | 279500 | 157173.17 | 157173.17 | 37.1%
X022 | Isolated Full Depth Coating Repairs - Hull Interior (3D) (Special Provisions) | square metre | 70 | 750 | 52500 | 539.41 | 37758.7 | 71.5%
X052 | Desiccant Packs - Supply and Install (Special Provisions) | unit | 36 | 100 | 3600 | 218.89 | 7880.04 | 49.2%
X052 | Maintenance Hole Covers - Bolt and Gasket Replacement (Special Provisions) | unit | 11 | 1000 | 11000 | 1140.25 | 12542.75 | 49%
X018 | Neoprene Bumper Pads - Supply and Install (Special Provisions) | lump sum | 1 | 10000 | 10000 | 8937.29 | 8937.29 | 10.4%
X018 | New Vessel Signage - Install (Special Provisions) | lump sum | 1 | 1000 | 1000 | 9757.97 | 9757.97 | 132.2%
X018 | Hydro Seeding (Special Provisions) | lump sum | 1 | 5000 | 5000 | 7509.9 | 7509.9 | 71.8%
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | 100000 | 100000 | 0%
|  | Bridge File Modified Tender Value |  |  | 3233222 |  | 3109116.37 | 8.9%
|  | Total Tender Value |  |  |  |  | 3271116.18 | 5.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 110 | 165000 | 108 | 162000 | 70.7%
Tender: 22729 ¦ Bridge File: 9125-1 ¦ Tender Opening Date: 2023-05-10
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22125 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2023-2024 | 2023-05-11 | 1 | 2023-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
2298-2 | 2 km Southeast of Pincher Creek | Southern | 507:04 | Kettles Creek | 8 x 510 SLC | 14 | 14 | 9.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 130000 | 130000 | - | - | -
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 55000 | 55000 | - | - | -
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 15000 | 15000 | - | - | -
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 1000 | 3000 | - | - | -
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 700 | 7000 | - | - | -
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 50000 | 50000 | - | - | -
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 30000 | 30000 | - | - | -
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 15000 | 15000 | - | - | -
F196 | Backfill - Non-Granular (BCS 2.4) | lump sum | 1 | 12000 | 12000 | - | - | -
F204 | Backfill - Crushed Aggregate (BCS 2.4) | lump sum | 1 | 18000 | 18000 | - | - | -
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 448 | 450 | 201600 | - | - | -
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 14 | 6000 | 84000 | - | - | -
F818 | Pile Driving (BCS 3.6.1) | metre | 448 | 140 | 62720 | - | - | -
F819 | Pile Tip Reinforcement (BCS 3.6.1) | pile | 14 | 300 | 4200 | - | - | -
F820 | PDA Testing (BCS 3.6.4) | test | 4 | 2500 | 10000 | - | - | -
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 3730 | 3.5 | 13055 | - | - | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 5299 | 8.5 | 45041.5 | - | - | -
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 424 | 16 | 6784 | - | - | -
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 9453 | 2.85 | 26941.05 | - | - | -
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 25.45 | 1600 | 40720 | - | - | -
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 46.73 | 2500 | 116825 | - | - | -
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) | lump sum | 1 | 255000 | 255000 | - | - | -
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 5500 | 5500 | - | - | -
F905 | Bearings - Supply and Delivery (BCS 8.5) | lump sum | 1 | 15500 | 15500 | - | - | -
F974 | Waterproofing (BCS 16.5) | square metre | 238 | 105 | 24990 | - | - | -
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 100 | 275 | 27500 | - | - | -
F780 | Bridgerail - Supply and Install (BCS 12.4) | lump sum | 1 | 32000 | 32000 | - | - | -
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 3 | 4500 | 13500 | - | - | -
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 47 | 22 | 1034 | - | - | -
X510 | Cutting of Pavement (HCS 3.40.3) | metre | 18 | 10 | 180 | - | - | -
Q565 | Cold Milling Asphalt Pavement (HCS 3.16.6) | square metre | 425 | 10 | 4250 | - | - | -
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 120 | 365 | 43800 | - | - | -
G225 | Common Excavation (HCS 2.3.6) | cubic metre | 1000 | 8.5 | 8500 | - | - | -
G235 | Borrow Excavation (HCS 2.3.6) | cubic metre | 500 | 10 | 5000 | - | - | -
S352 | Roadway Lines - Supplying Paint and Painting (Lane Dividing Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.1 | 10000 | 1000 | - | - | -
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 100 | 21.7 | 2170 | - | - | -
G300 | Topsoil Placement (HCS 2.6.4) | square metre | 1000 | 5 | 5000 | - | - | -
C232 | Hydroseeding (HCS 2.20.4) | square metre | 1000 | 2.75 | 2750 | - | - | -
|  | Bridge File Modified Tender Value |  |  | 1394560.55 |  | - | -
|  | Total Tender Value |  |  |  |  | - | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 70 | 105000 | - | - | -
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 90 | 135000 | - | - | -
Tender: 22125 ¦ Bridge File: 2298-2 ¦ Tender Opening Date: 2023-05-11
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21916 | Construct SLW Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2023-2024 | 2023-06-07 | 3 | 2023-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
6893-2 | 22 km Northeast of Torrington | Central | 587:04 | Threehills Creek | 8 x 510 SLW | 8 ¦ 14 ¦ 8 | 30 | 9.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 210000 | 210000 | 243198.78 | 243198.78 | 5.1%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 40000 | 40000 | 54539.94 | 54539.94 | 38.6%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 40000 | 40000 | 28899.73 | 28899.73 | 56.8%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 2297.44 | 6892.32 | 61.7%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 1500 | 9000 | 1492.9 | 8957.4 | 70.9%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 75000 | 75000 | 145971.13 | 145971.13 | 36%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 35977.66 | 35977.66 | 71.1%
F813 | Supply of Piling - Galvanized Steel H-Pile (BCS 3.6.1) | metre | 216 | 350 | 75600 | 179.4 | 38750.4 | 65.7%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 468 | 250 | 117000 | 136.57 | 63914.76 | 64.5%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 32 | 5000 | 160000 | 7339.67 | 234869.44 | 47.7%
F818 | Pile Driving (BCS 3.6.1) | metre | 684 | 30 | 20520 | 25.23 | 17257.32 | 99.7%
F018 | Abutment Construction (Special Provisions) | lump sum | 1 | 160000 | 160000 | 164563.16 | 164563.16 | 18.1%
F018 | Pier Construction (Special Provisions) | lump sum | 1 | 100000 | 100000 | 91694.74 | 91694.74 | 9.4%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1500 | 7.25 | 10875 | 7.5 | 11250 | 9.4%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1500 | 2.5 | 3750 | 2.26 | 3390 | 33.4%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 12 | 2000 | 24000 | 2608.98 | 31307.76 | 25.8%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 200 | 300 | 60000 | 209.27 | 41854 | 18.3%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 8 m Type SLW 510 (12 Interior, 4 Exterior) (BCS 7.4) | lump sum | 1 | 220000 | 220000 | 234786.29 | 234786.29 | 13.2%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 14 m Type SLW 510 (6 Interior, 2 Exterior) (BCS 7.4) | lump sum | 1 | 200000 | 200000 | 216901.47 | 216901.47 | 12.6%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 5000 | 5000 | 1873.74 | 1873.74 | 24%
F974 | Waterproofing (BCS 16.5) | square metre | 324 | 80 | 25920 | 87.36 | 28304.64 | 12.2%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 61 | 400 | 24400 | 478.77 | 29204.97 | 12.4%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 400000 | 400000 | 602041.44 | 602041.44 | 26.2%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 50000 | 50000 | 32753.68 | 32753.68 | 16.5%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 40000 | 40000 | 35531.71 | 35531.71 | 9.1%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 10 | 2000 | 8.52 | 1704 | 14.4%
E020 | Straw Rolls (Special Provisions) | metre | 200 | 20 | 4000 | 21.55 | 4310 | 77.9%
|  | Bridge File Modified Tender Value |  |  | 2114065 |  | 2410700.48 | 7%
|  | Total Tender Value |  |  |  |  | 2495706.67 | 6.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 60 | 90000 | 57 | 85500 | 39.4%
Tender: 21916 ¦ Bridge File: 6893-2 ¦ Tender Opening Date: 2023-06-07
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23534 | Construct Sign Structures | Sign Structure | Highway | New Sign Structures | 2023-2024 | 2023-06-15 | 4 | 2024-10-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
Multiple | Deerfoot Trail | Southern | - | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 585539.14 | 585539.14 | 944021.36 | 944021.36 | 24.5%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 156149.18 | 156149.18 | 505234.25 | 505234.25 | 21.4%
F046 | Sign Panels (Overhead) - Extruded Aluminum - Remove and Dispose (Special Provisions) | panel | 4 | 200 | 800 | 4663.18 | 18652.72 | 7.7%
X038 | Overhead Bridge Sign Structure and Sign Panels - Remove and Dispose (Special Provisions) | sign | 7 | 35000 | 245000 | 19871.76 | 139102.32 | 12%
X038 | Overhead Cantilever Sign Structure and Sign Panels - Remove and Dispose (Special Provisions) | sign | 2 | 25000 | 50000 | 17349.34 | 34698.68 | 3.5%
X011 | Overhead Sign Structure - Foundation Demolition and Disposal (Special Provisions) | bases | 16 | 6500 | 104000 | 5745.82 | 91933.12 | 7.1%
F992 | Sign Panels - Extruded Aluminum - Supply and Install (BCS 24.5) | square metre | 847 | 550 | 465850 | 540.31 | 457642.57 | 5.5%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 73794ZSX) (BCS 24.5) | lump sum | 1 | 220000 | 220000 | 276791.42 | 276791.42 | 8.8%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77251ZSX) (BCS 24.5) | lump sum | 1 | 250000 | 250000 | 324183.75 | 324183.75 | 2%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77199ZN2) (BCS 24.5) | lump sum | 1 | 450000 | 450000 | 515508.82 | 515508.82 | 11.1%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77199ZN3) (BCS 24.5) | lump sum | 1 | 290000 | 290000 | 337434.42 | 337434.42 | 7.2%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77199ZSX) (BCS 24.5) | lump sum | 1 | 290000 | 290000 | 293863.87 | 293863.87 | 6.2%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77198ZN1) (BCS 24.5) | lump sum | 1 | 220000 | 220000 | 273036.79 | 273036.79 | 10.8%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77199ZS3) (BCS 24.5) | lump sum | 1 | 290000 | 290000 | 348681.41 | 348681.41 | 7.2%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77199ZS2) (BCS 24.5) | lump sum | 1 | 450000 | 450000 | 537111.62 | 537111.62 | 7.8%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77199ZS1) (BCS 24.5) | lump sum | 1 | 290000 | 290000 | 359743.96 | 359743.96 | 7.3%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77198ZN2) (BCS 24.5) | lump sum | 1 | 290000 | 290000 | 289990 | 289990 | 7.7%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77198ZN3) (BCS 24.5) | lump sum | 1 | 450000 | 450000 | 535039.6 | 535039.6 | 7.4%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77198ZN4) (BCS 24.5) | lump sum | 1 | 290000 | 290000 | 337178.62 | 337178.62 | 7.3%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 81800ZN1) (BCS 24.5) | lump sum | 1 | 220000 | 220000 | 258028.89 | 258028.89 | 2.9%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 77198ZSX) (BCS 24.5) | lump sum | 1 | 450000 | 450000 | 512217.86 | 512217.86 | 2.5%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection (B.F. 81800ZN3) (BCS 24.5) | lump sum | 1 | 450000 | 450000 | 504590.82 | 504590.82 | 7.3%
|  | Bridge File Modified Tender Value |  |  | 6507338.32 |  | 7894686.87 | 3.3%
|  | Total Tender Value |  |  |  |  | 46825796.98 | 4.6%
Tender: 23534 ¦ Bridge File: Multiple ¦ Tender Opening Date: 2023-06-15
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22567 | Construct CSP Culvert | Culvert | Single | Replace Bridge with Culvert | 2023-2024 | 2023-06-27 | 1 | 2023-11-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
1404-2 | 14 km West of Morningside | Central | 604:02 | Tributary to Whelp Brook | 1 x 2200 CSP | 35 | 35 | 2.2
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 58213 | 58213 | - | - | -
A805 | Supply of Aggregate - No Option (HCS 5.2.5) | tonne | 650 | 2.5 | 1625 | - | - | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 01404) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 40000 | 40000 | - | - | -
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1000 | 10000 | - | - | -
X052 | Fish Capture and Release (Special Provisions) | unit | 5 | 1000 | 5000 | - | - | -
X018 | Removal and Demolition of Building (Special Provisions) | lump sum | 1 | 75000 | 75000 | - | - | -
G106 | Clearing, Timber Salvage and Mulching (HCS 2.1.4) (Special Provisions) | hectare | 0.56 | 25000 | 14000 | - | - | -
G452 | Remove and Dispose of Existing Fence (HCS 2.12.5) | kilometre | 1 | 5000 | 5000 | - | - | -
G470 | New Fence - Supply and Install - Class A (HCS 2.12.5) (Special Provisions) | kilometre | 0.8 | 7500 | 6000 | - | - | -
G014 | New Fence - Supply and Install Class F (Mod1) (60 inch Paige Wire) (Special Provisions) | kilometre | 0.8 | 25000 | 20000 | - | - | -
G225 | Common Excavation (HCS 2.3.6) | cubic metre | 8500 | 8.5 | 72250 | - | - | -
G236 | Borrow Excavation - Contractor Supplied (HCS 2.3.6) | cubic metre | 10000 | 25 | 250000 | - | - | -
G300 | Topsoil Placement (HCS 2.6.4) | square metre | 8500 | 1.2 | 10200 | - | - | -
D100 | Culverts - Remove and Dispose (C.S.P.) (up to 700 mm dia.) (HCS 2.4.4) | metre | 60 | 100 | 6000 | - | - | -
B180 | Preparing Subgrade Surface (First Layer) (HCS 3.1.3) | square metre | 4400 | 2 | 8800 | - | - | -
Q186 | Gravel Surfacing Des. 4 Class 25 (HCS 3.3.4) (HCS 5.2.5) | tonne | 650 | 35 | 22750 | - | - | -
F170 | Demolition and Disposal of Bridge Structure (B.F. 01404) (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 20000 | 20000 | - | - | -
F186 | Excavation - Structural (B.F. 01404) (BCS 1.6.1) | lump sum | 1 | 9000 | 9000 | - | - | -
F190 | Backfill (B.F. 01404) (BCS 2.4) (Special Provisions) | lump sum | 1 | 28000 | 28000 | - | - | -
F495 | CSP with Couplers - Supply (B.F. 01404) (2200mm) (BCS 18.7) | metre | 35 | 1300 | 45500 | - | - | -
F496 | CSP - Assembly (B.F. 01404) (2200mm) (BCS 18.7) | metre | 35 | 500 | 17500 | - | - | -
F500 | Heavy Rock Riprap (Class 1) (B.F. 01404) (BCS 10.7) | cubic metre | 68 | 250 | 17000 | - | - | -
F018 | De-Icing Line (Special Provisions) | lump sum | 1 | 7200 | 7200 | - | - | -
E020 | Erosion Control Barrier (Straw Rolls) | metre | 120 | 25 | 3000 | - | - | -
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 690 | 15 | 10350 | - | - | -
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 100 | 25 | 2500 | - | - | -
E515 | Synthetic Permeable Ditch Barrier (HCS 6.5.6) | metre | 120 | 35 | 4200 | - | - | -
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.85 | 19750 | 16787.5 | - | - | -
|  | Bridge File Modified Tender Value |  |  | 785875.5 |  | - | -
|  | Total Tender Value |  |  |  |  | - | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 4500 | 20 | 90000 | - | - | -
Tender: 22567 ¦ Bridge File: 1404-2 ¦ Tender Opening Date: 2023-06-27
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20234 | Remove Precast Concrete Girder Bridge | Bridge | Multiple | Remove Bridge | 2023-2024 | 2023-06-29 | 2 | 2023-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74978E-1 | North Boundary of Wabamun | North Central | 16:12 | Mine Haul Road | 7 x 1120 Concrete Stringer | 16 ¦ 16 ¦ 21 ¦ 19 | 72 | 15.2
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 246651.5 | 246651.5 | 320306.7 | 320306.7 | -
X018 | Traffic Accommodation for B.F. 74978E-1 (Special Provisions) | lump sum | 1 | 150000 | 150000 | 145326.5 | 145326.5 | -
X038 | Construction Advisory Sign for B.F. 74978E-1 (Special Provisions) | sign | 1 | 5000 | 5000 | 3665 | 3665 | -
F170 | Demolition and Disposal of Bridge Structure (B.F. 74978E-1) (BCS 21.4.1) | lump sum | 1 | 160000 | 160000 | 203119.38 | 203119.38 | -
X025 | Asphalt Surfacing - Removal and Disposal for B.F. 74978E-1 (Special Provisions) | cubic metre | 1000 | 56 | 56000 | 67.55 | 67550 | -
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 242 | 18 | 4356 | 28.94 | 7003.48 | -
C143 | Salvage and Reinstall Existing Riprap (B.F. 7498E-1) (Special Provisions) | cubic metre | 11 | 210 | 2310 | 573.6 | 6309.6 | -
D100 | Culverts - Remove and Dispose (C.S.P.) (up to 700 mm dia.) (HCS 2.4.4) | metre | 34 | 105 | 3570 | 98.72 | 3356.48 | -
D105 | Culverts - Remove and Dispose (C.S.P.) (over 700 mm dia.) (HCS 2.4.4) | metre | 11 | 130 | 1430 | 149.33 | 1642.63 | -
S376 | Removal of Existing Roadway Lines (HCS 7.2.6) | kilometre | 0.75 | 2500 | 1875 | 9601.7 | 7201.28 | -
X210 | Concrete and Masonry - Remove and Dispose (HCS 2.17.4) | cubic metre | 3.5 | 70 | 245 | 817.13 | 2859.96 | -
D718 | Manhole - Remove and Dispose (HCS 2.17.4) | unit | 1 | 4500 | 4500 | 2241.54 | 2241.54 | -
X220 | Concrete Surface - Remove and Dispose (HCS 2.17.4) | square metre | 2.5 | 40 | 100 | 2063.13 | 5157.83 | -
D018 | Remove Cross-over, Restore and Dispose of Materials B.F. 74978E-1 (Special Provisions) | lump sum | 1 | 112500 | 112500 | 137720.54 | 137720.54 | -
G225 | Common Excavation (HCS 2.3.6) | cubic metre | 5032 | 15 | 75480 | 11.22 | 56459.04 | -
G236 | Borrow Excavation - Contractor Supplied (HCS 2.3.6) | cubic metre | 28515 | 25 | 712875 | 16.71 | 476485.65 | -
X022 | Topsoil, Supply and Placement - Contractor Supplied for B.F. 74978E-1 (Special Provisions) | square metre | 16430 | 25 | 410750 | 6.01 | 98744.3 | -
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.17 | 8000 | 1360 | 37844.12 | 6433.5 | -
E500 | Erosion Control Soil Covering - Supply and Install (Type A) (HCS 6.5.6) | square metre | 2860 | 11 | 31460 | 4.5 | 12870 | -
G470 | New Fence - Supply and Install - Class A (HCS 2.12.5) | kilometre | 0.22 | 6200 | 1364 | 40539.05 | 8918.59 | -
E454 | Geotextile for Materials Separation - Supply and Install (Class B) (Special Provisions) | square metre | 13 | 6 | 78 | 37.05 | 481.65 | -
D200 | Granular Backfill - Culverts Des. 6 Class 80 (HCS 2.4.4) (HCS 5.2.5) | cubic metre | 181 | 60 | 10860 | 88.26 | 15975.06 | -
D410 | Culverts - Supply and Install (600 mm dia. C.S.P.) (HCS 2.4.4) (HCS 5.23.4) | metre | 307 | 400 | 122800 | 337.41 | 103584.87 | -
D020 | Manholes - Supply and Install (1200 mm dia. x Length) for B.F. 74978E-1 (Special Provisions) | metre | 4 | 4100 | 16400 | 4812.87 | 19251.48 | -
D020 | Manholes - Supply and Install (1500 mm dia x Length) for B.F. 74978E-1 (Special Provisions) | metre | 4 | 4100 | 16400 | 6672.92 | 26691.68 | -
D788 | Corrugated Steel Storm Sewer - Supply and Install (800 mm dia.) (HCS 2.18.4) | metre | 78 | 580 | 45240 | 627.94 | 48979.32 | -
G220 | Channel Excavation (HCS 2.3.6) | cubic metre | 370 | 10 | 3700 | 23.68 | 8761.6 | -
X346 | Hand-Laid Riprap - Other Locations - Supply and Place (HCS 2.5.4) | square metre | 12.5 | 110 | 1375 | 439.95 | 5499.38 | -
D042 | Articulated Concrete Block for B.F. 74978E-1 (Special Provisions) | square metre | 10 | 3100 | 31000 | 948.75 | 9487.5 | -
D018 | Cleaning and Flushing Existing 1400 mm CSP Culvert for B.F. 74978E-1 (Special Provisions) | lump sum | 1 | 50000 | 50000 | 5387.97 | 5387.97 | -
D018 | Inspection of Existing 1400 mm Culvert by CCTV for B.F. 74978E-1 (Special Provisions) | lump sum | 1 | 8000 | 8000 | 4805 | 4805 | -
A805 | Supply of Aggregate - No Option (HCS 5.2.5) | tonne | 9045 | 3 | 27135 | 11.84 | 107092.8 | -
B180 | Preparing Subgrade Surface (First Layer) (HCS 3.1.3) | square metre | 6571.5 | 1 | 6571.5 | 3.08 | 20240.22 | -
B282 | Granular Base Course Des. 2 Class 25 (HCS 3.6.8) (HCS 5.2.5) | tonne | 7104 | 30 | 213120 | 26.05 | 185059.2 | -
Q990 | Asphalt Concrete Pavement - EPS Mix Type H1 (PG 58-28) (HCS 5.2.5) (HCS 3.50.7) | tonne | 1473.5 | 120 | 176820 | 169.52 | 249787.72 | -
Q565 | Cold Milling Asphalt Pavement (HCS 3.16.6) | square metre | 176 | 3 | 528 | 95.21 | 16756.96 | -
S350 | Roadway Lines - Supplying Paint and Painting (Directional Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.75 | 950 | 712.5 | 2208.8 | 1656.6 | -
S355 | Roadway Lines - Supplying Paint and Painting (Directional Dividing and 1 Edge Line) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.75 | 800 | 600 | 1717.1 | 1287.83 | -
|  | Bridge File Modified Tender Value |  |  | 2713166.5 |  | 2404158.84 | -
|  | Total Tender Value |  |  |  |  | 4721151.59 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy - B.F. 74978E-1 (GCS 1.2.41.9) | day | 2500 | - | - | 46 | 115000 | -
Tender: 20234 ¦ Bridge File: 74978-1 ¦ Tender Opening Date: 2023-06-29
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20234 | Remove Precast Concrete Girder Bridge | Bridge | Multiple | Remove Bridge | 2023-2024 | 2023-06-29 | 2 | 2023-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74978W-2 | North Boundary of Wabamun | North Central | 16:12 | Mine Haul Road | 8 x 1320 VF | 32 ¦ 21 ¦ 20 | 73 | 13.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 217066.7 | 217066.7 | 243618.2 | 243618.2 | -
X018 | Traffic Accommodation for B.F. 74978W-2 (Special Provisions) | lump sum | 1 | 150000 | 150000 | 145326.5 | 145326.5 | -
X038 | Construction Advisory Sign for B.F. 74978W-1 (Special Provisions) | sign | 1 | 5000 | 5000 | 3665 | 3665 | -
F170 | Demolition and Disposal of Bridge Structure (B.F. 74978W-1) (BCS 21.4.1) | lump sum | 1 | 160000 | 160000 | 208619.38 | 208619.38 | -
X025 | Asphalt Surfacing - Removal and Disposal for B.F. 74978W-1 (Special Provisions) | cubic metre | 1000 | 56 | 56000 | 67.55 | 67550 | -
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 242 | 18 | 4356 | 28.94 | 7003.48 | -
C143 | Salvage and Reinstall Existing Riprap (B.F. 74978W-2) (Special Provisions) | cubic metre | 11 | 210 | 2310 | 573.6 | 6309.6 | -
D100 | Culverts - Remove and Dispose (C.S.P.) (up to 700 mm dia.) (HCS 2.4.4) | metre | 34 | 105 | 3570 | 98.72 | 3356.48 | -
S376 | Removal of Existing Roadway Lines (HCS 7.2.6) | kilometre | 0.75 | 2500 | 1875 | 9601.7 | 7201.28 | -
X210 | Concrete and Masonry - Remove and Dispose (HCS 2.17.4) | cubic metre | 3.5 | 70 | 245 | 817.13 | 2859.96 | -
X220 | Concrete Surface - Remove and Dispose (HCS 2.17.4) | square metre | 2.5 | 40 | 100 | 2063.13 | 5157.83 | -
D018 | Remove Cross-over, Restore and Dispose of Materials B.F. 74978W-2 (Special Provisions) | lump sum | 1 | 112500 | 112500 | 137720.54 | 137720.54 | -
G225 | Common Excavation (HCS 2.3.6) | cubic metre | 5032 | 15 | 75480 | 11.22 | 56459.04 | -
G236 | Borrow Excavation - Contractor Supplied (HCS 2.3.6) | cubic metre | 28515 | 25 | 712875 | 16.71 | 476485.65 | -
X022 | Topsoil, Supply and Placement - Contractor Supplied for B.F. 74978W-2 (Special Provisions) | square metre | 16430 | 25 | 410750 | 6.21 | 102030.3 | -
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.17 | 8000 | 1360 | 37844.12 | 6433.5 | -
E500 | Erosion Control Soil Covering - Supply and Install (Type A) (HCS 6.5.6) | square metre | 2860 | 11 | 31460 | 4.5 | 12870 | -
G470 | New Fence - Supply and Install - Class A (HCS 2.12.5) | kilometre | 0.22 | 6200 | 1364 | 40539.05 | 8918.59 | -
D200 | Granular Backfill - Culverts Des. 6 Class 80 (HCS 2.4.4) (HCS 5.2.5) | cubic metre | 181 | 60 | 10860 | 88.26 | 15975.06 | -
G220 | Channel Excavation (HCS 2.3.6) | cubic metre | 370 | 10 | 3700 | 23.68 | 8761.6 | -
X346 | Hand-Laid Riprap - Other Locations - Supply and Place (HCS 2.5.4) | square metre | 12.5 | 110 | 1375 | 439.95 | 5499.38 | -
A805 | Supply of Aggregate - No Option (HCS 5.2.5) | tonne | 9045 | 3 | 27135 | 11.84 | 107092.8 | -
B180 | Preparing Subgrade Surface (First Layer) (HCS 3.1.3) | square metre | 6571.5 | 1 | 6571.5 | 3.08 | 20240.22 | -
B282 | Granular Base Course Des. 2 Class 25 (HCS 3.6.8) (HCS 5.2.5) | tonne | 7104 | 30 | 213120 | 26.05 | 185059.2 | -
Q990 | Asphalt Concrete Pavement - EPS Mix Type H1 (PG 58-28) (HCS 5.2.5) (HCS 3.50.7) | tonne | 1473.5 | 120 | 176820 | 169.52 | 249787.72 | -
Q565 | Cold Milling Asphalt Pavement (HCS 3.16.6) | square metre | 176 | 3 | 528 | 95.21 | 16756.96 | -
S350 | Roadway Lines - Supplying Paint and Painting (Directional Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.75 | 950 | 712.5 | 2208.8 | 1656.6 | -
S355 | Roadway Lines - Supplying Paint and Painting (Directional Dividing and 1 Edge Line) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.75 | 800 | 600 | 1717.1 | 1287.83 | -
|  | Bridge File Modified Tender Value |  |  | 2387733.7 |  | 2113702.7 | -
|  | Total Tender Value |  |  |  |  | 4721151.59 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (B.F. 74978W-2) (GCS 1.2.41.9) | day | 2500 | - | - | 36 | 90000 | -
Tender: 20234 ¦ Bridge File: 74978-2 ¦ Tender Opening Date: 2023-06-29
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22927 | Bridge Flood Damage Repair | Bridge | Single | Bridge Repair | 2023-2024 | 2023-07-06 | 5 | 2023-12-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75425-1 | Near Slave Lake | North Central | Local Road | Lily Creek | Bailey Truss | 21 | 21 | 3.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 68734 | 68734 | 197283.33 | 197283.33 | 83.8%
F189 | Excavation - Channel (B.F. 75425) (BCS 1.6.1) | cubic metre | 1600 | 31 | 49600 | 26.67 | 42672 | 24.8%
F203 | Backfill - Crushed Aggregate (B.F. 75425) Des. 2 Class 25 (BCS 2.4) | cubic metre | 1960 | 75 | 147000 | 137.82 | 270127.2 | 11.7%
F195 | Backfill - Non-Granular (B.F. 75425) (BCS 2.4) | cubic metre | 2670 | 35 | 93450 | 65.93 | 176033.1 | 29.4%
F515 | Heavy Rock Riprap (Class 2) (B.F. 75425) (BCS 10.7) | cubic metre | 96 | 250 | 24000 | 419 | 40224 | 14.3%
F500 | Heavy Rock Riprap (Class 1) (B.F. 75425) (BCS 10.7) | cubic metre | 193 | 280 | 54040 | 474.33 | 91545.69 | 19.6%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 1500 | 1500 | 32700 | 32700 | 65.6%
F018 | Timber Backwall - Supply and Install (Special Provisions) | lump sum | 1 | 6000 | 6000 | 47500 | 47500 | 50.6%
F018 | Debris Removal (Special Provisions) | lump sum | 1 | 10000 | 10000 | 11133.33 | 11133.33 | 110.2%
E021 | Gabion Baskets - Supply and Install (Special Provisions) | cubic metre | 30 | 1700 | 51000 | 1233 | 36990 | 37.8%
E022 | Dense Live Toe Staking (Special Provisions) | square metre | 240 | 600 | 144000 | 716.38 | 171931.2 | 41.9%
E022 | Low Density Staking with Willow (Special Provisions) | square metre | 540 | 50 | 27000 | 78.03 | 42136.2 | 6.6%
E020 | Wildlife Fence (Special Provisions) | metre | 95 | 50 | 4750 | 120.07 | 11406.65 | 68.8%
E612 | Fish Capture, Salvage and Release (Special Provisions) | day | 10 | 3000 | 30000 | 1982.33 | 19823.3 | 73%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1500 | 15000 | 1136.33 | 11363.3 | 72.4%
|  | Bridge File Modified Tender Value |  |  | 726074 |  | 1202869.3 | 12.1%
|  | Total Tender Value |  |  |  |  | 1250369.33 | 11.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 60 | 90000 | 32 | 48000 | 7.4%
Tender: 22927 ¦ Bridge File: 75425-1 ¦ Tender Opening Date: 2023-07-06
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23062 | Construct CSP Culvert | Culvert | Multiple | New Culvert | 2023-2024 | 2023-07-27 | 4 | 2023-12-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
85370-1 | 4 km North of Cadomin | North Central | 40:28 | Tributary to Luscar Creek | 1 x 1600 CSP | 25 | 25 | 1.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 37000 | 37000 | 124302.53 | 124302.53 | 69.9%
F750 | Traffic Accommodation for Bridge Construction (B.F. 85370) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 80000 | 80000 | 34984.17 | 34984.17 | 81.3%
X018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 30000 | 30000 | 37845.83 | 37845.83 | 106.8%
E612 | Fish Capture, Salvage, and Release (Special Provisions) | day | 2 | 1500 | 3000 | 4011.42 | 8022.84 | 71.2%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 2 | 1200 | 2400 | 3358.79 | 6717.58 | 91.8%
F186 | Excavation - Structural (B.F. 85370) (BCS 1.6.1) | lump sum | 1 | 30000 | 30000 | 15206.67 | 15206.67 | 34.1%
F170 | Demolition and Disposal of Bridge Structure (B.F. 85370) (BCS 21.4.1) | lump sum | 1 | 4000 | 4000 | 5708.33 | 5708.33 | 52.3%
F495 | CSP with Couplers - Supply (B.F. 85370) (1600 mm Dia.) (BCS 18.7) | metre | 25 | 2000 | 50000 | 1056.07 | 26401.75 | 8.5%
F496 | CSP - Assembly (B.F. 85370) (1600 mm Dia.) (BCS 18.7) | metre | 25 | 1600 | 40000 | 422.32 | 10558 | 94.5%
F190 | Backfill (B.F. 85370) (BCS 2.4) | lump sum | 1 | 40000 | 40000 | 56517.86 | 56517.86 | 45.2%
F505 | Heavy Rock Riprap (Class 1M) (B.F. 85370) (BCS 10.7) (Special Provisions) | cubic metre | 7 | 350 | 2450 | 699.54 | 4896.78 | 51.7%
F500 | Heavy Rock Riprap (Class 1) (B.F. 85370) (BCS 10.7) (Special Provisions) | cubic metre | 39 | 320 | 12480 | 259.17 | 10107.63 | 28.3%
F492 | Roadway Work (B.F. 85370) (BCS 18.7) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 35426.14 | 35426.14 | 24.2%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 600 | 8 | 4800 | 12.93 | 7758 | 38.8%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 300 | 15 | 4500 | 15.67 | 4701 | 48.4%
E020 | Erosion Control Barrier (Fibre Rolls) (Special Provisions) | metre | 300 | 20 | 6000 | 20.47 | 6141 | 22.8%
E052 | Potted Willow (~1 Gallon Pot) (Special Provisions) | unit | 111 | 50 | 5550 | 55.58 | 6169.38 | 49.5%
E052 | Potted Conifer (~1 Gallon Pot) (Special Provisions) | unit | 12 | 80 | 960 | 288.6 | 3463.2 | 102.1%
E018 | Rootwad Structures (Special Provisions) | lump sum | 1 | 5000 | 5000 | 6873.33 | 6873.33 | 50.3%
|  | Bridge File Modified Tender Value |  |  | 408140 |  | 411802.02 | 24.2%
|  | Total Tender Value |  |  |  |  | 1100156.79 | 16.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 15 | 22500 | 19 | 28500 | 30.2%
Tender: 23062 ¦ Bridge File: 85370-1 ¦ Tender Opening Date: 2023-07-27
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23062 | Construct CSP Culvert | Culvert | Multiple | New Culvert | 2023-2024 | 2023-07-27 | 4 | 2023-12-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
85371-1 | 22 km Southeast of Hinton | North Central | 40:28 | Tributary to Teepee Creek | 1 x 2200 CSP | 42 | 42 | 2.2
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 67000 | 67000 | 145073.97 | 145073.97 | 64.9%
F750 | Traffic Accommodation for Bridge Construction (B.F. 85371) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 120000 | 120000 | 36634.17 | 36634.17 | 75.2%
X018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 10000 | 10000 | 37937.5 | 37937.5 | 106.4%
E612 | Fish Capture, Salvage, and Release (Special Provisions) | day | 2 | 1500 | 3000 | 4011.42 | 8022.84 | 71.2%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 2 | 1200 | 2400 | 3358.79 | 6717.58 | 91.8%
F186 | Excavation - Structural (B.F. 85371) (BCS 1.6.1) | lump sum | 1 | 60000 | 60000 | 26903.33 | 26903.33 | 47.2%
F170 | Demolition and Disposal of Bridge Structure (B.F. 85371) (BCS 21.4.1) | lump sum | 1 | 10000 | 10000 | 7570 | 7570 | 29.8%
F495 | CSP with Couplers - Supply (B.F. 85371) (2200 mm Dia) (BCS 18.7) | metre | 42 | 2600 | 109200 | 1376.49 | 57812.58 | 2.5%
F496 | CSP - Assembly (B.F. 85371) (BCS 18.7) | metre | 42 | 1800 | 75600 | 532.27 | 22355.34 | 105.9%
F190 | Backfill (B.F. 85371) (BCS 2.4) | lump sum | 1 | 80000 | 80000 | 107864.75 | 107864.75 | 29.7%
F505 | Heavy Rock Riprap (Class 1M) (B.F. 85371) (BCS 10.7) | cubic metre | 28 | 350 | 9800 | 518.6 | 14520.8 | 46.2%
F500 | Heavy Rock Riprap (Class 1) (B.F. 85371) (BCS 10.7) | cubic metre | 50 | 320 | 16000 | 270.11 | 13505.5 | 32.9%
F492 | Roadway Work (B.F. 85371) (BCS 18.7) (Special Provisions) | lump sum | 1 | 150000 | 150000 | 92195.69 | 92195.69 | 20.9%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 600 | 8 | 4800 | 12.93 | 7758 | 38.8%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 400 | 15 | 6000 | 15.3 | 6120 | 47.7%
E020 | Erosion Control Barrier (Fibre Rolls) (Special Provisions) | metre | 400 | 20 | 8000 | 20.1 | 8040 | 20.9%
E052 | Potted Willow (~1 Gallon Pot) (Special Provisions) | unit | 70 | 50 | 3500 | 56.74 | 3971.8 | 51.2%
E052 | Willow Stick (Special Provisions) | unit | 250 | 30 | 7500 | 44.48 | 11120 | 76.9%
E052 | Potted Conifer (~1 Gallon Pot) (Special Provisions) | unit | 19 | 80 | 1520 | 281.85 | 5355.15 | 105.8%
E018 | Rootwad Structure (Special Provisions) | lump sum | 1 | 5000 | 5000 | 6873.33 | 6873.33 | 50.3%
|  | Bridge File Modified Tender Value |  |  | 749320 |  | 626352.33 | 10%
|  | Total Tender Value |  |  |  |  | 1100156.79 | 16.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 30 | 45000 | 22 | 33000 | 26.8%
Tender: 23062 ¦ Bridge File: 85371-1 ¦ Tender Opening Date: 2023-07-27
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20343 | Construct WSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2023-2024 | 2023-08-17 | 1 | 2024-06-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
9851-2 | 29 km East of Ardrossan | Central | 16:22 | Norris Creek | 1 x 2740 WSP | 72 | 72 | 2.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 145000 | 145000 | - | - | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 09851) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 25000 | 25000 | - | - | -
F186 | Excavation - Structural (B.F. 09851) (BCS 1.6.1) (Special Provisions) | lump sum | 1 | 15000 | 15000 | - | - | -
D018 | CSP Bevel Ends - Remove and Dispose (Special Provisions) | lump sum | 1 | 6500 | 6500 | - | - | -
D020 | WSP - Supply (2743 mm dia.) (Special Provisions) | metre | 72 | 6750 | 486000 | - | - | -
D020 | WSP - Install (2743 mm dia.) (Special Provisions) | metre | 72 | 6750 | 486000 | - | - | -
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 180 | 650 | 117000 | - | - | -
F204 | Backfill - Crushed Aggregate (B.F. 09851) (BCS 2.4) | lump sum | 1 | 12000 | 12000 | - | - | -
F195 | Backfill - Non-Granular (B.F. 09851) (BCS 2.4) | cubic metre | 550 | 60 | 33000 | - | - | -
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 1500 | 1500 | - | - | -
D018 | Steel Median Drain (Special Provisions) | lump sum | 1 | 8000 | 8000 | - | - | -
F500 | Heavy Rock Riprap (Class 1) (B.F. 09851) (BCS 10.7) | cubic metre | 85 | 300 | 25500 | - | - | -
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 1500 | 15 | 22500 | - | - | -
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 150 | 15 | 2250 | - | - | -
G452 | Remove and Dispose of Existing Fence (HCS 2.12.5) | kilometre | 0.03 | 100000 | 3000 | - | - | -
G483 | New Fence - Supply and Install - Class F (HCS 2.12.5) | kilometre | 0.05 | 150000 | 7500 | - | - | -
E052 | Total Suspended Soilds (TSS) Testing (Special Provisions) | unit | 15 | 1000 | 15000 | - | - | -
E052 | Fish Capture and Release (Special Provisions) | unit | 2 | 3750 | 7500 | - | - | -
E018 | Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 5000 | 5000 | - | - | -
|  | Bridge File Modified Tender Value |  |  | 1423250 |  | - | -
|  | Total Tender Value |  |  |  |  | - | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 45 | 67500 | - | - | -
Tender: 20343 ¦ Bridge File: 9851-2 ¦ Tender Opening Date: 2023-08-17
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23872 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2023-08-30 | 3 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
73810W-1 | 5 km Northwest of Whitecourt | North Central | 43:14 | Athabasca River | 8 x 1270 VF | 24 ¦ 38 ¦ 38 ¦ 31 ¦ 31 ¦ 24 | 186 | 13.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 450000 | 450000 | 1007633.33 | 1007633.33 | 18.2%
F750 | Traffic Accommodation for Bridge Construction (Special Provisions) | lump sum | 1 | 250000 | 250000 | 389250 | 389250 | 61.8%
F018 | Care of Birds (Special Provisions) | lump sum | 1 | 75000 | 75000 | 132833.33 | 132833.33 | 30.7%
F755 | Surface Removal (B.F. 73810W-1) (BCS 20.6.1) | square metre | 2282 | 80 | 182560 | 113.67 | 259394.94 | 17%
F022 | ACP Surface Removal (Special Provisions) | square metre | 549 | 60 | 32940 | 49.33 | 27082.17 | 30.4%
F018 | Removal and Disposal of Bridge Components (Special Provisions) | lump sum | 1 | 300000 | 300000 | 442216.67 | 442216.67 | 24%
F760 | Partial Depth Repair - Deck/Girder Top (BCS 20.6.2) | square metre | 115 | 1150 | 132250 | 730 | 83950 | 27.5%
F760 | Partial Depth Repair - Girders (Underside, Legs, etc.) (BCS 20.6.2) | square metre | 25 | 3500 | 87500 | 3710 | 92750 | 42.7%
F760 | Partial Depth Repair - Curbs (Face and Top) (BCS 20.6.2) | square metre | 60 | 1150 | 69000 | 1733.33 | 103999.8 | 23.2%
F760 | Partial Depth Repair - Curbs (Fascia and Soffit) (BCS 20.6.2) | square metre | 60 | 2500 | 150000 | 3070 | 184200 | 33.7%
F760 | Partial Depth Repair - Abutments and Wingwalls (BCS 20.6.2) | square metre | 10 | 1850 | 18500 | 3323.33 | 33233.3 | 59%
F760 | Partial Depth Repair - Piers (BCS 20.6.2) | square metre | 10 | 4000 | 40000 | 3486.67 | 34866.7 | 54.6%
F760 | Partial Depth Repair - Shear Keys (BCS 20.6.2) | square metre | 75 | 1150 | 86250 | 3953.33 | 296499.75 | 74.3%
F765 | Full Depth Repair - Deck/Girder Top (BCS 20.6.2) | square metre | 30 | 3500 | 105000 | 1920 | 57600 | 36.5%
F765 | Full Depth Repair - Headslope Protection and Drain Troughs (BCS 20.6.2) | square metre | 10 | 1000 | 10000 | 2815 | 28150 | 35.7%
F020 | Gravity Fed Crack Repairs (curbs, girder/deck top, shear keys) (Special Provisions) | metre | 900 | 75 | 67500 | 70.33 | 63297 | 58.3%
F993 | Galvanic Corrosion Protection - Supply and Install (Special Provisions) | anodes | 795 | 75 | 59625 | 95 | 75525 | 11.4%
F018 | Deck Drain Repairs (Special Provisions) | lump sum | 1 | 25000 | 25000 | 40666.67 | 40666.67 | 114.7%
F019 | Girder Bearing Pad Replacement (Special Provisions) | location | 3 | 30000 | 90000 | 71250 | 213750 | 47.9%
F019 | Bearing Cleaning and Metalizing (Special Provisions) | location | 80 | 1500 | 120000 | 3920 | 313600 | 19.6%
F019 | Girder Bearing Expansion Links (Special Provisions) | location | 20 | 1500 | 30000 | 1266.67 | 25333.4 | 19.7%
F018 | New Underslung Diaphragms (Special Provisions) | lump sum | 1 | 550000 | 550000 | 2143516.67 | 2143516.67 | 22.6%
F770 | Abrasive Blasting - Deck Surface (B.F. 73810W-1) (BCS 20.6.3) | square metre | 2282 | 25 | 57050 | 84 | 191688 | 97.7%
F775 | Deck Overlay Concrete - Supply (Class HPC with Steel Fibres) (BCS 20.6.4) | cubic metre | 148.33 | 1800 | 266994 | 2783.33 | 412851.34 | 32.8%
F776 | Deck Overlay Concrete - Place (B.F. 73810W-1) (BCS 20.6.4) | square metre | 2282 | 150 | 342300 | 189.67 | 432826.94 | 60.1%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation - Type 1 (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 240000 | 240000 | 529216.67 | 529216.67 | 13.6%
F019 | Lateral Post-Tensioning Repairs (Special Provisions) | location | 52 | 2000 | 104000 | 7250 | 377000 | 32.5%
F018 | Abutments, Girder Ends & Curb Modifications (Special Provisions) | lump sum | 1 | 175000 | 175000 | 212333.33 | 212333.33 | 21.7%
F018 | New Approach Slabs (Special Provisions) | lump sum | 1 | 150000 | 150000 | 234066.67 | 234066.67 | 12.4%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation - Cover Plated V-Seal (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 411000 | 411000 | 710466.67 | 710466.67 | 22.2%
F020 | Epoxy Crack Injection Repairs (piers, girders, etc.) (Special Provisions) | metre | 50 | 500 | 25000 | 583.33 | 29166.5 | 39.9%
F014 | Bridgerail Grout Pad Replacements (Special Provisions) | grout pad | 100 | 250 | 25000 | 285 | 28500 | 56.2%
F018 | Bridgerail Repairs (Special Provisions) | lump sum | 1 | 20000 | 20000 | 7100 | 7100 | 39.6%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 65 | 425 | 27625 | 950 | 61750 | 41.4%
F018 | Concrete Cleaning and Sealing (Special Provisions) | lump sum | 1 | 25000 | 25000 | 116366.67 | 116366.67 | 19%
|  | Bridge File Modified Tender Value |  |  | 4800094 |  | 9392681.52 | 15.4%
|  | Total Tender Value |  |  |  |  | 10186172.17 | 17.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy - Bridge Construction (GCS 1.2.41.9) (Special Provisions) | day | 1500 | 140 | 210000 | 280 | 420000 | 52.3%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 150 | 225000 | 249 | 373500 | 32.4%
Tender: 23872 ¦ Bridge File: 73810-1 ¦ Tender Opening Date: 2023-08-30
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22393 | Construct SLC Precast Concrete Girder Bridge | Bridge | Complex | Replace Bridge with Bridge | 2023-2024 | 2023-09-19 | 6 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75695-2 | 36 km Northeast of Ft Vermilion | Peace | 58:10 | Caribou River | 9 x 700 SLC | 20 ¦ 20 ¦ 20 | 60 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 590924.65 | 590924.65 | 769808 | 769808 | 4.2%
F750 | Traffic Accommodation for Bridge Construction (B.F. 75695) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 100000 | 100000 | 10733.33 | 10733.33 | 3.5%
F018 | Option 1- Demolition and Disposal of Bridge Structures (BCS 21.4) (Special Provisions) | lump sum | 1 | 300000 | 300000 | 53666.67 | 53666.67 | 3.5%
F018 | Option 2 - Removal and Salvage of Bridge Structure (BCS 21.4) (Special Provisions) | lump sum | 1 | 400000 | 400000 | 135000 | 135000 | 4%
E018 | Environmental Protection Works (Special Provisions) | lump sum | 1 | 70000 | 70000 | 10733.33 | 10733.33 | 3.5%
C025 | Care of Water (Special Provisions) | lump sum | 1 | 120000 | 120000 | 107333.33 | 107333.33 | 3.5%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 50 | 2000 | 100000 | 25.4 | 1270 | 82.4%
F186 | Excavation - Structural (B.F. 75695) (BCS 1.6.1) | lump sum | 1 | 40000 | 40000 | 12398.6 | 12398.6 | 81%
F190 | Backfill - Crushed Granular, Des 2 Class 25 (B.F. 75695) (BCS 2.4) | lump sum | 1 | 30000 | 30000 | 11103.73 | 11103.73 | 73.9%
F824 | Drill Rig Set-up (Drilled Piles) - 610 mm Dia. Holes (B.F. 75695) (BCS 3.6.2) | pile | 16 | 6000 | 96000 | 12813.33 | 205013.28 | 3.2%
F812 | Supply of Piling - Plain Steel H-Pile - 360 x 132 (B.F. 75695) (BCS 3.6.1) | metre | 304 | 350 | 106400 | 386.07 | 117365.28 | 3.5%
F818 | Pile Driving - Drilled Piles (610 mm dia.) (B.F. 75695) (BCS 3.6.1) | metre | 304 | 250 | 76000 | 10.73 | 3261.92 | 3.5%
F818 | Pile Driving - in Pre-Bored Holes - HP 360 x 132 (B.F. 75695) (BCS 3.6.1) | metre | 304 | 100 | 30400 | 10.73 | 3261.92 | 3.5%
F824 | Drill Rig Set-up (Drilled Piles) - Pipe 760 dia. x 15.9 mm Thick (B.F. 75695) (BCS 3.6.2) | pile | 12 | 6500 | 78000 | 16600 | 199200 | 6.7%
F818 | Pile Driving - Drilled Piles (760 mm dia.) (B.F. 75695) (BCS 3.6.1) | metre | 265 | 300 | 79500 | 10.73 | 2843.45 | 3.5%
F814 | Supply of Piling - Plain Steel Pipe Pile - Pipe 760 dia. x 15.9 mm Thick (B.F. 75695) (BCS 3.6.1) | metre | 146 | 700 | 102200 | 772.13 | 112730.98 | 3.5%
F815 | Supply of Piling - Galvanized Steel Pipe Pile - Pipe 760 dia. x 15.9 mm Thick (B.F. 75695) (BCS 3.6.1) | metre | 119 | 900 | 107100 | 1073.33 | 127726.27 | 3.5%
F818 | Pile Driving - in Pre-Bored Holes - Pipe 760 dia. x 15.9 mm Thick (B.F. 75695) (BCS 3.6.1) | metre | 265 | 150 | 39750 | 10.73 | 2843.45 | 3.5%
F020 | Pile Casings (610 dia. x 9.5 mm Thick) - Supply and Install (Special Provisions) | metre | 53 | 1200 | 63600 | 1073.33 | 56886.49 | 3.5%
F822 | Pile Concrete (Class) - Supply and Place (B.F. 75695) (BCS 4.27.1) | cubic metre | 178 | 1000 | 178000 | 1626.67 | 289547.26 | 4.4%
F834 | Concrete (Class C) - Supply and Place (B.F. 75695) (BCS 4.27.1) | cubic metre | 59 | 1500 | 88500 | 3220 | 189980 | 3.5%
F841 | Concrete (Class HPC) - Supply and Place (B.F. 75695) (BCS 4.27.1) | cubic metre | 120 | 2000 | 240000 | 3220 | 386400 | 3.5%
F850 | Plain Reinforcing Steel - Supply (B.F. 75695) (BCS 5.6) | kilogram | 13150 | 2 | 26300 | 2.89 | 38003.5 | 3.4%
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 75695) (BCS 5.6) | kilogram | 26756 | 8 | 214048 | 9.69 | 259265.64 | 3.8%
F853 | Stainless Reinforcing Steel - Supply (B.F. 75695) (BCS 5.6) | kilogram | 703 | 12 | 8436 | 13.85 | 9736.55 | 3.2%
F854 | Reinforcing Steel - Place (B.F. 75695) (BCS 5.6) | kilogram | 41855 | 1.5 | 62782.5 | 2.15 | 89988.25 | 3.5%
F017 | Precast Concrete Unit - Supply and Fabrication, Delivery and Erection - 700mm Deep SLC Girders (B.F. 75695) (BCS 7.4) | lump sum | 1 | 1238000 | 1238000 | 2393553.99 | 2393553.99 | 18.3%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 20000 | 20000 | 1626.67 | 1626.67 | 4.4%
F780 | Bridgerail - Supply and Install (B.F. 75695) (BCS 12.4) | lump sum | 1 | 105600 | 105600 | 107333.33 | 107333.33 | 3.5%
F752 | Guardrail - Supply and Install (B.F. 75695) (BCS 14.5) | lump sum | 1 | 76200 | 76200 | 75133.33 | 75133.33 | 3.5%
F053 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3 - Supply and Install (Special Provisions) | unit | 4 | 6000 | 24000 | 3877.33 | 15509.32 | 3.8%
F974 | Waterproofing (BCS 16.5) | square metre | 725 | 60 | 43500 | 107.33 | 77814.25 | 3.5%
F042 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 134 | 200 | 26800 | 483 | 64722 | 3.5%
F053 | Drain Troughs (Special Provisions) | unit | 1 | 60000 | 60000 | 37200 | 37200 | 16%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 300 | 20 | 6000 | 11.72 | 3516 | 11.4%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 2200 | 20 | 44000 | 3.44 | 7568 | 21.4%
F018 | Temporary Detour Bridge - Supply, Install, Removal and Haul (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 600000 | 600000 | 2273046.83 | 2273046.83 | 58.4%
E612 | Total Suspended Solids (TSS) Testing - Detour (Special Provisions) | day | 25 | 2000 | 50000 | 190.13 | 4753.25 | 133.9%
G225 | Common Excavation (HCS 2.3.6) | cubic metre | 16500 | 20 | 330000 | 16.98 | 280170 | 23.5%
E453 | Geogrid - Supply and Install (Special Provisions) | square metre | 2000 | 10 | 20000 | 5.22 | 10440 | 63.4%
E616 | Separation/Filtration Geotextile - Supply and Install (Class Type C) (HCS 5.31.6) | square metre | 2000 | 5 | 10000 | 5.54 | 11080 | 55.7%
D425 | Culverts - Supply and Install (800 mm dia. C.S.P.) (HCS 2.4.4) (HCS 5.23.4) | metre | 16 | 620 | 9920 | 687.1 | 10993.6 | 32.5%
S830 | Flexible Guide Post/Delineator - Round - Supply and Install (HCS 5.28.3) (HCS 2.19.4) | post | 20 | 50 | 1000 | 125.45 | 2509 | 67%
Q186 | Gravel Surfacing Des. 4 Class 25 (HCS 3.3.4) (HCS 5.2.5) | tonne | 275 | 50 | 13750 | 55.77 | 15336.75 | 18.8%
G300 | Topsoil Placement (HCS 2.6.4) | square metre | 7500 | 2 | 15000 | 0.94 | 7050 | 49.7%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 30000 | 30000 | 7965.97 | 7965.97 | 47.4%
F190 | Backfill - Crushed Granular, Des. 2 Class 25 (BCS 2.4) | lump sum | 1 | 30000 | 30000 | 8335.85 | 8335.85 | 51.5%
F824 | Drill Rig Set-up (Drilled Piles) - 610 mm Dia Holes (BCS 3.6.2) | pile | 14 | 6000 | 84000 | 10733.33 | 150266.62 | 3.5%
F812 | Supply of Piling - Plain Steel H-Pile - HP 360 x 132 (BCS 3.6.1) | metre | 186 | 350 | 65100 | 386.07 | 71809.02 | 3.5%
F818 | Pile Driving - Drilled Piles (610mm dia.) (BCS 3.6.1) | metre | 186 | 250 | 46500 | 10.73 | 1995.78 | 3.5%
F818 | Pile Driving - Pile Installation in Pre-Bored Holes - HP 360 x 132 (BCS 3.6.1) | metre | 186 | 100 | 18600 | 10.73 | 1995.78 | 3.5%
F021 | Concrete (Class Pile) (BCS 4.27.1) | cubic metre | 49 | 1000 | 49000 | 1626.67 | 79706.83 | 4.4%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 51 | 1500 | 76500 | 3773.33 | 192439.83 | 3.8%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 5360 | 2 | 10720 | 2.68 | 14364.8 | 3.5%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 5360 | 1.5 | 8040 | 2.15 | 11524 | 3.5%
F752 | Guardrail - Supply and Install - Concrete F Blocks (BCS 14.5) | lump sum | 1 | 40000 | 40000 | 42933.33 | 42933.33 | 3.5%
|  | Bridge File Modified Tender Value |  |  | 6500171.15 |  | 9188795.36 | 18.6%
|  | Total Tender Value |  |  |  |  | 22290926.94 | 12.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy - Bridge Construction (GCS 1.2.41.9) | day | 1500 | - | - | 2 | 3000 | 117.9%
Tender: 22393 ¦ Bridge File: 75695-2 ¦ Tender Opening Date: 2023-09-19
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22393 | Construct CSP Culvert | Culvert | Complex | Replace Culvert with Culvert | 2023-2024 | 2023-09-19 | 6 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75716-2 | 31 km North of Ft Vermilion | Peace | 58:10 | Tributary to Caribou River | 1 x 2700 CSP | 32 | 32 | 2.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 42000 | 42000 | 181241.21 | 181241.21 | 118%
F750 | Traffic Accommodation for Bridge Construction (B.F. 75716) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 70000 | 70000 | 44065.64 | 44065.64 | 29%
F486 | Demolition, Disposal and Salvage of Existing Structure (B.F. 75716) (BCS 18.7) | lump sum | 1 | 20000 | 20000 | 28451.03 | 28451.03 | 99%
F186 | Excavation - Structural (B.F. 75716) (BCS 1.6.1) | lump sum | 1 | 20000 | 20000 | 15717.25 | 15717.25 | 21.7%
E018 | Environmental Protection Works (Special Provisions) | lump sum | 1 | 25000 | 25000 | 21238.61 | 21238.61 | 62.4%
E018 | Care of Water (Special Provisions) | lump sum | 1 | 25000 | 25000 | 23568.14 | 23568.14 | 53.3%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 25 | 2000 | 50000 | 637.47 | 15936.75 | 127.1%
F495 | CSP with Couplers - Supply (B.F. 75716) (BCS 18.7) | metre | 32 | 3000 | 96000 | 1539.24 | 49255.68 | 21.2%
F496 | CSP - Assembly (B.F. 75716) (BCS 18.7) | metre | 32 | 1200 | 38400 | 1110.84 | 35546.88 | 63.6%
F190 | Backfill - Compacted Granular (B.F. 75716) (BCS 2.4) | lump sum | 1 | 33000 | 33000 | 67005.77 | 67005.77 | 32.1%
F190 | Backfill - Compacted Non-Granular (B.F. 75716) (BCS 2.4) | lump sum | 1 | 21000 | 21000 | 23830.56 | 23830.56 | 15.3%
F500 | Heavy Rock Riprap (Class 1) (B.F. 75716) (BCS 10.7) | cubic metre | 95 | 300 | 28500 | 532.2 | 50559 | 11.5%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 200 | 20 | 4000 | 13.42 | 2684 | 16.6%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 500 | 20 | 10000 | 4.22 | 2110 | 44.3%
|  | Bridge File Modified Tender Value |  |  | 482900 |  | 561210.52 | 50.1%
|  | Total Tender Value |  |  |  |  | 22290926.94 | 12.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variability
X004 | Site Occupancy - Bridge Construction (GCS 1.2.41.9) | day | 800 | - | - | 2 | 1600 | 165%
Tender: 22393 ¦ Bridge File: 75716-2 ¦ Tender Opening Date: 2023-09-19
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23922 | Replace Superstructure SLW Precast Concrete Girder Bridge | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2023-10-11 | 2 | 2023-12-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
73218-1 | 11 km West of Dapp | North Central | 661:06 | Shoal Creek | 8 x 510 SLW | 10 ¦ 10 ¦ 10 | 30 | 10
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 51931.5 | 51931.5 | 105000 | 105000 | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 73218) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 50000 | 50000 | 15000 | 15000 | -
F186 | Excavation - Structural (B.F. 73218) (BCS 1.6.1) | lump sum | 1 | 10000 | 10000 | 22500 | 22500 | -
F486 | Demolition, Disposal and Salvage of Existing Structure (B.F. 73218) (BCS 18.7) | lump sum | 1 | 80000 | 80000 | 282900 | 282900 | -
F760 | Partial Depth Repair - Wingwalls and Abutment Seats (BCS 20.6.2) | square metre | 1.5 | 2000 | 3000 | 7800 | 11700 | -
F850 | Plain Reinforcing Steel - Supply (B.F. 73218) (BCS 5.6) | kilogram | 1761 | 3 | 5283 | 4 | 7044 | -
F854 | Reinforcing Steel - Place (B.F. 73218) (BCS 5.6) | kilogram | 1761 | 2 | 3522 | 4 | 7044 | -
F834 | Concrete (Class C) - Supply and Place (B.F. 73218) (BCS 4.27.1) | cubic metre | 9.8 | 2500 | 24500 | 5750 | 56350 | -
F017 | Misc. Bridge Material - Plain Elastomeric Bearings - Supply and Installation | lump sum | 1 | 5000 | 5000 | 13000 | 13000 | -
F945 | Precast Concrete Units - Erection (B.F. 73218) | lump sum | 1 | 120000 | 120000 | 157500 | 157500 | -
F970 | Miscellaneous Iron - Drift Pins and Plaques (BCS 13.5) | lump sum | 1 | 5000 | 5000 | 8500 | 8500 | -
F204 | Backfill - Crushed Aggregate (B.F. 73218) (BCS 2.4) | lump sum | 1 | 20000 | 20000 | 21500 | 21500 | -
F974 | Waterproofing (BCS 16.5) | square metre | 324.5 | 80 | 25960 | 90 | 29205 | -
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 148.4 | 450 | 66780 | 375 | 55650 | -
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (B.F. 73218) (BCS 12.4) | lump sum | 1 | 33600 | 33600 | 55000 | 55000 | -
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 160 | 150 | 24000 | 217.5 | 34800 | -
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 4 | 6000 | 24000 | 11000 | 44000 | -
F492 | Roadway Work (B.F. 73218) (BCS 18.7) | lump sum | 1 | 25000 | 25000 | 42500 | 42500 | -
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 100 | 12 | 1200 | 46 | 4600 | -
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 200 | 15 | 3000 | 32.5 | 6500 | -
|  | Bridge File Modified Tender Value |  |  | 581776.5 |  | 980293 | -
|  | Total Tender Value |  |  |  |  | 1053043 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 49 | 73500 | -
Tender: 23922 ¦ Bridge File: 73218-1 ¦ Tender Opening Date: 2023-10-11
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23137 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2023-2024 | 2023-10-18 | 4 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76054N-3 | At Morinville | North Central | 2:36 | CNR Railway | 12 x 510 SLC | 11 ¦ 16 ¦ 11 | 38 | 14.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 505000 | 505000 | 498333.33 | 498333.33 | 11.9%
F018 | CN Railway Coordination (Special Provisions) | lump sum | 1 | 600000 | 600000 | 182666.67 | 182666.67 | 9.1%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 45000 | 45000 | 42200 | 42200 | 57.8%
X022 | ACP Surface Removal - Deck, Approach Slabs, and Approaches (BCS 17.7.4) | square metre | 1950 | 60 | 117000 | 20.67 | 40306.5 | 23.8%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 500000 | 500000 | 662666.67 | 662666.67 | 17.5%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 50000 | 50000 | 430833.33 | 430833.33 | 29.1%
F204 | Backfill - Crushed Aggregate - Des. 2 Class 25 - Abutments and Piers (BCS 2.4) | lump sum | 1 | 50000 | 50000 | 357333.33 | 357333.33 | 48.7%
F820 | PDA Testing (BCS 3.6.4) | test | 4 | 5000 | 20000 | 1741.67 | 6966.68 | 14.8%
F814 | Supply of Piling - Plain Steel Pipe Pile - Pipe 610 mm dia. x 12.5 mm (BCS 3.6.1) | metre | 96 | 825 | 79200 | 353.33 | 33919.68 | 1.3%
F815 | Supply of Piling - Galvanized Steel Pipe Pile - Pipe 610 mm dia. x 12.5 mm (BCS 3.6.1) | metre | 148 | 1200 | 177600 | 558.33 | 82632.84 | 2.1%
F816 | Pile Set-up (Driven Piles) - Pipe 610 mm dia. x 12.5 mm (BCS 3.6.1) | pile | 16 | 2500 | 40000 | 9375 | 150000 | 9.4%
F818 | Pile Driving - Pipe 610 mm dia. x 12.5 mm (BCS 3.6.1) | metre | 151 | 220 | 33220 | 6.33 | 955.83 | 7.4%
F819 | Pile Tip Reinforcement (BCS 3.6.1) | pile | 16 | 500 | 8000 | 1100 | 17600 | 19.6%
F019 | Drill Rig Set-up (Special Provisions) | location | 16 | 4000 | 64000 | 3241.67 | 51866.72 | 23.6%
F020 | Pile Installation 610 dia. (Special Provisions) | metre | 151 | 125 | 18875 | 6.33 | 955.83 | 7.4%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 19007 | 3 | 57021 | 2.92 | 55500.44 | 20.2%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 24515 | 8 | 196120 | 7.83 | 191952.45 | 3%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 720 | 12.5 | 9000 | 14.33 | 10317.6 | 3.3%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 44242 | 2 | 88484 | 1.85 | 81847.7 | 13.3%
F822 | Pile Concrete (Class) - Supply and Place (BCS 4.27.1) | cubic metre | 67 | 1750 | 117250 | 641.67 | 42991.89 | 19.2%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 158 | 2000 | 316000 | 1600 | 252800 | 15.5%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 133 | 3000 | 399000 | 1666.67 | 221667.11 | 14.1%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) | lump sum | 1 | 1400000 | 1400000 | 1132833.33 | 1132833.33 | 9.1%
F911 | Drain Troughs (BCS 9.7) | metre | 50 | 750 | 37500 | 936.67 | 46833.5 | 28.9%
F974 | Waterproofing (BCS 16.5) | square metre | 686.3 | 95 | 65198.5 | 65.33 | 44835.98 | 0.7%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 382.2 | 350 | 133770 | 245 | 93639 | 16.9%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 229.2 | 400 | 91680 | 240 | 55008 | 11.2%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 170000 | 170000 | 109166.67 | 109166.67 | 34.8%
F018 | Guardrail Re-installation (Special Provisions) | lump sum | 1 | 75000 | 75000 | 25166.67 | 25166.67 | 64.9%
F018 | Median Crossovers Removal (Special Provisions) | lump sum | 1 | 75000 | 75000 | 180433.33 | 180433.33 | 13.8%
|  | Bridge File Modified Tender Value |  |  | 5538918.5 |  | 5104231.08 | 7.8%
|  | Total Tender Value |  |  |  |  | 5290101.08 | 8.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 180 | 270000 | 124 | 186000 | 37.9%
Tender: 23137 ¦ Bridge File: 76054-3 ¦ Tender Opening Date: 2023-10-18
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
15989 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2023-11-02 | 2 | 2025-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74227-1 | 8 km Northwest of Ft Vermilion | Peace | 88:18 | Peace River | 2 x 3580 Welded Box Girder | 90 ¦ 111 ¦ 111 ¦ 111 ¦ 90 | 513 | 10.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 710000 | 710000 | 1815000 | 1815000 | -
S241 | Construction Advisory Sign (Special Provisions) | sign | 7 | 1500 | 10500 | 3950 | 27650 | -
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 300000 | 300000 | 757000 | 757000 | -
F755 | Surface Removal - Deck and Roof Slab (BCS 20.6.1) (Special Provisions) | square metre | 4495 | 185 | 831575 | 152.5 | 685487.5 | -
F022 | ACP Surface Removal - Approach Slab & Approaches (Special Provisions) | square metre | 479 | 50 | 23950 | 67.5 | 32332.5 | -
F170 | Demolition and Disposal of Bridge Structure (B.F. 74227) (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 100000 | 100000 | 797500 | 797500 | -
F850 | Plain Reinforcing Steel - Supply (B.F. 74227) (BCS 5.6) | kilogram | 338 | 3 | 1014 | 7 | 2366 | -
F853 | Stainless Reinforcing Steel - Supply (B.F. 74227) (BCS 5.6) | kilogram | 4434 | 12 | 53208 | 27.25 | 120826.5 | -
F854 | Reinforcing Steel - Place (B.F. 74227) (BCS 5.6) | kilogram | 4772 | 2 | 9544 | 5.25 | 25053 | -
F834 | Concrete (Class C) - Supply and Place (B.F. 74227) (BCS 4.27.1) | cubic metre | 8.8 | 1600 | 14080 | 9900 | 87120 | -
F841 | Concrete (Class HPC) - Supply and Place (B.F. 74227) (BCS 4.27.1) | cubic metre | 26.1 | 2500 | 65250 | 11000 | 287100 | -
F760 | Partial Depth Repair - Deck and Roof Slab (BCS 20.6.2) | square metre | 450 | 1000 | 450000 | 1305 | 587250 | -
F760 | Partial Depth Repair - Deck Overhang and Underside between Girders (BCS 20.6.2) | square metre | 10 | 1850 | 18500 | 6325 | 63250 | -
F760 | Partial Depth Repair - Deck Underside within Box Girder (BCS 20.6.2) | square metre | 10 | 2350 | 23500 | 6600 | 66000 | -
F760 | Partial Depth Repair - Curbs (BCS 20.6.2) | square metre | 30 | 1300 | 39000 | 3430 | 102900 | -
F760 | Partial Depth Repair - Abutments (BCS 20.6.2) | square metre | 20 | 1700 | 34000 | 3800 | 76000 | -
F765 | Full Depth Repair - Deck and Roof Slab (BCS 20.6.2) | square metre | 15 | 1750 | 26250 | 6575 | 98625 | -
F765 | Full Depth Repair - Deck within Box Girder (BCS 20.6.2) | square metre | 10 | 2250 | 22500 | 6900 | 69000 | -
F765 | Full Depth Repair - Curbs (BCS 20.6.2) | square metre | 30 | 2000 | 60000 | 10725 | 321750 | -
F765 | Full Depth Repair - Abutments (BCS 20.6.2) | square metre | 5 | 2000 | 10000 | 6975 | 34875 | -
F020 | Concrete Crack Repair - Curbs (Special Provisions) | metre | 950 | 125 | 118750 | 215 | 204250 | -
F020 | Concrete Crack Repair - Abutments (Special Provisions) | metre | 15 | 500 | 7500 | 530 | 7950 | -
F024 | Retrofit Deck Drains (Special Provisions) | drain | 40 | 4000 | 160000 | 3650 | 146000 | -
F018 | Steel Girder Modifications (Special Provisions) | lump sum | 1 | 170000 | 170000 | 707500 | 707500 | -
F993 | Galvanic Corrosion Protection - Supply and Install (Special Provisions) | anodes | 2000 | 50 | 100000 | 120 | 240000 | -
F770 | Abrasive Blasting - Deck Surface (B.F. 74227) (BCS 20.6.3) | square metre | 4558 | 22 | 100276 | 180 | 820440 | -
F775 | Deck Overlay Concrete - Supply (BCS 20.6.4) | cubic metre | 228 | 2800 | 638400 | 4420 | 1007760 | -
F776 | Deck Overlay Concrete - Place (BCS 20.6.4) | square metre | 4558 | 130 | 592540 | 169.5 | 772581 | -
F022 | Deck Surface Preparation For Waterproofing (Special Provisions) | square metre | 4558 | 30 | 136740 | 38 | 173204 | -
F018 | Deck Surface Testing and Inspection (Special Provisions) | lump sum | 1 | 25000 | 25000 | 34500 | 34500 | -
F022 | Deck Waterproofing System (Special Provisions) | square metre | 4558 | 250 | 1139500 | 391.5 | 1784457 | -
F980 | Asphalt Concrete Pavement Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 113 | 400 | 45200 | 1825 | 206225 | -
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (Special Provisions) | lump sum | 1 | 340000 | 340000 | 1807500 | 1807500 | -
F014 | Replace Bearing Grout Pads (Special Provisions) | grout pad | 4 | 12500 | 50000 | 126250 | 505000 | -
F911 | Drain Troughs (B.F. 74227) (BCS 9.7) | metre | 176 | 500 | 88000 | 1425 | 250800 | -
F018 | Concrete Cleaning and Sealing (Special Provisions) | lump sum | 1 | 75000 | 75000 | 155500 | 155500 | -
F021 | Fillcrete - Supply and Place (Special Provisions) | cubic metre | 15 | 800 | 12000 | 2100 | 31500 | -
F018 | Headslope Improvement (Special Provisions) | lump sum | 1 | 250000 | 250000 | 499500 | 499500 | -
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 10000 | 10000 | 33000 | 33000 | -
F018 | Approach Guardrail Transitions (Special Provisions) | lump sum | 1 | 60000 | 60000 | 104000 | 104000 | -
F018 | Approach Grade Widening (Special Provisions) | lump sum | 1 | 100000 | 100000 | 418500 | 418500 | -
F752 | Guardrail - Supply and Install (B.F. 74227) (BCS 14.5) | lump sum | 1 | 73200 | 73200 | 131000 | 131000 | -
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 4 | 5000 | 20000 | 9500 | 38000 | -
F018 | Catwalk Door Repairs (Special Provisions) | lump sum | 1 | 2000 | 2000 | 9500 | 9500 | -
X018 | Slope Inclinometer - Supply and Install (Special Provisions) | lump sum | 1 | 60000 | 60000 | 94000 | 94000 | -
X052 | Vibrating Wire Piezometer - Supply and Install (Special Provisions) | unit | 2 | 3000 | 6000 | 5250 | 10500 | -
X018 | Shorten and Repair Existing Instruments (Special Provisions) | lump sum | 1 | 5000 | 5000 | 18500 | 18500 | -
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 6000 | 10 | 60000 | 30 | 180000 | -
E020 | Fibre Rolls (Special Provisions) | metre | 600 | 20 | 12000 | 57 | 34200 | -
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 1100 | 20 | 22000 | 49.5 | 54450 | -
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 365000 | 365000 | 365000 | 365000 | -
X002 | Extra Work - Wide Load Management (Special Provisions) | Total Force Account | 1 | 400000 | 400000 | 400000 | 400000 | -
|  | Bridge File Modified Tender Value |  |  | 8046977 |  | 17302402.5 | -
|  | Total Tender Value |  |  |  |  | 18307402.5 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) (Special Provisions) | day | 1500 | 160 | 240000 | 315 | 472500 | -
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 200 | 300000 | 355 | 532500 | -
Tender: 15989 ¦ Bridge File: 74227-1 ¦ Tender Opening Date: 2023-11-02
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22614 | Repair SPCSP Culvert | Culvert | Single | Culvert Repair | 2023-2024 | 2023-11-28 | 6 | 2024-03-14
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
76749-2 | 15 km Northeast of Grande Cache | Peace | 40:34 | Tributary to Susa Creek | 1 x 2430 SPCSP | 115 | 115 | 2.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 68000 | 68000 | 136666.67 | 136666.67 | 13.8%
F750 | Traffic Accommodation for Bridge Construction (B.F. 76749) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 20000 | 20000 | 28333.33 | 28333.33 | 68.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 18 | 1500 | 27000 | 1036.67 | 18660.06 | 134%
F186 | Excavation - Structural (B.F. 76749) (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 51000 | 51000 | 2.8%
X018 | Sediment and Debris Removal (Special Provisions) | lump sum | 1 | 60000 | 60000 | 47666.67 | 47666.67 | 23.4%
F018 | CSP Liner with Couplers - Supply (Special Provisions) | lump sum | 1 | 80000 | 80000 | 112666.67 | 112666.67 | 34%
F018 | CSP Liner with Couplers - Instalation (Special Provisions) | lump sum | 1 | 70000 | 70000 | 198000 | 198000 | 27.1%
F021 | Concrete (Class S Modified) - Supply and Place (Special Provisions) | cubic metre | 170 | 1100 | 187000 | 1516.67 | 257833.9 | 1.6%
F525 | Heavy Rock Riprap (Class 3) (B.F. 76749) (BCS 10.7) | cubic metre | 190 | 350 | 66500 | 350 | 66500 | 11.7%
F492 | Roadway Work (B.F. 76749) (BCS 18.7) | lump sum | 1 | 75000 | 75000 | 20333.33 | 20333.33 | 22.1%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 50 | 30 | 1500 | 31.67 | 1583.5 | 41.4%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 50 | 30 | 1500 | 31.67 | 1583.5 | 41.4%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 170 | 20 | 3400 | 23.33 | 3966.1 | 10.1%
|  | Bridge File Modified Tender Value |  |  | 684900 |  | 944793.73 | 5.7%
|  | Total Tender Value |  |  |  |  | 1071460 | 6.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 4000 | - | - | 32 | 128000 | 41%
Tender: 22614 ¦ Bridge File: 76749-2 ¦ Tender Opening Date: 2023-11-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22336 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2023-2024 | 2023-11-29 | 2 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
13541-2 | 2 km West of Goodfare | Peace | 671:02 | Beavertail Creek | 9 x 700 SLC | 20 | 20 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 200000 | 200000 | 1145267 | 1145267 | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 13541) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 30000 | 30000 | 179989 | 179989 | -
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 20 | 500 | 10000 | 872.38 | 17447.6 | -
F170 | Demolition and Disposal of Bridge Structure (B.F. 13541) (BCS 21.4.1) | lump sum | 1 | 60000 | 60000 | 271994.5 | 271994.5 | -
F018 | Headslope Preparation and Backfill (Special Provisions) | lump sum | 1 | 100000 | 100000 | 195064 | 195064 | -
F812 | Supply of Piling - Plain Steel H-Pile (B.F. 13541) (BCS 3.6.1) | metre | 471.26 | 450 | 212067 | 381.45 | 179762.13 | -
F816 | Pile Set-up (Driven Piles) (B.F. 13541) (BCS 3.6.1) | pile | 16 | 5930 | 94880 | 3562.47 | 56999.52 | -
F818 | Pile Driving (B.F. 13541) (BCS 3.6.1) | metre | 471.26 | 137 | 64562.62 | 249.11 | 117395.58 | -
F820 | PDA Testing (B.F. 13541) (BCS 3.6.4) | test | 8 | 2227.49 | 17819.92 | 2268.38 | 18147.04 | -
F850 | Plain Reinforcing Steel - Supply (B.F. 13541) (BCS 5.6) | kilogram | 4830 | 3.5 | 16905 | 20.37 | 98387.1 | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 13541) (BCS 5.6) | kilogram | 9999 | 8.46 | 84591.54 | 10.08 | 100789.92 | -
F853 | Stainless Reinforcing Steel - Supply (B.F. 13541) (BCS 5.6) | kilogram | 557 | 16.08 | 8956.56 | 34.27 | 19088.39 | -
F854 | Reinforcing Steel - Place (B.F. 13541) (BCS 5.6) | kilogram | 15386 | 2.85 | 43850.1 | 3.78 | 58159.08 | -
F834 | Concrete (Class C) - Supply and Place (B.F. 13541) (BCS 4.27.1) | cubic metre | 39 | 2860 | 111540 | 2085.13 | 81320.07 | -
F841 | Concrete (Class HPC) - Supply and Place (B.F. 13541) (BCS 4.27.1) | cubic metre | 62.4 | 4450 | 277680 | 2025.4 | 126384.96 | -
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (B.F. 13541) (BCS 7.4) | lump sum | 1 | 420000 | 420000 | 580848.5 | 580848.5 | -
F974 | Waterproofing (BCS 16.5) | square metre | 321 | 93 | 29853 | 265.07 | 85087.47 | -
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 2000 | 2000 | 40332 | 40332 | -
F780 | Bridgerail - Supply and Install (B.F. 13541) | lump sum | 1 | 45000 | 45000 | 106378.5 | 106378.5 | -
F752 | Guardrail - Supply and Install (B.F. 13541) (BCS 14.5) | lump sum | 1 | 35000 | 35000 | 95838 | 95838 | -
F492 | Roadway Work (B.F. 13541) (BCS 18.7) (Special Provisions) | lump sum | 1 | 45000 | 45000 | 131796 | 131796 | -
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 305 | 367.6 | 112118 | 486.54 | 148394.7 | -
F500 | Heavy Rock Riprap (Class 1) (B.F. 13541) (BCS 10.7) | cubic metre | 295 | 350 | 103250 | 758.26 | 223686.7 | -
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 50 | 15 | 750 | 22.64 | 1132 | -
E020 | Erosion Control Barrier (Straw Fiber Roll) (Special Provisions) | metre | 80 | 15 | 1200 | 111.87 | 8949.6 | -
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 200 | 15 | 3000 | 8.87 | 1774 | -
|  | Bridge File Modified Tender Value |  |  | 2130023.74 |  | 4090413.36 | -
|  | Total Tender Value |  |  |  |  | 4255254.33 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variability
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 35 | 52500 | 110 | 165000 | -
Tender: 22336 ¦ Bridge File: 13541-2 ¦ Tender Opening Date: 2023-11-29
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22346 | Construct SLC Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2023-2024 | 2023-12-07 | 2 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
71933-2 | 10 km Southwest of Bezanson | Peace | 670:02 | Tributary to Wapiti River | 9 x 700 SLC | 20 | 20 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 224000 | 224000 | 437000 | 437000 | -
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 80000 | 80000 | 67500 | 67500 | -
X041 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1000 | 10000 | 610 | 6100 | -
E018 | Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 25000 | 25000 | 12500 | 12500 | -
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 50000 | 50000 | 376500 | 376500 | -
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 112500 | 112500 | -
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 15000 | 15000 | 19400 | 19400 | -
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 301 | 500 | 150500 | 315 | 94815 | -
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 16 | 6000 | 96000 | 7950 | 127200 | -
F818 | Pile Driving (BCS 3.6.1) | metre | 301 | 150 | 45150 | 8 | 2408 | -
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 5200 | 6 | 31200 | 2.75 | 14300 | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 10900 | 12 | 130800 | 8.5 | 92650 | -
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 16100 | 3 | 48300 | 3 | 48300 | -
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 35 | 3200 | 112000 | 2330 | 81550 | -
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 65 | 4500 | 292500 | 2622.5 | 170462.5 | -
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - - 20 metre Type SLC-700 (7 Interior, 2 Exterior) (BCS 7.4) | lump sum | 1 | 275000 | 275000 | 570000 | 570000 | -
F974 | Waterproofing (BCS 16.5) | square metre | 330 | 100 | 33000 | 92 | 30360 | -
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 220 | 340 | 74800 | 295 | 64900 | -
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 2000 | 2000 | 2312.5 | 2312.5 | -
F780 | Bridgerail - Supply and Install (BCS 12.4) | lump sum | 1 | 35000 | 35000 | 63000 | 63000 | -
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 60500 | 60500 | 41000 | 41000 | -
S052 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 2 | 4850 | 9700 | 5800 | 11600 | -
S830 | Flexible Guide Post/Delineator - Round - Supply and Install (HCS 5.28.3) (HCS 2.19.4) | post | 8 | 60 | 480 | 140 | 1120 | -
D105 | Culverts - Remove and Dispose (C.S.P.) (over 700 mm dia.) (HCS 2.4.4) | metre | 6 | 200 | 1200 | 1350 | 8100 | -
D431 | Culverts - Supply and Install (1 000 mm dia. C.S.P.) (HCS 2.4.4) (HCS 5.23.4) | metre | 20 | 1500 | 30000 | 1430 | 28600 | -
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 200 | 20 | 4000 | 16 | 3200 | -
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 300 | 5 | 1500 | 16 | 4800 | -
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 600000 | 600000 | 515500 | 515500 | -
|  | Bridge File Modified Tender Value |  |  | 2462630 |  | 3007678 | -
|  | Total Tender Value |  |  |  |  | 3210178 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 70 | 105000 | 65 | 97500 | -
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | 70 | 105000 | 70 | 105000 | -
Tender: 22346 ¦ Bridge File: 71933-2 ¦ Tender Opening Date: 2023-12-07
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22610 | Reconstruct Guide Bank | Guide Bank | Single | Reconstruct Guide Bank | 2023-2024 | 2023-12-19 | 5 | 2024-06-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
74229BGL-2 | 4 km North of Blue Ridge | North Central | - | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 865000 | 865000 | 574279.67 | 574279.67 | 19.3%
F750 | Traffic Accommodation for Bridge Construction (B.F. 74229) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 27024.67 | 27024.67 | 63.3%
E052 | Total Suspended Solids (TSS) Testing (Special Provisions) | unit | 70 | 1500 | 105000 | 1780.79 | 124655.3 | 2.9%
E018 | Temporary River Works (Special Provisions) | lump sum | 1 | 250000 | 250000 | 245475.2 | 245475.2 | 54.4%
X018 | Clearing and Timber Salvage | lump sum | 1 | 46750 | 46750 | 116131.67 | 116131.67 | 39.7%
F018 | Concrete Slope Protection Removal (Special Provisions) | lump sum | 1 | 60000 | 60000 | 23655.33 | 23655.33 | 19.6%
X018 | Common Excavation (Special Provisions) | lump sum | 1 | 15675 | 15675 | 38845.07 | 38845.07 | 75.2%
X018 | Channel Excavation and Backfill (Special Provisions) | lump sum | 1 | 455000 | 455000 | 318130.27 | 318130.27 | 49%
B026 | Granular Fill - Des. 2 Cl. 40 (Special Provisions) | cubic metre | 16000 | 92 | 1472000 | 96.79 | 1548640 | 11%
B040 | Clean Coarse Granular Fill - Channel (Special Provisions) | tonne | 14000 | 114.5 | 1603000 | 69.76 | 976640 | 11.7%
F042 | Heavy Rock Riprap - Modified Class 3 (Special Provisions) | tonne | 24500 | 185 | 4532500 | 145.85 | 3573325 | 16.2%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 750 | 30 | 22500 | 12.75 | 9562.5 | 72.6%
E405 | Straw Bale Barrier (HCS 6.5.6) | metre | 300 | 25 | 7500 | 76.52 | 22956 | 98.7%
X018 | Topsoil and Seeding (Special Provisions) | lump sum | 1 | 55000 | 55000 | 96057.6 | 96057.6 | 49.4%
|  | Bridge File Modified Tender Value |  |  | 9514925 |  | 7695378.28 | 14.4%
|  | Total Tender Value |  |  |  |  | 7695305.53 | 14.4%
Tender: 22610 ¦ Bridge File: 74229-2 ¦ Tender Opening Date: 2023-12-19
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20631 | Construct CSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2023-2024 | 2024-01-23 | 13 | 2024-10-14
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
9684-2 | 47 km Southeast of Gadsby | Central | 593:02 | 2nd Order Tributary to Gough Lake | 1 x 1800 CSP | 52 | 52 | 1.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 60000 | 60000 | 60813.33 | 60813.33 | 46.8%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 15000 | 15000 | 20199.67 | 20199.67 | 51.3%
E018 | Site Isolation / Water Accommodation (Special Provisions) | lump sum | 1 | 30000 | 30000 | 16542.33 | 16542.33 | 57.5%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 1299.72 | 3899.16 | 105.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 1500 | 9000 | 935.44 | 5612.64 | 99.4%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 30000 | 30000 | 17920.67 | 17920.67 | 87.5%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 60000 | 60000 | 54200.6 | 54200.6 | 89.5%
F495 | CSP with Couplers - Supply (1.8 m Dia.) (BCS 18.7) | metre | 52 | 1300 | 67600 | 890.45 | 46303.4 | 9%
F496 | CSP - Assembly (1.8 m Dia.) (BCS 18.7) | metre | 52 | 500 | 26000 | 114.85 | 5972.2 | 54.6%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 90000 | 90000 | 75194.67 | 75194.67 | 20.8%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 50 | 250 | 12500 | 325.05 | 16252.5 | 23.9%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 120000 | 120000 | 58543.22 | 58543.22 | 31.1%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 1 | 20000 | 20000 | 19243.33 | 19243.33 | 17.6%
E020 | Straw Rolls (Special Provisions) | metre | 150 | 20 | 3000 | 13.96 | 2094 | 35.1%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 300 | 10 | 3000 | 8.99 | 2697 | 38%
|  | Bridge File Modified Tender Value |  |  | 558100 |  | 405488.72 | 11.4%
|  | Total Tender Value |  |  |  |  | 424989.26 | 11.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 25 | 37500 | 13 | 19500 | 10.9%
Tender: 20631 ¦ Bridge File: 9684-2 ¦ Tender Opening Date: 2024-01-23
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
12507 | Construct SPCSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2023-2024 | 2024-01-24 | 5 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
78651-2 | 1 km South of Pine Lake | Central | 816:02 | Tributary to Ghostpine Creek | 1 x 3360 SPCSP | 49 | 49 | 3.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 130000 | 130000 | 132319.05 | 132319.05 | 27.8%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 90000 | 90000 | 25926.67 | 25926.67 | 21.7%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 70000 | 70000 | 36003.33 | 36003.33 | 28.6%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 311.33 | 933.99 | 50.6%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 1500 | 9000 | 556 | 3336 | 88.3%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 30000 | 30000 | 11503.33 | 11503.33 | 40.4%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 100000 | 100000 | 136496.67 | 136496.67 | 67.2%
F493 | SPCSP - Supply (3.36 m Dia.) (BCS 18.7) | metre | 48.77 | 3800 | 185326 | 3131.67 | 152731.55 | 10.5%
F494 | SPCSP - Assembly (3.36 m Dia.) (BCS 18.7) | metre | 48.77 | 1300 | 63401 | 829.94 | 40476.17 | 39.7%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 130000 | 130000 | 215200 | 215200 | 29.7%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 45000 | 45000 | 43480 | 43480 | 5.7%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 130 | 275 | 35750 | 241 | 31330 | 4.7%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 350000 | 350000 | 396516.67 | 396516.67 | 29.5%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.8 | 20000 | 16000 | 20240 | 16192 | 20.2%
E020 | Straw Rolls (Special Provisions) | metre | 200 | 20 | 4000 | 16.83 | 3366 | 36%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 300 | 10 | 3000 | 7.67 | 2301 | 22.2%
|  | Bridge File Modified Tender Value |  |  | 1273477 |  | 1248112.43 | 5.7%
|  | Total Tender Value |  |  |  |  | 1284111.94 | 5.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 35 | 52500 | 24 | 36000 | 15.6%
Tender: 12507 ¦ Bridge File: 78651-2 ¦ Tender Opening Date: 2024-01-24
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23812 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2024-01-25 | 2 | 2024-10-25
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
1642-1 | 2 km East of Donalda | Central | 53:10 | Meeting Creek | 9 x 510 VS | 9 ¦ 11 ¦ 9 | 29 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 168700 | 168700 | 170644.03 | 170644.03 | -
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 90000 | 90000 | 178482.1 | 178482.1 | -
E018 | Nest Removal and/or Deterrence (Special Provisions) | lump sum | 1 | 10000 | 10000 | 31138.54 | 31138.54 | -
F018 | Pier Access (Special Provisions) | lump sum | 1 | 60000 | 60000 | 80350.17 | 80350.17 | -
F760 | Partial Depth Repair - Pier Caps (BCS 20.6.2) | square metre | 12 | 2500 | 30000 | 2865.16 | 34381.92 | -
F760 | Partial Depth Repair - Curbs (BCS 20.6.2) | square metre | 2 | 1800 | 3600 | 5198.37 | 10396.74 | -
F755 | Surface Removal - FRSF Overlay (BCS 20.6.1) | square metre | 295 | 85 | 25075 | 188 | 55460 | -
F018 | Curb Demolition over Piers (Special Provisions) | lump sum | 1 | 20000 | 20000 | 36135.64 | 36135.64 | -
F770 | Abrasive Blasting - Deck Surface (BCS 20.6.3) | square metre | 295 | 40 | 11800 | 37.3 | 11003.5 | -
F018 | Girder Shear Connectors - Drill and Adhesive (Special Provisions) | lump sum | 1 | 40000 | 40000 | 65511.06 | 65511.06 | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 12127 | 8 | 97016 | 9.15 | 110962.05 | -
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 12127 | 2.25 | 27285.75 | 3.76 | 45597.52 | -
F903 | Structural Steel - Supply and Fabrication, Delivery and Erection - Filler Plates (B.F. 01642) (BCS 6.4.1) | lump sum | 1 | 10000 | 10000 | 25266.81 | 25266.81 | -
F018 | Grout Girder Ends at Piers (Special Provisions) | lump sum | 1 | 8000 | 8000 | 7883.04 | 7883.04 | -
F775 | Deck Overlay Concrete - Supply - Deck and Curbs - Class HPC with Steel Fibres (BCS 20.6.4) | cubic metre | 53 | 3000 | 159000 | 3188.1 | 168969.3 | -
F776 | Deck Overlay Concrete - Place - Deck and Curbs - Class HPC with Steel Fibres (BCS 20.6.4) | square metre | 302 | 275 | 83050 | 279.64 | 84451.28 | -
F151 | Protection of the Environment - Pier Pile Columns (BCS 22.25.1) | lump sum | 1 | 30000 | 30000 | 33480.96 | 33480.96 | -
F150 | Surface Preparation and Painting - Pier Pile Columns (BCS 22.25.2) | lump sum | 1 | 120000 | 120000 | 147199.2 | 147199.2 | -
F018 | Settlement Mitigation Wall (Special Provisions) | lump sum | 1 | 57500 | 57500 | 179628 | 179628 | -
F911 | Drain Troughs (BCS 9.7) | metre | 60 | 400 | 24000 | 977.65 | 58659 | -
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 160 | 25 | 4000 | 38.6 | 6176 | -
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 50000 | 50000 | 51368.37 | 51368.37 | -
F018 | Approach Rail Transitions - Supply and Install (Special Provisions) | lump sum | 1 | 30000 | 30000 | 67364.46 | 67364.46 | -
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 65 | 500 | 32500 | 1029.26 | 66901.9 | -
G018 | Headslope and Sideslope Grading (Special Provisions) | lump sum | 1 | 25000 | 25000 | 25740.94 | 25740.94 | -
F018 | Class 2 Concrete Surface Finish - Pier Caps (Special Provisions) | lump sum | 1 | 15000 | 15000 | 13970.27 | 13970.27 | -
F018 | Sealer - Curbs and Exterior Girder Fascia (Special Provisions) | lump sum | 1 | 10000 | 10000 | 23825.56 | 23825.56 | -
F018 | River Identification Signs - Supply and Install (Special Provisions) | lump sum | 1 | 2000 | 2000 | 3761.47 | 3761.47 | -
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 50000 | 50000 | 50000 | 50000 | -
|  | Bridge File Modified Tender Value |  |  | 1293526.75 |  | 1844709.83 | -
|  | Total Tender Value |  |  |  |  | 1973585.5 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 100 | 150000 | 86 | 129000 | -
Tender: 23812 ¦ Bridge File: 1642-1 ¦ Tender Opening Date: 2024-01-25
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21981 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2024-01-30 | 6 | 2024-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
1031-1 | At South Boundary of Two Hills | Central | 36:20 | Vermilion River | 12 x 510 SM (Modified) | 11 ¦ 11 ¦ 11 ¦ 11 | 44 | 14.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 70000 | 70000 | 197663.52 | 197663.52 | 37.2%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 100000 | 100000 | 148790.42 | 148790.42 | 54.2%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 10000 | 10000 | 58314.11 | 58314.11 | 102.1%
F755 | Surface Removal (BCS 20.6.1) | square metre | 679 | 60 | 40740 | 67.9 | 46104.1 | 34.8%
Q554 | Cold Milling Asphalt Pavement - 50 <mm Depth> (HCS 3.16.6) (Special Provisions) | square metre | 300 | 30 | 9000 | 56.28 | 16884 | 56.6%
F760 | Partial Depth Repair - Girders (BCS 20.6.2) | square metre | 4 | 2500 | 10000 | 4009.79 | 16039.16 | 13.4%
F760 | Partial Depth Repair - Deck and Approach Slabs (BCS 20.6.2) | square metre | 68 | 2500 | 170000 | 2504.02 | 170273.36 | 43.4%
F760 | Partial Depth Repair - Curbs (BCS 20.6.2) | square metre | 26 | 2500 | 65000 | 1732.47 | 45044.22 | 63%
F760 | Partial Depth Repair - Abutment (BCS 20.6.2) | square metre | 10 | 2500 | 25000 | 2454.81 | 24548.1 | 48.5%
F760 | Partial Depth Repair - Pier Caps (BCS 20.6.2) | square metre | 4 | 3500 | 14000 | 2902.88 | 11611.52 | 33.6%
F020 | Crack Repair - Deck and Approach Slabs (Special Provisions) | metre | 58 | 100 | 5800 | 164.89 | 9563.62 | 79.5%
F020 | Concrete Crack Repair - Pressure Injected Epoxy (Special Provisions) | metre | 40 | 400 | 16000 | 339.48 | 13579.2 | 65.2%
F974 | Waterproofing (BCS 16.5) | square metre | 583 | 80 | 46640 | 118.09 | 68846.47 | 19.2%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 121 | 250 | 30250 | 614.21 | 74319.41 | 47.3%
F018 | Approach Rail Transition - Supply and Install (Special Provisions) | lump sum | 1 | 40000 | 40000 | 99120.83 | 99120.83 | 43.8%
F018 | Concrete Drain Troughs - Supply and Install (Special Provisions) | lump sum | 1 | 40000 | 40000 | 78904.17 | 78904.17 | 48.3%
F018 | Concrete Sealer - Type 3 Pigmented (Special Provisions) | lump sum | 1 | 15000 | 15000 | 51361.46 | 51361.46 | 54.1%
F018 | Concrete Sealer - Type 1C (Special Provisions) | lump sum | 1 | 10000 | 10000 | 9606.25 | 9606.25 | 11.9%
F018 | Headslope Erosion Repairs (Special Provisions) | lump sum | 1 | 10000 | 10000 | 20895.83 | 20895.83 | 69.7%
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 15000 | 15000 | 6891.67 | 6891.67 | 97.8%
X002 | Extra Work - Various Repairs (Special Provisions) | Total Force Account | 1 | 50000 | 50000 | 50000 | 50000 | 0%
|  | Bridge File Modified Tender Value |  |  | 792430 |  | 1218361.42 | 6%
|  | Total Tender Value |  |  |  |  | 1339359.96 | 5.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 50 | 75000 | 81 | 121500 | 24.9%
Tender: 21981 ¦ Bridge File: 1031-1 ¦ Tender Opening Date: 2024-01-30
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21893 | Construct SPCSP Culvert | Culvert | Single | Replace Bridge with Culvert | 2023-2024 | 2024-01-31 | 3 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
13693-2 | 17 km West of Penhold | Central | 781:02 | Tindastoll Creek | 2 x 3360 SPCSP | 38 - 38 | 76 | 3.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 140000 | 140000 | 196153 | 196153 | 45.3%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 250000 | 250000 | 375954.67 | 375954.67 | 48.1%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 70000 | 70000 | 25845 | 25845 | 33%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 2133.67 | 6401.01 | 123.6%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 5 | 1500 | 7500 | 803.67 | 4018.35 | 99.1%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 50000 | 50000 | 57516 | 57516 | 55.7%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 40000 | 40000 | 13533.33 | 13533.33 | 62.5%
F493 | SPCSP - Supply (3.36 m Dia.) (BCS 18.7) | metre | 75.6 | 4000 | 302400 | 3185 | 240786 | 9.9%
F494 | SPCSP - Assembly (3.36 m Dia.) (BCS 18.7) | metre | 75.6 | 1300 | 98280 | 892.33 | 67460.15 | 18.4%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 160000 | 160000 | 204990 | 204990 | 26%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 80000 | 80000 | 82010.67 | 82010.67 | 35.6%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 160 | 275 | 44000 | 267.33 | 42772.8 | 8.9%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 120000 | 120000 | 199373.33 | 199373.33 | 21.1%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 1 | 20000 | 20000 | 28111.33 | 28111.33 | 68.5%
E020 | Straw Rolls (Special Provisions) | metre | 100 | 20 | 2000 | 17.17 | 1717 | 45.4%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 10 | 2000 | 10.3 | 2060 | 20.3%
|  | Bridge File Modified Tender Value |  |  | 1398180 |  | 1548702.64 | 18.7%
|  | Total Tender Value |  |  |  |  | 1623703.07 | 19.6%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 50 | 75000 | 50 | 75000 | 42.4%
Tender: 21893 ¦ Bridge File: 13693-2 ¦ Tender Opening Date: 2024-01-31
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22039 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2024-02-01 | 1 | 2024-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
72819-1 | At Rocky Mountain House | Central | 11:10 | CNR Railway | 14 x 610 RD | 15 ¦ 15 ¦ 15 | 45 | 17.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 210000 | 210000 | - | - | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 72819) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 100000 | 100000 | - | - | -
E612 | CN Rail - Flagging Protection (Special Provisions) | day | 15 | 3000 | 45000 | - | - | -
F755 | Surface Removal (50 mm Depth) (BCS 20.6.1) | square metre | 760 | 200 | 152000 | - | - | -
F770 | Abrasive Blasting - Deck Surface (BCS 20.6.3) | square metre | 760 | 30 | 22800 | - | - | -
Q554 | Cold Milling Asphalt Pavement - 50 <mm Depth> (HCS 3.16.6) (Special Provisions) | square metre | 520 | 30 | 15600 | - | - | -
F170 | Demolition and Disposal of Bridge Structure (Approach Slab) (BCS 21.4.1) | lump sum | 1 | 15000 | 15000 | - | - | -
F170 | Demolition and Disposal of Bridge Structure (Deck Joint Assembly) (BCS 21.4.1) | lump sum | 1 | 30000 | 30000 | - | - | -
F170 | Demolition and Disposal of Bridge Structure (Traffic Separation Barriers) (BCS 21.4.1) | lump sum | 1 | 20000 | 20000 | - | - | -
F170 | Demolition and Disposal of Bridge Structure (Existing Bridgerail) (BCS 21.4.1) | lump sum | 1 | 15000 | 15000 | - | - | -
F775 | Deck Overlay Concrete - Supply (B.F. 72819) (BCS 20.6.4) | cubic metre | 115 | 1800 | 207000 | - | - | -
F776 | Deck Overlay Concrete - Place (B.F. 72819) (BCS 20.6.4) | square metre | 760 | 150 | 114000 | - | - | -
F841 | Concrete (Class HPC) - Supply and Place (B.F. 72819) (BCS 4.27.1) | cubic metre | 85 | 2750 | 233750 | - | - | -
F853 | Stainless Reinforcing Steel - Supply (B.F. 72819) (BCS 5.6) | kilogram | 359 | 11 | 3949 | - | - | -
F851 | Corrosion Resistant Reinforcing Steel - Supply (B.F. 72819) (BCS 5.6) | kilogram | 29417 | 7 | 205919 | - | - | -
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 29776 | 3 | 89328 | - | - | -
F018 | Deck Link Slabs - Supply and Install (Special Provisions) | lump sum | 1 | 10000 | 10000 | - | - | -
F760 | Partial Depth Repair - Girders (BCS 20.6.2) | square metre | 40 | 2500 | 100000 | - | - | -
F760 | Partial Depth Repair - Curbs (BCS 20.6.2) | square metre | 19 | 2500 | 47500 | - | - | -
F760 | Partial Depth Repair - Abutment and Wingwall (BCS 20.6.2) | square metre | 14 | 2500 | 35000 | - | - | -
F760 | Partial Depth Repair - Pier Caps and Columns (BCS 20.6.2) | square metre | 65 | 3500 | 227500 | - | - | -
F020 | Crack Repair - Pressure Injected Epoxy - Supply and Install (Special Provisions) | metre | 50 | 400 | 20000 | - | - | -
F018 | Approach Slabs - Supply and Install (Special Provisions) | lump sum | 1 | 7500 | 7500 | - | - | -
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 99 | 700 | 69300 | - | - | -
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (TL-4 Double Tube) (BCS 12.4) | lump sum | 1 | 65000 | 65000 | - | - | -
F018 | Approach Rail Transition - Remove and Reinstall (Special Provisions) | lump sum | 1 | 10000 | 10000 | - | - | -
F018 | Pedestrian Barrier - Remove and Reinstall (Special Provisions) | lump sum | 1 | 35000 | 35000 | - | - | -
F018 | Concrete Sealer - Type 3 Pigmented (Special Provisions) | lump sum | 1 | 20000 | 20000 | - | - | -
F018 | Concrete Sealer - Type 1C (Special Provisions) | lump sum | 1 | 30000 | 30000 | - | - | -
F018 | Galvanized Steel Grating and Type 'C' Catch Basin - Supply and Install (Special Provisions) | lump sum | 1 | 15000 | 15000 | - | - | -
F018 | Concrete Slope Protection Repairs (Special Provisions) | lump sum | 1 | 70000 | 70000 | - | - | -
F018 | Deck Drain Extension at Pier Caps (Special Provisions) | lump sum | 1 | 5000 | 5000 | - | - | -
F018 | Bridge Plaque - Supply and Install (Special Provisions) | lump sum | 1 | 2500 | 2500 | - | - | -
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 2500 | 2500 | - | - | -
X002 | Extra Work - Various Repairs (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | - | - | -
|  | Bridge File Modified Tender Value |  |  | 2351146 |  | - | -
|  | Total Tender Value |  |  |  |  | - | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 50 | 75000 | - | - | -
Tender: 22039 ¦ Bridge File: 72819-1 ¦ Tender Opening Date: 2024-02-01
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22040 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2024-02-01 | 5 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
1569-1 | 14 km West of Spruce View | Central | 54:06 | North Raven River | 11 x 510 SC | 10 ¦ 12 ¦ 10 | 32 | 13.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 70000 | 70000 | 83566.67 | 83566.67 | 24%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 100000 | 100000 | 169800 | 169800 | 50%
F755 | Surface Removal (BCS 20.6.1) (Special Provisions) | square metre | 740 | 80 | 59200 | 114.33 | 84604.2 | 54.7%
F760 | Partial Depth Repair - Curb (inside) (BCS 20.6.2) (Special Provisions) | square metre | 22 | 2500 | 55000 | 2241.67 | 49316.74 | 26.9%
F760 | Partial Depth Repair - Curb (outside) (BCS 20.6.2) | square metre | 5 | 5000 | 25000 | 3528.33 | 17641.65 | 13.4%
F760 | Partial Depth Repair - Wingwall (BCS 20.6.2) | square metre | 2 | 2500 | 5000 | 3503.33 | 7006.66 | 16.3%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) (Special Provisions) | tonne | 130 | 500 | 65000 | 668.33 | 86882.9 | 29%
F974 | Waterproofing (BCS 16.5) | square metre | 400 | 150 | 60000 | 131.67 | 52668 | 22.9%
F022 | Concrete Sealer - Pigmented (Special Provisions) | square metre | 170 | 60 | 10200 | 130 | 22100 | 55.8%
F022 | Concrete Sealer - Type 1c (Special Provisions) | square metre | 70 | 60 | 4200 | 76.67 | 5366.9 | 58.7%
F018 | Deck Drain Removal (Special Provisions) | lump sum | 1 | 10000 | 10000 | 11200 | 11200 | 88.7%
F021 | Grouting Voids under the Approach Slab and Cap (Special Provisions) | cubic metre | 10 | 2000 | 20000 | 1895 | 18950 | 67.2%
F018 | Approach Rail Transition - Supply and Install (BCS 12.4) (Special Provisions) | lump sum | 1 | 80000 | 80000 | 106666.67 | 106666.67 | 30.4%
F018 | Erosion Repairs (Special Provisions) | lump sum | 1 | 40000 | 40000 | 14766.67 | 14766.67 | 29.6%
F020 | Drain Trough (Special Provisions) | metre | 30 | 2000 | 60000 | 1666.67 | 50000.1 | 15%
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 10000 | 10000 | 5333.33 | 5333.33 | 62.3%
X002 | Extra Work - Miscellaneous Repairs | Total Force Account | 1 | 50000 | 50000 | 50000 | 50000 | 0%
|  | Bridge File Modified Tender Value |  |  | 723600 |  | 835870.49 | 8.9%
|  | Total Tender Value |  |  |  |  | 918371.67 | 11.1%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 50 | 75000 | 55 | 82500 | 34%
Tender: 22040 ¦ Bridge File: 1569-1 ¦ Tender Opening Date: 2024-02-01
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
19213 | Construct SPCSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2023-2024 | 2024-02-07 | 4 | 2024-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
79509-2 | 83 km South of Grande Prairie | Peace | 40:38 | Ratson Creek | 1 x 6470 SPCSP | 76 | 76 | 6.5
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 400000 | 400000 | 538901.79 | 538901.79 | 48.1%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 250000 | 250000 | 1235727.98 | 1235727.98 | 20.5%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 15 | 2000 | 30000 | 2214.79 | 33221.85 | 9.1%
E018 | Fish Capture and Release (Special Provisions) | lump sum | 1 | 5000 | 5000 | 14034.49 | 14034.49 | 31.5%
E018 | Water Management (Special Provisions) | lump sum | 1 | 160000 | 160000 | 359051.17 | 359051.17 | 40.5%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 20000 | 20000 | 48368.41 | 48368.41 | 81.4%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 65000 | 65000 | 219332.39 | 219332.39 | 42.8%
F018 | Supply and Install Subdrains (Special Provisions) | lump sum | 1 | 15000 | 15000 | 50750.43 | 50750.43 | 49.6%
F488 | SPCSP - Supply (BCS 18.7) | lump sum | 1 | 1050000 | 1050000 | 503422.28 | 503422.28 | 9.2%
F489 | SPCSP - Assembly (BCS 18.7) | lump sum | 1 | 300000 | 300000 | 257416.84 | 257416.84 | 68.1%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 315000 | 315000 | 547530.32 | 547530.32 | 34%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 100000 | 100000 | 210134.92 | 210134.92 | 24.2%
E018 | Miscellaneous Environmental Work (Special Provisions) | lump sum | 1 | 90000 | 90000 | 166936.63 | 166936.63 | 77.7%
F515 | Heavy Rock Riprap (Class 2) (BCS 10.7) | cubic metre | 810 | 369 | 298890 | 414.38 | 335647.8 | 13%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 500000 | 500000 | 559506.32 | 559506.32 | 39.7%
E020 | Class 1M Rock Ditch Drains (Special Provisions) | metre | 147 | 450 | 66150 | 587.75 | 86399.25 | 12.1%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 415 | 15 | 6225 | 20.9 | 8673.5 | 31%
|  | Bridge File Modified Tender Value |  |  | 3671265 |  | 5175056.37 | 5.3%
|  | Total Tender Value |  |  |  |  | 5336054.14 | 5.5%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 107 | 160500 | 12.3%
Tender: 19213 ¦ Bridge File: 79509-2 ¦ Tender Opening Date: 2024-02-07
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
19645 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2024-02-08 | 3 | 2025-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
6615-1 | At Drumheller | Central | 9:06 | Red Deer River | 7 x 910 RB | 27 ¦ 34 ¦ 34 ¦ 34 ¦ 27 | 156 | 14.9
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 546416.3 | 546416.3 | 1325367 | 1325367 | 14.5%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 444000 | 444000 | 767444.33 | 767444.33 | 65.6%
X002 | Extra Work - Concrete Repairs (Special Provisions) | Total Force Account | 1 | 200000 | 200000 | 200000 | 200000 | 0%
F018 | Remove and Dispose - Existing Cover Plated V-Seal (Special Provisions) | lump sum | 1 | 48528 | 48528 | 228757 | 228757 | 27%
F018 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (Special Provisions) | lump sum | 1 | 363960 | 363960 | 904083.33 | 904083.33 | 35.4%
F018 | Barrier Cover Plates - Supply, Fabrication, Delivery and Installation (Special Provisions) | lump sum | 1 | 30000 | 30000 | 64384 | 64384 | 59.4%
F755 | Surface Removal - Roof Slab (BCS 20.6.1) | square metre | 93 | 170 | 15810 | 242.67 | 22568.31 | 35.1%
F755 | Surface Removal - Deck Concrete Overlay (BCS 20.6.1) (Special Provisions) | square metre | 1428 | 210 | 299880 | 195.67 | 279416.76 | 30.5%
F022 | Debonded Deck Concrete Overlay Removal (Special Provisions) | square metre | 345 | 500 | 172500 | 356.67 | 123051.15 | 27.5%
F760 | Partial Depth Repair - Deck, Roof Slab and Sidewalk (BCS 20.6.2) | square metre | 250 | 1750 | 437500 | 1151 | 287750 | 8.1%
F760 | Partial Depth Repair - Abutment (BCS 20.6.2) | square metre | 8 | 2000 | 16000 | 2482.67 | 19861.36 | 19%
F765 | Full Depth Repair - Deck, Roof Slab and Sidewalk (BCS 20.6.2) | square metre | 23 | 3450 | 79350 | 2776.33 | 63855.59 | 21.6%
F770 | Abrasive Blasting - Deck Surface - and Roof Slab Surface (BCS 20.6.3) | square metre | 1905 | 40 | 76200 | 31.33 | 59683.65 | 9.2%
F775 | Deck Overlay Concrete - Supply (BCS 20.6.4) | cubic metre | 115 | 2100 | 241500 | 3370.67 | 387627.05 | 30.6%
F776 | Deck Overlay Concrete - Place (BCS 20.6.4) | square metre | 1905 | 150 | 285750 | 179.67 | 342271.35 | 32.6%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 133 | 2100 | 279300 | 4982.67 | 662695.11 | 32.5%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 59 | 3200 | 188800 | 6972.67 | 411387.53 | 14.9%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 29250 | 10.5 | 307125 | 13.83 | 404527.5 | 16.3%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 29250 | 2.5 | 73125 | 4.73 | 138352.5 | 11.8%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (TL-4 Combination Barrier Bridgerail) (BCS 12.4) | lump sum | 1 | 243000 | 243000 | 170115 | 170115 | 8.3%
F018 | Supply and Install - Bearing Anchor Nuts and Washers (10 Locations) (Special Provisions) | lump sum | 1 | 6000 | 6000 | 19982 | 19982 | 85%
F018 | Supply and Install - Roof Slab Temporary Supports (Special Provisions) | lump sum | 1 | 12500 | 12500 | 32984.33 | 32984.33 | 35.8%
F018 | Remove and Dispose of East Pedestrian Railing (Special Provisions) | lump sum | 1 | 25500 | 25500 | 16826.67 | 16826.67 | 57%
F053 | Remove and Dispose of Existing Deck Drains (Special Provisions) | unit | 6 | 4000 | 24000 | 1938 | 11628 | 57.2%
F053 | Supply and Install - Deck Drains (Special Provisions) | unit | 6 | 5500 | 33000 | 4032.33 | 24193.98 | 34.6%
F018 | Concrete Removal - East Sidewalk and Barrier (Special Provisions) | lump sum | 1 | 632000 | 632000 | 1895136.33 | 1895136.33 | 19.7%
F018 | Concrete Removal - West Barrier (Special Provisions) | lump sum | 1 | 210000 | 210000 | 684278 | 684278 | 21.4%
F018 | Bridge Approach Barrier (East Side) (Special Provisions) | lump sum | 1 | 12000 | 12000 | 45545.67 | 45545.67 | 41.8%
F020 | Crack Repair - Gravity Fed Epoxy (Special Provisions) | metre | 250 | 130 | 32500 | 172 | 43000 | 27.1%
F185 | Non-Skid Polymer Overlay (Sidewalk) (BCS 15.8) (Special Provisions) | square metre | 467 | 400 | 186800 | 394.67 | 184310.89 | 6.2%
F018 | Clean and Apply Type 1c Sealer at Abutments (Special Provisions) | lump sum | 1 | 20000 | 20000 | 13486.33 | 13486.33 | 49.3%
F018 | West Pedestrian Railing Repairs (Special Provisions) | lump sum | 1 | 12000 | 12000 | 28982.33 | 28982.33 | 19.8%
F018 | Salvage and Reinstall Bridge Plaques and Information Plaques (Special Provisions) | lump sum | 1 | 8000 | 8000 | 5208.67 | 5208.67 | 70.7%
F018 | Fill Erosion Gullies and Regrade at Abutment Head Slopes (Special Provisions) | lump sum | 1 | 10000 | 10000 | 11992 | 11992 | 39.7%
F018 | Remove and Dispose APEX Gas Pipeline from Bridge (Special Provisions) | lump sum | 1 | 60000 | 60000 | 25489 | 25489 | 68%
G225 | Common Excavation (HCS 2.3.6) | cubic metre | 510 | 30 | 15300 | 89.33 | 45558.3 | 61.2%
G025 | Waste Excavation (Special Provisions) | cubic metre | 155 | 40 | 6200 | 125 | 19375 | 51%
G300 | Topsoil Placement (HCS 2.6.4) | square metre | 1300 | 2.5 | 3250 | 19.67 | 25571 | 43.6%
E609 | Hydro Seeding (HCS 2.20.4) | hectare | 0.13 | 10000 | 1300 | 50000 | 6500 | 5.9%
A805 | Supply of Aggregate - No Option (HCS 5.2.5) | tonne | 350 | 3 | 1050 | 18 | 6300 | 16.4%
B180 | Preparing Subgrade Surface (First Layer) (HCS 3.1.3) | square metre | 150 | 6 | 900 | 30 | 4500 | 17%
B282 | Granular Base Course Des. 2 Class 25 (HCS 3.6.8) (HCS 5.2.5) | tonne | 150 | 50 | 7500 | 96.33 | 14449.5 | 17.8%
Q991 | Asphalt Concrete Pavement - EPS Mix Type H2 (PG 58-34) (HCS 5.2.5) (HCS 3.50.7) | tonne | 200 | 200 | 40000 | 377.67 | 75534 | 28.6%
Q565 | Cold Milling Asphalt Pavement (HCS 3.16.6) | square metre | 1205 | 18 | 21690 | 27.33 | 32932.65 | 17.5%
X510 | Cutting of Pavement (HCS 3.40.3) | metre | 275 | 15 | 4125 | 20.33 | 5590.75 | 2.3%
X018 | Remove and Dispose Abandoned Telus Manholes (Special Provisions) | lump sum | 1 | 10000 | 10000 | 23324.67 | 23324.67 | 51.1%
X215 | Concrete Curb and Gutter - Remove and Dispose (HCS 2.17.4) | metre | 196 | 50 | 9800 | 96.33 | 18880.68 | 21.8%
X020 | Concrete Barrier - Remove and Dispose (Special Provisions) | metre | 82 | 80 | 6560 | 316 | 25912 | 32.5%
X220 | Concrete Surface - Remove and Dispose (HCS 2.17.4) | square metre | 436 | 75 | 32700 | 95.67 | 41712.12 | 24.9%
X022 | Asphalt Pathway - Remove and Dispose (Special Provisions) | square metre | 30 | 40 | 1200 | 100 | 3000 | 88.5%
X020 | Steel Post and Chain - Remove and Dispose (Special Provisions) | metre | 13 | 100 | 1300 | 127.67 | 1659.71 | 43.5%
X325 | Curb and Gutter (250 mm Standard) (HCS 4.2.5) | metre | 112 | 160 | 17920 | 387.67 | 43419.04 | 24.3%
X360 | Concrete Swale (500 mm wide) (HCS 4.2.5) (Special Provisions) | metre | 15.1 | 300 | 4530 | 618.33 | 9336.78 | 36%
X022 | Concrete Sidewalk (width varies) (Special Provisions) | square metre | 351 | 115 | 40365 | 303.67 | 106588.17 | 34.2%
X355 | Concrete Barrier - Single Slope (900 mm High) (HCS 4.2.5) | metre | 127 | 425 | 53975 | 1509.33 | 191684.91 | 29.4%
X020 | Concrete Slurry (Special Provisions) | metre | 35 | 40 | 1400 | 291.33 | 10196.55 | 75%
Q022 | Asphalt Pathway (Special Provisions) | square metre | 75 | 100 | 7500 | 254 | 19050 | 21.4%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 58 | 40 | 2320 | 67.67 | 3924.86 | 54.7%
S275 | Removal and Reinstallation or Disposal of Existing Sign Assembly - One Post (HCS 7.7.5) | sign | 14 | 200 | 2800 | 201.67 | 2823.38 | 22.2%
S034 | Steel Breakaway Post (60 mm dia.) - Supply and Install (Special Provisions) | post | 5 | 350 | 1750 | 585 | 2925 | 14.4%
S772 | Supply and Install Post (100 mm x 150 mm) (HCS 7.7.5) | post | 11 | 200 | 2200 | 245.33 | 2698.63 | 16%
S272 | Supply of Signs, Aluminum (HCS 5.18.3) | square metre | 4 | 175 | 700 | 202 | 808 | 20.6%
S273 | Supply of Signs, Aluminum - Reflective Sheeting for Specialized Applications (HCS 5.18.3) | square metre | 0.5 | 400 | 200 | 274.67 | 137.34 | 7.4%
S288 | Install Sign - Less than 1 m2 (HCS 7.7.5) | sign | 14 | 125 | 1750 | 98.33 | 1376.62 | 73.1%
S018 | Roadway Lines - Supplying Paint and Painting (Special Provisions) | lump sum | 1 | 5000 | 5000 | 14610 | 14610 | 21.3%
S342 | Durable Pavement Message - Stop Bar (HCS 7.3.5) (HCS 5.20.5) | message | 1 | 525 | 525 | 1084.33 | 1084.33 | 12.8%
S346 | Durable Pavement Message - Pedestrian Crossing (HCS 7.3.5) (HCS 5.20.5) | message | 2 | 800 | 1600 | 1793 | 3586 | 30.2%
U018 | Removal and Salvage of Existing Bridge Mounted Light Standards (Special Provisions) | lump sum | 1 | 20000 | 20000 | 18836.33 | 18836.33 | 31.6%
U110 | Removal and Salvage of Existing Standards (HCS 2.25.8) | unit | 1 | 4100 | 4100 | 7714.33 | 7714.33 | 23.1%
U100 | Trenching and Backfilling (HCS 2.25.8) | metre | 20 | 35 | 700 | 82.33 | 1646.6 | 24%
S400 | Underground Electrical Conduit - Supply and Install - Trench Excavation (HCS 2.7.4) | metre | 10 | 65 | 650 | 2160.67 | 21606.7 | 23.2%
U105 | Secondary Cable - Supply and Install (3C - #8 AWG TECK 90 - 1000V) (HCS 2.25.8) | metre | 20 | 25 | 500 | 49.67 | 993.4 | 22.1%
U018 | Bridge Electrical Conduit and Wire - Supply and Install (Special Provisions) | lump sum | 1 | 25000 | 25000 | 54360.67 | 54360.67 | 18.1%
U103 | Overhead Power Cable - Supply and Install (Special Provisions) | metre | 55 | 45 | 2475 | 146.67 | 8066.85 | 21.1%
U122 | Pre-Cast Concrete Street Light Base - Supply and Install (HCS 2.25.8) | unit | 1 | 4000 | 4000 | 5156.67 | 5156.67 | 22.8%
U130 | Salvaged Street Light Standard - Install (10.7m Davit with Existing Luminaire on Bridge Corbel) (HCS 2.25.8) | pole | 1 | 3000 | 3000 | 3551.33 | 3551.33 | 23.2%
U130 | Salvaged Street Light Standard - Install (10.7m Davit with New 73W Luminaire on Bridge Corbel) (HCS 2.25.8) | pole | 1 | 3500 | 3500 | 5776 | 5776 | 22.6%
U130 | Salvaged Street Light Standard - Install (12.0m Davit with New 73W Luminaire w/ Non-Frangible Base) (HCS 2.25.8) | pole | 1 | 2200 | 2200 | 5776 | 5776 | 22.6%
U102 | Junction Box - Supply and Install (Special Provisions) | unit | 2 | 1500 | 3000 | 847.67 | 1695.34 | 21.4%
U102 | Ground Rod - Supply and Install (Special Provisions) | unit | 1 | 1000 | 1000 | 1828 | 1828 | 22.2%
|  | Bridge File Modified Tender Value |  |  | 6010579.3 |  | 10808300.93 | 4.5%
|  | Total Tender Value |  |  |  |  | 11575153.83 | 4.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 2500 | - | - | 307 | 767500 | 13.4%
Tender: 19645 ¦ Bridge File: 6615-1 ¦ Tender Opening Date: 2024-02-08
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22430 | Remove Precast Concrete Girder Bridge | Bridge | Multiple | Remove Bridge | 2023-2024 | 2024-03-13 | 3 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
77563E-1 | 11 km East of Chestermere | Southern | 1:12 | CPR Railway | 11 x 610 RD | 11 ¦ 12 ¦ 11 | 34 | 13.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 170000 | 170000 | 147965.12 | 147965.12 | 40.1%
F750 | PRORATED - Traffic Accommodation for Bridge Construction (B.F. 77563E-1 & B.F.77563 W-2) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 447500 | 447500 | 327112.92 | 327112.92 | 34.3%
Q554 | Cold Milling Asphalt Pavement - 50 <mm Depth> (Special Provisions) | square metre | 1675 | 20 | 33500 | 10.13 | 16967.75 | 11.8%
F169 | Salvage of Existing Bridge Materials (B.F. 77563E-1) (BCS 21.4.2) | lump sum | 1 | 5000 | 5000 | 12636.52 | 12636.52 | 53.2%
F170 | Demolition and Disposal of Bridge Structure (B.F. 77563E-1) (BCS 21.4.1) | lump sum | 1 | 250000 | 250000 | 144485.13 | 144485.13 | 7.5%
X025 | Contaminated Soils - Waste Excavation (Special Provisions) | cubic metre | 375 | 125 | 46875 | 146.39 | 54896.25 | 31.3%
G225 | Common Excavation (HCS 2.3.6) (Special Provisions) | cubic metre | 1200 | 25 | 30000 | 18.31 | 21972 | 40.6%
G236 | Borrow Excavation - Contractor Supplied (HCS 2.3.6) (Special Provisions) | cubic metre | 6300 | 35 | 220500 | 39.01 | 245763 | 16.8%
G300 | Topsoil Placement (HCS 2.6.4) | square metre | 1750 | 2 | 3500 | 3.09 | 5407.5 | 49.8%
G320 | Topsoil - Supply and Place (Special Provisions) | square metre | 250 | 25 | 6250 | 18.03 | 4507.5 | 110.5%
B180 | Preparing Subgrade Surface (First Layer) (HCS 3.1.3) | square metre | 1500 | 8 | 12000 | 4.44 | 6660 | 30.1%
B282 | Granular Base Course Des. 2 Class 25 (HCS 3.6.8) | tonne | 1050 | 50 | 52500 | 60.65 | 63682.5 | 17.2%
Q996 | Asphalt Concrete Pavement - EPS Mix Type S3 (PG 58-34) (HCS 3.50.7) (Special Provisions) | tonne | 300 | 250 | 75000 | 183.77 | 55131 | 20.8%
Q990 | Asphalt Concrete Pavement - EPS Mix Type H1 (PG 58-34) (HCS 3.50.7) | tonne | 450 | 225 | 101250 | 306.21 | 137794.5 | 52.9%
Q972 | PRORATED - Inter-Laboratory Repeatability Testing (Special Provisions) | lump sum | 1 | 2500 | 2500 | 3674.5 | 3674.5 | 37.1%
E614 | Broadcast Seeding (HCS 2.20.4) | square metre | 1750 | 5 | 8750 | 1.8 | 3150 | 18.5%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 1200 | 10 | 12000 | 3.89 | 4668 | 11.2%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 120 | 25 | 3000 | 16.51 | 1981.2 | 40.8%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 197.5 | 25 | 4937.5 | 29.89 | 5903.28 | 59.4%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 95 | 300 | 28500 | 238.5 | 22657.5 | 38.2%
S841 | Remove and Dispose of Existing High Tension Cable Barrier (HCS 2.11.9) | metre | 145 | 25 | 3625 | 32.34 | 4689.3 | 65.5%
S836 | High Tension Cable Barrier (TL-4, design dynamic deflection 2.44 m) - Supply and Install (HCS 2.11.9) | metre | 117.5 | 150 | 17625 | 162.42 | 19084.35 | 45.7%
D100 | Culverts - Remove and Dispose (C.S.P.) (up to 700 mm dia.) (HCS 2.4.4) | metre | 6.5 | 200 | 1300 | 87 | 565.5 | 87.7%
S706 | Milled Rumble Strip - Shoulder (HCS 3.52.4) | kilometre | 0.44 | 5000 | 2200 | 11405.61 | 5018.47 | 53.1%
S351 | Roadway Lines - Supplying Paint and Painting (Lane Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.23 | 10000 | 2300 | 10824.95 | 2489.74 | 107.8%
|  | Bridge File Modified Tender Value |  |  | 1540612.5 |  | 1318863.53 | 10.6%
|  | Total Tender Value |  |  |  |  | 3016936.57 | 10.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 4000 | 40 | 160000 | 47 | 188000 | 24.1%
Tender: 22430 ¦ Bridge File: 77563-1 ¦ Tender Opening Date: 2024-02-13
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22430 | Remove Precast Concrete Girder Bridge | Bridge | Multiple | Remove Bridge | 2023-2024 | 2024-02-13 | 3 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
77563W-2 | 11 km East of Chestermere | Southern | 1:12 | CPR Railway | 11 x 610 RD | 11 ¦ 12 ¦ 11 | 34 | 13.6
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 170000 | 170000 | 147965.12 | 147965.12 | 40.1%
F750 | PRORATED - Traffic Accommodation for Bridge Construction (B.F. 77563E-1 & B.F.77563 W-2) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 447500 | 447500 | 327112.92 | 327112.92 | 34.3%
Q554 | Cold Milling Asphalt Pavement - 50 <mm Depth> (Special Provisions) | square metre | 1675 | 20 | 33500 | 10.13 | 16967.75 | 11.8%
F169 | Salvage of Existing Bridge Materials (B.F. 77563W-2) (BCS 21.4.2) | lump sum | 1 | 5000 | 5000 | 12636.52 | 12636.52 | 53.2%
F170 | Demolition and Disposal of Bridge Structure (B.F. 77563W-2) (BCS 21.4.1) | lump sum | 1 | 250000 | 250000 | 149055.28 | 149055.28 | 6.7%
X025 | Contaminated Soils - Waste Excavation (Special Provisions) | cubic metre | 375 | 125 | 46875 | 146.39 | 54896.25 | 31.3%
G225 | Common Excavation (HCS 2.3.6) (Special Provisions) | cubic metre | 1200 | 25 | 30000 | 18.31 | 21972 | 40.6%
G236 | Borrow Excavation - Contractor Supplied (HCS 2.3.6) (Special Provisions) | cubic metre | 6300 | 35 | 220500 | 39.01 | 245763 | 16.8%
G300 | Topsoil Placement (HCS 2.6.4) | square metre | 1750 | 2 | 3500 | 3.09 | 5407.5 | 49.8%
G320 | Topsoil - Supply and Place (Special Provisions) | square metre | 250 | 25 | 6250 | 18.03 | 4507.5 | 110.5%
B180 | Preparing Subgrade Surface (First Layer) (HCS 3.1.3) | square metre | 1500 | 8 | 12000 | 4.44 | 6660 | 30.1%
B282 | Granular Base Course Des. 2 Class 25 (HCS 3.6.8) | tonne | 1050 | 50 | 52500 | 60.65 | 63682.5 | 17.2%
Q996 | Asphalt Concrete Pavement - EPS Mix Type S3 (PG 58-34) (HCS 3.50.7) (Special Provisions) | tonne | 300 | 250 | 75000 | 183.77 | 55131 | 20.8%
Q990 | Asphalt Concrete Pavement - EPS Mix Type H1 (PG 58-34) (HCS 3.50.7) | tonne | 450 | 225 | 101250 | 306.21 | 137794.5 | 52.9%
Q972 | PRORATED - Inter-Laboratory Repeatability Testing (Special Provisions) | lump sum | 1 | 2500 | 2500 | 3674.5 | 3674.5 | 37.1%
E614 | Broadcast Seeding (HCS 2.20.4) | square metre | 1750 | 5 | 8750 | 1.8 | 3150 | 18.5%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 1200 | 10 | 12000 | 3.89 | 4668 | 11.2%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 120 | 25 | 3000 | 16.51 | 1981.2 | 40.8%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) | metre | 197.5 | 25 | 4937.5 | 29.89 | 5903.28 | 59.4%
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 95 | 300 | 28500 | 238.5 | 22657.5 | 38.2%
S841 | Remove and Dispose of Existing High Tension Cable Barrier (HCS 2.11.9) | metre | 145 | 25 | 3625 | 32.34 | 4689.3 | 65.5%
S836 | High Tension Cable Barrier (TL-4, design dynamic deflection 2.44 m) - Supply and Install (HCS 2.11.9) | metre | 117.5 | 150 | 17625 | 162.42 | 19084.35 | 45.7%
D100 | Culverts - Remove and Dispose (C.S.P.) (up to 700 mm dia.) (HCS 2.4.4) | metre | 6.5 | 200 | 1300 | 87 | 565.5 | 87.7%
S706 | Milled Rumble Strip - Shoulder (HCS 3.52.4) | kilometre | 0.44 | 5000 | 2200 | 11405.61 | 5018.47 | 53.1%
S351 | Roadway Lines - Supplying Paint and Painting (Lane Dividing and 2 Edge Lines) (HCS 7.2.6) (HCS 5.20.5) | kilometre | 0.23 | 10000 | 2300 | 10824.95 | 2489.74 | 107.8%
|  | Bridge File Modified Tender Value |  |  | 1540612.5 |  | 1323433.68 | 10.8%
|  | Total Tender Value |  |  |  |  | 3016936.57 | 10.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 4000 | 40 | 160000 | 47 | 188000 | 24.1%
Tender: 22430 ¦ Bridge File: 77563-2 ¦ Tender Opening Date: 2024-02-13
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23535 | Construct Sign Structures | Sign Structure | Highway | New Sign Structures | 2023-2024 | 2024-02-13 | 4 | 2025-10-01
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
Multiple | Deerfoot Trail | Southern | - | - | - | - | - | -
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 390443.81 | 390443.81 | 621655.53 | 621655.53 | 23.5%
S018 | PRORATED - Traffic Accommodation (Special Provisions) | lump sum | 1 | 259506.04 | 259506.04 | 804019.76 | 804019.76 | 15.5%
F046 | Sign Panels (Overhead) - Extruded Aluminum - Remove and Dispose (Special Provisions) | panel | 1 | 4000 | 4000 | 7839.27 | 7839.27 | 47.4%
X038 | Overhead Bridge Sign Structure and Sign Panels - Remove and Dispose (Special Provisions) | sign | 4 | 25000 | 100000 | 17824.78 | 71299.12 | 17.3%
X038 | Overhead Cantilever Sign Structure and Sign Panels - Remove and Dispose (Special Provisions) | sign | 2 | 20000 | 40000 | 10643.82 | 21287.64 | 29.2%
X011 | Overhead Sign Structure - Foundation Demolition and Disposal (Special Provisions) | bases | 10 | 6500 | 65000 | 17018.41 | 170184.1 | 34.5%
F992 | Sign Panels - Extruded Aluminum - Supply and Install (BCS 24.5) | square metre | 474 | 550 | 260700 | 719.04 | 340824.96 | 19.6%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection - B.F. 77801ZS2-6 (BCS 24.5) | lump sum | 1 | 550000 | 550000 | 649768.44 | 649768.44 | 27.4%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection - B.F. 73907ZN2-6 (BCS 24.5) | lump sum | 1 | 550000 | 550000 | 649483.27 | 649483.27 | 27.5%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection - B.F. 77251ZN1-8 (BCS 24.5) | lump sum | 1 | 280000 | 280000 | 373860.8 | 373860.8 | 25.3%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection - B.F. 73794ZS3-9 (BCS 24.5) | lump sum | 1 | 550000 | 550000 | 659348.92 | 659348.92 | 25.8%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection - B.F. 73794ZS2-8 (BCS 24.5) | lump sum | 1 | 350000 | 350000 | 469177.85 | 469177.85 | 35.7%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection - B.F. 77251ZN2-9 (BCS 24.5) | lump sum | 1 | 350000 | 350000 | 483739.19 | 483739.19 | 31.9%
F991 | Overhead Sign Structure - Supply and Fabrication, Foundations, Delivery and Erection - B.F. 77251ZN3-10 (BCS 24.5) | lump sum | 1 | 550000 | 550000 | 676162.76 | 676162.76 | 23.8%
|  | Bridge File Modified Tender Value |  |  | 4299649.85 |  | 5998651.61 | 24.4%
|  | Total Tender Value |  |  |  |  | 37120269.52 | 1.6%
Tender: 23535 ¦ Bridge File: Multiple ¦ Tender Opening Date: 2024-02-13
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
19214 | Construct SPCSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2023-2024 | 2024-02-14 | 7 | 2024-09-30
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
9276-2 | 24 km East of Teepee Creek | Peace | 674:02 | Tributary to Kleskun Creek | 1 x 3990 SPCSP | 41 | 41 | 4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 150000 | 150000 | 112737.53 | 112737.53 | 16.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 20 | 1500 | 30000 | 603.33 | 12066.6 | 129.7%
E018 | Water Management | lump sum | 1 | 25000 | 25000 | 23385 | 23385 | 37.5%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 225000 | 225000 | 72746 | 72746 | 74%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 25000 | 25000 | 58733.33 | 58733.33 | 46.6%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 18750 | 18750 | 106164.8 | 106164.8 | 69.7%
F488 | SPCSP - Supply (BCS 18.7) | lump sum | 1 | 216000 | 216000 | 201706.33 | 201706.33 | 48.7%
F489 | SPCSP - Assembly (BCS 18.7) | lump sum | 1 | 65000 | 65000 | 100729.33 | 100729.33 | 70%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 65000 | 65000 | 87121 | 87121 | 23.3%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 30000 | 30000 | 36990.67 | 36990.67 | 30.9%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 220 | 337 | 74140 | 161 | 35420 | 49.2%
F492 | Roadway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 120000 | 120000 | 103768 | 103768 | 58.2%
E020 | Class 1M Rock Ditch Drains (Special Provisions) | metre | 33 | 450 | 14850 | 307.55 | 10149.15 | 55.6%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 240 | 15 | 3600 | 13.43 | 3223.2 | 46.6%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 1040 | 10 | 10400 | 5.77 | 6000.8 | 12.4%
|  | Bridge File Modified Tender Value |  |  | 1072740 |  | 970941.74 | 15.9%
|  | Total Tender Value |  |  |  |  | 1026939.04 | 15.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 37 | 55500 | 18.4%
Tender: 19214 ¦ Bridge File: 9276-2 ¦ Tender Opening Date: 2024-02-14
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22727 | Construct SPCSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2023-2024 | 2024-02-27 | 4 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
75369-2 | Near Millet | Central | 2:30 | Pipestone Creek | 2 x 4300 SPCSP | 94 - 94 | 188 | 4.3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 500000 | 500000 | 1075094.04 | 1075094.04 | 55.5%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 1000000 | 1000000 | 2141426.27 | 2141426.27 | 47.9%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 60000 | 60000 | 286717.48 | 286717.48 | 46%
E612 | Fish Capture and Release (Special Provisions) | day | 4 | 4000 | 16000 | 1064.32 | 4257.28 | 108.6%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 8 | 1500 | 12000 | 580.28 | 4642.24 | 91.9%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 60000 | 60000 | 886512.99 | 886512.99 | 136.7%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 300000 | 300000 | 212394.94 | 212394.94 | 53.7%
F493 | SPCSP - Supply (4.3 m Dia.) (BCS 18.7) | metre | 187.76 | 6500 | 1220440 | 3506.44 | 658369.17 | 15.7%
F494 | SPCSP - Assembly (4.3 m Dia.) (BCS 18.7) | metre | 187.76 | 2500 | 469400 | 1151.34 | 216175.6 | 45.4%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 550000 | 550000 | 664605.34 | 664605.34 | 10.6%
F610 | Concrete End Treatment (BCS 18.7) | lump sum | 1 | 80000 | 80000 | 138718.48 | 138718.48 | 47.8%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 360 | 250 | 90000 | 406.03 | 146170.8 | 64.7%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 600000 | 600000 | 664252.77 | 664252.77 | 29%
S841 | Remove and Dispose of Existing High Tension Cable Barrier (HCS 2.11.9) | metre | 360 | 125 | 45000 | 26.86 | 9669.6 | 48.8%
S842 | Remove and Reinstall Existing High Tension Cable Barrier (HCS 2.11.9) | metre | 70 | 250 | 17500 | 131.64 | 9214.8 | 37.3%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 1 | 15000 | 15000 | 17978.19 | 17978.19 | 32.7%
E020 | Straw Rolls (Special Provisions) | metre | 250 | 20 | 5000 | 12.81 | 3202.5 | 19%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 400 | 10 | 4000 | 13.82 | 5528 | 53.5%
|  | Bridge File Modified Tender Value |  |  | 5044340 |  | 7144930.49 | 26.8%
|  | Total Tender Value |  |  |  |  | 7339928.99 | 26.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 90 | 135000 | 130 | 195000 | 6.3%
Tender: 22727 ¦ Bridge File: 75369-2 ¦ Tender Opening Date: 2024-02-27
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21582 | Construct SLC Precast Concrete Girder Bridge | Wildlife Bridge | Combined | New Wildlife Bridge | 2023-2024 | 2024-02-28 | 3 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
84165-1 | 5 km West of Lundbreck | Southern | 3:04 | Wildlife Trail | 12 x 510 SLC | 16 | 16 | 14.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 477434.82 | 477434.82 | 395682.46 | 395682.46 | 14.9%
F750 | PRORATED - Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 28418.74 | 28418.74 | 74009.16 | 74009.16 | 39.5%
F018 | Temporary Detour Road (Special Provisions) | lump sum | 1 | 750000 | 750000 | 1106549.48 | 1106549.48 | 3.2%
C003 | Supply, Delivery and Installation of Specified Trees (Special Provisions) | lump sum | 1 | 9000 | 9000 | 46653.23 | 46653.23 | 53.4%
E609 | Hydro Seeding (HCS 2.20.4) (Special Provisions) | hectare | 3.39 | 9200 | 31188 | 16412.76 | 55639.26 | 56.3%
E608 | Broadcast Seeding (HCS 2.20.4) (Special Provisions) | hectare | 0.09 | 32000 | 2880 | 65125.25 | 5861.27 | 78.4%
G225 | Common Excavation (HCS 2.3.6) (Special Provisions) | cubic metre | 3200 | 15 | 48000 | 32.58 | 104256 | 13.1%
B280 | Granular Base Course Des. 2 Class 25 (HCS 3.6.8) (HCS 5.2.5) (Special Provisions) | tonne | 680 | 35 | 23800 | 62.03 | 42180.4 | 39.5%
F190 | Backfill - Des. 2 Class 40 (BCS 2.4) (Special Provisions) | lump sum | 1 | 72000 | 72000 | 142915.51 | 142915.51 | 28.3%
F018 | Drainage Improvements (Special Provisions) | lump sum | 1 | 25000 | 25000 | 34750.19 | 34750.19 | 50.7%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 404 | 350 | 141400 | 343.59 | 138810.36 | 9.9%
F816 | Pile Set-up (Driven Piles) (BCS 3.6.1) | pile | 34 | 4500 | 153000 | 4631.86 | 157483.24 | 52.8%
F818 | Pile Driving (BCS 3.6.1) | metre | 404 | 85 | 34340 | 88.53 | 35766.12 | 4%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 200 | 1800 | 360000 | 1933.46 | 386692 | 4.6%
F841 | Concrete (Class HPC) - Supply and Place (BCS 4.27.1) | cubic metre | 109 | 2900 | 316100 | 2165.49 | 236038.41 | 25.7%
F850 | Plain Reinforcing Steel - Supply (BCS 5.6) | kilogram | 21255 | 3 | 63765 | 3.33 | 70779.15 | 7.6%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 9040 | 8 | 72320 | 11.74 | 106129.6 | 14.2%
F853 | Stainless Reinforcing Steel - Supply (BCS 5.6) | kilogram | 682 | 10.5 | 7161 | 20.46 | 13953.72 | 4.7%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 30977 | 2.25 | 69698.25 | 3.22 | 99745.94 | 12%
F020 | Elastomeric Pad Bearings - Supply and Install | metre | 35 | 120 | 4200 | 5474.73 | 191615.55 | 130.7%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) | lump sum | 1 | 600000 | 600000 | 535575.23 | 535575.23 | 12.1%
F780 | Bridgerail - Supply and Install (BCS 12.4) | lump sum | 1 | 30000 | 30000 | 33992.88 | 33992.88 | 32.8%
S288 | Install Sign - Less than 1 m2 (HCS 7.7.5) | sign | 4 | 250 | 1000 | 249.31 | 997.24 | 50.1%
F970 | Miscellaneous Iron - Bridge Plaque - Supply and Install (BCS 13.5) | lump sum | 1 | 1000 | 1000 | 2434.71 | 2434.71 | 70.6%
F974 | Waterproofing (BCS 16.5) | square metre | 390 | 70 | 27300 | 112.76 | 43976.4 | 18.9%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) (Special Provisions) | tonne | 150 | 380 | 57000 | 400.58 | 60087 | 37.5%
S825 | Remove and Dispose of Existing Guardrail (HCS 2.19.4) (Special Provisions) | metre | 340 | 18 | 6120 | 35.24 | 11981.6 | 26.4%
F019 | Approach Guardrail Transition (Special Provisions) | location | 4 | 15000 | 60000 | 10214.37 | 40857.48 | 20.5%
S836 | High Tension Cable Barrier (TL-4) - Supply and Install (HCS 2.11.9) | metre | 400 | 120 | 48000 | 122.31 | 48924 | 7.8%
S837 | High Tension Cable Barrier End Terminal (Crashworthy) - Supply and Install (HCS 2.11.9) | unit | 4 | 12000 | 48000 | 13825.13 | 55300.52 | 16%
S838 | High Tension Cable Barrier Transition to W-Beam (TL-4) - Supply and Install (HCS 2.11.9) | unit | 4 | 10000 | 40000 | 11193.82 | 44775.28 | 43%
S830 | Flexible Guide Post/Delineator - Round - Supply and Install (HCS 5.28.3) (HCS 2.19.4) | post | 12 | 85 | 1020 | 100.23 | 1202.76 | 14.2%
F018 | Line Painting (Special Provisions) | lump sum | 1 | 18000 | 18000 | 22559.89 | 22559.89 | 57%
F018 | Rumble Strips (Special Provisions) | lump sum | 1 | 3000 | 3000 | 10830.83 | 10830.83 | 32.2%
C003 | Landscaping (Special Provisions) | lump sum | 1 | 12000 | 12000 | 44774.18 | 44774.18 | 45.6%
C057 | Imported Topsoil Placement - Revegetation Area (Special Provisions) | cubic metre | 900 | 14 | 12600 | 90.41 | 81369 | 13.4%
C012 | Hazard Markers (Special Provisions) | each | 4 | 250 | 1000 | 479.85 | 1919.4 | 13.4%
|  | Bridge File Modified Tender Value |  |  | 3655745.81 |  | 4487069.45 | 5.5%
|  | Total Tender Value |  |  |  |  | 11437015.16 | 6.3%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 147 | 220500 | 9%
F003 | Lane Closure for Bridge Construction (GCS 1.2.42.5) (Special Provisions) | day | 1500 | - | - | 120 | 180000 | 19%
Tender: 21582 ¦ Bridge File: 84165-1 ¦ Tender Opening Date: 2024-02-28
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21915 | Construct SLW Precast Concrete Girder Bridge | Bridge | Single | Replace Bridge with Bridge | 2023-2024 | 2024-03-05 | 5 | 2024-10-31
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
7765-2 | 65 km Southeast of Hanna | Central | 570:02 | Berry Creek | 9 x 510 SLW | 10 ¦ 14 ¦ 10 | 34 | 11.1
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 400000 | 400000 | 355854.2 | 355854.2 | 25.8%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 300000 | 300000 | 259650 | 259650 | 26.9%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 50000 | 50000 | 12956.67 | 12956.67 | 60.6%
E612 | Fish Capture and Release (Special Provisions) | day | 3 | 4000 | 12000 | 364.33 | 1092.99 | 69.4%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 6 | 1500 | 9000 | 464.33 | 2785.98 | 71.8%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 100000 | 100000 | 72000 | 72000 | 37.1%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 25000 | 25000 | 22366.67 | 22366.67 | 89.2%
F813 | Supply of Piling - Galvanized Steel H-Pile (BCS 3.6.1) | metre | 296 | 400 | 118400 | 305 | 90280 | 11%
F812 | Supply of Piling - Plain Steel H-Pile (BCS 3.6.1) | metre | 238 | 300 | 71400 | 193.67 | 46093.46 | 10.6%
F824 | Drill Rig Set-up (Drilled Piles) (BCS 3.6.2) | pile | 36 | 10000 | 360000 | 9750 | 351000 | 5.5%
F826 | Pile Installation (Drilled Piles) (BCS 3.6.2) | metre | 534 | 1000 | 534000 | 6.93 | 3700.62 | 31.6%
F822 | Pile Concrete (Class) - Supply and Place (BCS 4.27.1) | cubic metre | 120 | 1800 | 216000 | 868 | 104160 | 31.1%
F018 | Abutment Construction (Special Provisions) | lump sum | 1 | 180000 | 180000 | 170833.33 | 170833.33 | 14.4%
F018 | Pier Construction (Special Provisions) | lump sum | 1 | 120000 | 120000 | 82910 | 82910 | 5%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1702 | 9 | 15318 | 8.33 | 14177.66 | 23.4%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1702 | 2.5 | 4255 | 2.03 | 3455.06 | 36.5%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) | cubic metre | 15 | 2200 | 33000 | 2136.67 | 32050.05 | 28.6%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 240 | 300 | 72000 | 211.67 | 50800.8 | 7.3%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 10 m Type SLW 510 (14 Interior, 4 Exterior) (BCS 7.4) | lump sum | 1 | 500000 | 500000 | 334766.67 | 334766.67 | 15.9%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection - 14 m Type SLW 510 (7 Interior, 2 Exterior) (BCS 7.4) | lump sum | 1 | 350000 | 350000 | 265300 | 265300 | 23.7%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 5000 | 5000 | 1681.67 | 1681.67 | 22.7%
F974 | Waterproofing (BCS 16.5) | square metre | 410 | 100 | 41000 | 72 | 29520 | 8.6%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) | tonne | 78 | 550 | 42900 | 235.67 | 18382.26 | 20.5%
F018 | Roadway Work (Special Provisions) | lump sum | 1 | 350000 | 350000 | 572400 | 572400 | 16.7%
F780 | Bridgerail - Supply and Install | lump sum | 1 | 45000 | 45000 | 30630 | 30630 | 13.3%
F752 | Guardrail - Supply and Install (BCS 14.5) | lump sum | 1 | 50000 | 50000 | 48660 | 48660 | 11.9%
G475 | New Fence - Supply and Install - Class B (HCS 2.12.5) | kilometre | 0.5 | 20000 | 10000 | 15336.67 | 7668.34 | 58.7%
E020 | Straw Rolls (Special Provisions) | metre | 200 | 20 | 4000 | 9.5 | 1900 | 28.2%
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 200 | 10 | 2000 | 9.43 | 1886 | 8.5%
|  | Bridge File Modified Tender Value |  |  | 4020273 |  | 2988962.43 | 8.1%
|  | Total Tender Value |  |  |  |  | 3100974.33 | 7.4%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 80 | 120000 | 75 | 112500 | 16.34%
Tender: 21915 ¦ Bridge File: 7765-2 ¦ Tender Opening Date: 2024-03-05
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
20595 | Construct SWSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2023-2024 | 2024-03-07 | 5 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
1710-2 | 15 km East of Penhold | Central | 42:08 | Tributary to Threehills Creek | 1 x 1200 SWSP | 41 | 41 | 1.2
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 59595 | 59595 | 38987.5 | 38987.5 | 46.4%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 50000 | 50000 | 9400 | 9400 | 60.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 8 | 1500 | 12000 | 250 | 2000 | 84.9%
E612 | Fish Capture and Release (Special Provisions) | day | 4 | 5000 | 20000 | 731.67 | 2926.68 | 86.4%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 5000 | 5000 | 10914.5 | 10914.5 | 39.2%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 5000 | 5000 | 9743 | 9743 | 42.1%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 30000 | 30000 | 20843 | 20843 | 9.3%
D26 | Smooth Wall Steel Pipe - Supply and Install (1 200 mm dia.) (HCS 5.22.4) | metre | 41.3 | 4500 | 185850 | 2635.05 | 108827.57 | 21.3%
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 80 | 650 | 52000 | 514.17 | 41133.6 | 26.3%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 50 | 325 | 16250 | 330.09 | 16504.5 | 26.2%
G452 | Remove and Dispose of Existing Fence (HCS 2.12.5) | kilometre | 0.05 | 10000 | 500 | 43333.33 | 2166.67 | 43.5%
C248 | Temporary Fencing (Special Provisions) | metre | 50 | 30 | 1500 | 53.67 | 2683.5 | 28.5%
G480 | New Fence - Supply and Install - Class C (HCS 2.12.5) | kilometre | 0.05 | 35000 | 1750 | 80766.67 | 4038.33 | 27.2%
E020 | Erosion Control Barrier (Fibre Roll) (Special Provisions) | metre | 150 | 15 | 2250 | 15.83 | 2374.5 | 41.5%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 200 | 15 | 3000 | 9.7 | 1940 | 38.8%
E018 | Clearing, Topsoil, and Seeding (Special Provisions) | lump sum | 1 | 12000 | 12000 | 10666.67 | 10666.67 | 8.8%
|  | Bridge File Modified Tender Value |  |  | 456695 |  | 285150.02 | 8.4%
|  | Total Tender Value |  |  |  |  | 305650.09 | 5.9%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 30 | 45000 | 14 | 21000 | 38.8%
Tender: 20595 ¦ Bridge File: 1710-2 ¦ Tender Opening Date: 2024-03-07
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
21875 | Replace Superstructure SLW Precast Concrete Girder Bridge | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2024-03-08 | 6 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
9173-1 | 2 km North of Empress | Central | 562:02 | Empress Creek | 8 x 510 SLW (Modified) | 8 ¦ 10 ¦ 8 | 26 | 10
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 130000 | 130000 | 185243.33 | 185243.33 | 15.2%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 100000 | 100000 | 66583.33 | 66583.33 | 39.2%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 50000 | 50000 | 165066.67 | 165066.67 | 36.6%
Q554 | Cold Milling Asphalt Pavement - 50 <mm Depth> (HCS 3.16.6) (Special Provisions) | square metre | 180 | 30 | 5400 | 51.5 | 9270 | 54.3%
F760 | Partial Depth Repair - Pier Caps & Abutment (BCS 20.6.2) (Special Provisions) | square metre | 13 | 3000 | 39000 | 3753.33 | 48793.29 | 63.1%
F941 | Precast Concrete Units - Supply and Fabrication, Delivery and Erection (BCS 7.4) (Special Provisions) | lump sum | 1 | 650000 | 650000 | 496333.33 | 496333.33 | 8.3%
F834 | Concrete (Class C) - Supply and Place (BCS 4.27.1) (Special Provisions) | cubic metre | 12 | 2500 | 30000 | 3921.67 | 47060.04 | 48.3%
F851 | Corrosion Resistant Reinforcing Steel - Supply (BCS 5.6) | kilogram | 1376 | 10 | 13760 | 13.67 | 18809.92 | 34%
F854 | Reinforcing Steel - Place (BCS 5.6) | kilogram | 1376 | 4 | 5504 | 4.75 | 6536 | 78.2%
F974 | Waterproofing (BCS 16.5) | square metre | 307 | 90 | 27630 | 115 | 35305 | 34.2%
F982 | Asphalt Concrete Pavement - Mix Type M1 (PG 52-34) Mix Type M1 (PG 52-34) (BCS 17.7.2) (Special Provisions) | tonne | 88 | 600 | 52800 | 495 | 43560 | 44.6%
F781 | Bridgerail - Supply and Fabrication, Delivery and Installation (BCS 12.4) | lump sum | 1 | 80000 | 80000 | 51883.33 | 51883.33 | 3%
F752 | Guardrail - Supply and Install (BCS 14.5) (Special Provisions) | lump sum | 1 | 45000 | 45000 | 46883.33 | 46883.33 | 26.8%
F022 | Concrete Sealer - Type 1c (Special Provisions) | square metre | 73 | 80 | 5840 | 156.67 | 11436.91 | 65.2%
F151 | Protection of the Environment (BCS 22.25.1) | lump sum | 1 | 30000 | 30000 | 43316.67 | 43316.67 | 30.5%
F150 | Surface Preparation and Painting - Pier Pipes and Braces (BCS 22.25.2) (Special Provisions) | lump sum | 1 | 30000 | 30000 | 136966.67 | 136966.67 | 52.6%
F022 | Erosion Damage Repairs (Special Provisions) | square metre | 40 | 250 | 10000 | 208.33 | 8333.2 | 65.2%
F970 | Miscellaneous Iron - Supply, Fabrication and Installation (BCS 13.5) (Special Provisions) | lump sum | 1 | 10000 | 10000 | 15533.33 | 15533.33 | 51.3%
F018 | Drain Rock Drain Troughs (Special Provisions) | lump sum | 1 | 15000 | 15000 | 31233.33 | 31233.33 | 61.1%
X002 | Extra Work - Miscellaneous Repairs (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | 100000 | 100000 | 0%
|  | Bridge File Modified Tender Value |  |  | 1429934 |  | 1568147.68 | 2.7%
|  | Total Tender Value |  |  |  |  | 1657143 | 3.6%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 60 | 90000 | 59 | 88500 | 30.2%
Tender: 21875 ¦ Bridge File: 9173-1 ¦ Tender Opening Date: 2024-03-08
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
42 | Construct SPCSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2023-2024 | 2024-03-14 | 5 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
8098-2 | Near Rocky Mountain House | Central | 752:04 | Tributary to North Saskatchewan River | 1 x 2700 SPCSP | 44 | 44 | 2.7
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 194000 | 194000 | 217419 | 217419 | 19.9%
F750 | Traffic Accommodation for Bridge Construction (Including Pedestrian Accommodation) (HCS 7.1.12) (HCS 7.1.15) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 47736 | 47736 | 2.4%
E018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 35000 | 35000 | 60816.33 | 60816.33 | 40%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 4 | 1500 | 6000 | 1693.83 | 6775.32 | 52.9%
E612 | Fish Capture & Release (Special Provisions) | day | 2 | 5000 | 10000 | 2853.67 | 5707.34 | 62.3%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) (Special Provisions) | lump sum | 1 | 25000 | 25000 | 30947.67 | 30947.67 | 112%
X018 | Water Main and Associated Work (Special Provisions) | lump sum | 1 | 150000 | 150000 | 80814.98 | 80814.98 | 42.2%
X018 | Sanitary Main and Associated Work (Special Provisions) | lump sum | 1 | 170000 | 170000 | 261642.33 | 261642.33 | 44.3%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 40000 | 40000 | 67565.33 | 67565.33 | 58.7%
F187 | Excavation - Channel (BCS 1.6.1) | lump sum | 1 | 15000 | 15000 | 13658 | 13658 | 60.9%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 145000 | 145000 | 211692.42 | 211692.42 | 38.9%
F493 | SPCSP - Supply (BCS 18.7) | metre | 44 | 3500 | 154000 | 4372.95 | 192409.8 | 2%
F494 | SPCSP - Assembly (BCS 18.7) | metre | 44 | 1200 | 52800 | 989.57 | 43541.08 | 19.2%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 100 | 250 | 25000 | 271.36 | 27136 | 19.9%
F505 | Heavy Rock Riprap (Class 1M) (BCS 10.7) | cubic metre | 15 | 325 | 4875 | 353.85 | 5307.75 | 30.1%
F970 | Miscellaneous Iron (BCS 13.5) | lump sum | 1 | 1000 | 1000 | 1091 | 1091 | 67.4%
F492 | Roadway Work - and Pathway Work (BCS 18.7) (Special Provisions) | lump sum | 1 | 100000 | 100000 | 218645.48 | 218645.48 | 26%
E020 | Erosion Control Barrier (Fibre Roll) (Special Provisions) | metre | 320 | 15 | 4800 | 20.67 | 6614.4 | 31.7%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) (Special Provisions) | square metre | 300 | 20 | 6000 | 9.7 | 2910 | 21.9%
|  | Bridge File Modified Tender Value |  |  | 1163475 |  | 1502430.23 | 20.9%
|  | Total Tender Value |  |  |  |  | 1589929.61 | 20.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 25 | 37500 | 58 | 87000 | 24.7%
Tender: 42 ¦ Bridge File: 8098-2 ¦ Tender Opening Date: 2024-03-14
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22984 | Construct WSP Culvert | Culvert | Highway | Replace Culvert with Culvert | 2023-2024 | 2024-03-14 | 5 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
77759-2 | Near Wanham | Peace | 733:04 | Pinto Creek | 1 x 1830 WSP | 32 | 32 | 1.8
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | PRORATED - Mobilization (GCS 1.2.9) | lump sum | 1 | 51715 | 51715 | 24763.58 | 24763.58 | 47.7%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1500 | 15000 | 1516.67 | 15166.7 | 24.1%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 10000 | 10000 | 12533.33 | 12533.33 | 42.8%
F018 | Silt and Ice Removal (Special Provisions) | lump sum | 1 | 10000 | 10000 | 11100 | 11100 | 61.8%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 15000 | 15000 | 21066.67 | 21066.67 | 71.4%
F027 | Welded Steel Pipe - Supply (Special Provisions) | metre | 32 | 3500 | 112000 | 2828 | 90496 | 22.3%
F020 | Welded Steel Pipe - Install (Special Provisions) | metre | 32 | 4200 | 134400 | 2859.33 | 91498.56 | 20.6%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 20000 | 20000 | 33000 | 33000 | 38.9%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 20000 | 20000 | 25000 | 25000 | 71.2%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 60 | 340 | 20400 | 306 | 18360 | 4.5%
E020 | Rock Ditch Drains - Class 1M (Special Provisions) | metre | 12 | 300 | 3600 | 426.67 | 5120.04 | 5.3%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 450 | 15 | 6750 | 7.17 | 3226.5 | 60.9%
|  | Bridge File Modified Tender Value |  |  | 418865 |  | 351331.38 | 21.6%
|  | Total Tender Value |  |  |  |  | 19041170.56 | 1.7%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy - Bridge Construction (GCS 1.2.41.9) | day | 1500 | - | - | 17 | 25500 | 11.1%
Tender: 22984 ¦ Bridge File: 77759-2 ¦ Tender Opening Date: 2024-03-14
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
22842 | Construct WSP Culvert | Culvert | Single | Replace Culvert with Culvert | 2023-2024 | 2024-03-19 | 3 | 2025-02-28
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
733-2 | 12 km West of Fort Saskatchewan | North Central | 28A:1 | Tributary to North Saskatchewan River | 1 x 3050 WSP | 45 | 45 | 3
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 150000 | 150000 | 167625 | 167625 | 31.6%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 20000 | 20000 | 28333.33 | 28333.33 | 44%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 10 | 1000 | 10000 | 556.67 | 5566.7 | 116%
F170 | Demolition and Disposal of Bridge Structure (BCS 21.4.1) | lump sum | 1 | 10000 | 10000 | 8566.67 | 8566.67 | 23.7%
F018 | Silt, Ice and Debris Removal (Special Provisions) | lump sum | 1 | 15000 | 15000 | 13610 | 13610 | 37.5%
D540 | Grouting of Abandoned Culverts (HCS 2.4.4) | cubic metre | 187 | 800 | 149600 | 620 | 115940 | 18.2%
F186 | Excavation - Structural (BCS 1.6.1) | lump sum | 1 | 7500 | 7500 | 36483.33 | 36483.33 | 45.9%
F020 | Welded Steel Pipe - Supply (Special Provisions) | metre | 45 | 13000 | 585000 | 11296.67 | 508350.15 | 32.9%
F020 | Welded Steel Pipe - Install (Special Provisions) | metre | 45 | 10000 | 450000 | 12411 | 558495 | 17.6%
F190 | Backfill (BCS 2.4) | lump sum | 1 | 25000 | 25000 | 59550 | 59550 | 29%
F500 | Heavy Rock Riprap (Class 1) (BCS 10.7) | cubic metre | 260 | 270 | 70200 | 349 | 90740 | 16.5%
F492 | Roadway Work (BCS 18.7) | lump sum | 1 | 40000 | 40000 | 28390 | 28390 | 16.6%
E020 | Rock Ditch Drains - Class 1M (Special Provisions) | metre | 75 | 400 | 30000 | 561.67 | 42125.25 | 25.7%
E020 | Erosion Control Barrier (Straw Rolls) (Special Provisions) | metre | 250 | 15 | 3750 | 17.33 | 4332.5 | 35.4%
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 250 | 15 | 3750 | 17.83 | 4457.5 | 28.6%
E510 | Erosion Control Soil Covering - Supply and Install (Type C) (HCS 6.5.6) | square metre | 200 | 15 | 3000 | 12.33 | 2466 | 16.7%
|  | Bridge File Modified Tender Value |  |  | 1572800 |  | 1675031.43 | 20.1%
|  | Total Tender Value |  |  |  |  | 1757533.33 | 18.2%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | - | - | 55 | 82500 | 19.6%
Tender: 22842 ¦ Bridge File: 733-2 ¦ Tender Opening Date: 2024-03-19
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
23921 | Bridge Rehabilitation | Bridge | Single | Bridge Rehabilitation | 2023-2024 | 2024-03-22 | 4 | 2024-10-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
70277-1 | 16 km Southeast of Rocky Mountain House | Central | 22:22 | Clearwater River | 6 x 1140 FC | 32 ¦ 32 ¦ 32 ¦ 14 | 110 | 10.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 175000 | 175000 | 182055.58 | 182055.58 | 9.9%
F750 | Traffic Accommodation for Bridge Construction (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 75000 | 75000 | 153148.04 | 153148.04 | 26%
F170 | Demolition and Disposal of Bridge Structure - Various Elements (BCS 21.4.1) | lump sum | 1 | 60000 | 60000 | 129427.43 | 129427.43 | 32.1%
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 2 | 2500 | 5000 | 1957.73 | 3915.46 | 52.6%
F755 | Surface Removal - Approach Slabs (BCS 20.6.1) | square metre | 51 | 80 | 4080 | 123.24 | 6285.24 | 35.6%
Q554 | Cold Milling Asphalt Pavement - 50 <mm Depth> (HCS 3.16.6) (Special Provisions) | square metre | 275 | 15 | 4125 | 72.74 | 20003.5 | 29.8%
F021 | Grout Void Under Approach Slabs (Special Provisions) | cubic metre | 5 | 1500 | 7500 | 12892.61 | 64463.05 | 116.5%
F018 | Access for Pier Caps & Diaphragm Repairs (Special Provisions) | lump sum | 1 | 150000 | 150000 | 129765.77 | 129765.77 | 35.7%
F760 | Partial Depth Repair - Deck and Approach Slabs (BCS 20.6.2) | square metre | 35 | 1500 | 52500 | 1362.48 | 47686.8 | 38.8%
F760 | Partial Depth Repair - Deck Underside (BCS 20.6.2) | square metre | 2 | 4000 | 8000 | 4752.5 | 9505 | 43.8%
F760 | Partial Depth Repair - Abutments and Exterior Girder Ends (BCS 20.6.2) | square metre | 10 | 1500 | 15000 | 2215.67 | 22156.7 | 30%
F760 | Partial Depth Repair - Girders (BCS 20.6.2) | square metre | 3 | 4000 | 12000 | 3677.64 | 11032.92 | 42.7%
F760 | Partial Depth Repair - Pier Caps and Pier Diaphragms (BCS 20.6.2) | square metre | 20 | 2500 | 50000 | 2088.43 | 41768.6 | 30.1%
F760 | Partial Depth Repair - Curbs (Top and Interior Face) (BCS 20.6.2) | square metre | 10 | 2000 | 20000 | 2197.59 | 21975.9 | 21.1%
F760 | Partial Depth Repair - Curb Fascia (Exterior Face) (BCS 20.6.2) | square metre | 10 | 5000 | 50000 | 2814.25 | 28142.5 | 32%
F020 | Concrete Crack Sealing - Pressure Injected Epoxy (Exterior Curb Fascia) (Special Provisions) | metre | 10 | 1000 | 10000 | 472.6 | 4726 | 69.7%
F020 | Concrete Crack Sealing - Pressure Injected Epoxy (Curb Top and Interior Face) (Special Provisions) | metre | 100 | 150 | 15000 | 312.81 | 31281 | 31.7%
F020 | Concrete Crack Sealing - Pressure Injected Epoxy (Pier Caps) (Special Provisions) | metre | 30 | 500 | 15000 | 346.79 | 10403.7 | 21.1%
F928 | Deck Joint Assemblies - Supply, Fabrication, Delivery and Installation (BCS 6.4.2) (Special Provisions) | lump sum | 1 | 600000 | 600000 | 369858.19 | 369858.19 | 28.9%
F980 | Asphalt Concrete Pavement - Mix Type H2 (PG 58-28) Mix Type H2 (PG 58-28) (BCS 17.7.2) | tonne | 47 | 650 | 30550 | 1113.15 | 52318.05 | 36.6%
Q795 | Chip Seal Coat (CRS-2P) - Bridge Decks Des. 3 Class 12.5BW (HCS 3.24.12) | square metre | 20 | 250 | 5000 | 1061.01 | 21220.2 | 78.3%
F018 | Approach Rail Transition - Supply and Install (Special Provisions) | lump sum | 1 | 80000 | 80000 | 113640.44 | 113640.44 | 13.6%
F022 | Concrete Sealer - Type 3 Pigmented (Special Provisions) | square metre | 226 | 60 | 13560 | 102.97 | 23271.22 | 68.1%
F022 | Concrete Sealer - Type 1C (Special Provisions) | square metre | 230 | 60 | 13800 | 53.21 | 12238.3 | 49.1%
F053 | Drain Trough Collectors - Supply and Install (Special Provisions) | unit | 2 | 15000 | 30000 | 12854.22 | 25708.44 | 10.3%
F018 | Erosion Repairs (Special Provisions) | lump sum | 1 | 40000 | 40000 | 26204.51 | 26204.51 | 30.5%
F505 | Heavy Rock Riprap (Class 1M) (BCS 10.7) | cubic metre | 40 | 200 | 8000 | 302.52 | 12100.8 | 31.6%
F018 | Remove Drift (Special Provisions) | lump sum | 1 | 5000 | 5000 | 14443.71 | 14443.71 | 28.8%
F018 | Miscellaneous Repairs (Special Provisions) | lump sum | 1 | 2000 | 2000 | 23866.2 | 23866.2 | 24.5%
X002 | Extra Work - Various Repairs (Special Provisions) | Total Force Account | 1 | 100000 | 100000 | 100000 | 100000 | 0%
|  | Bridge File Modified Tender Value |  |  | 1656115 |  | 1712613.25 | 10.7%
|  | Total Tender Value |  |  |  |  | 1847613.55 | 9.8%
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 75 | 112500 | 90 | 135000 | 4.5%
Tender: 23921 ¦ Bridge File: 70277-1 ¦ Tender Opening Date: 2024-03-22
Tender | Work Description | Structure Type | Project Type | Work Type | Tender Fiscal Year | Tender Opening | Number of Bidders | Specified Completion
18144 | Construct SWSP Culvert - Spray Line SPCSP Culvert | Culvert | Single | New and Lined Culverts | 2023-2024 | 2024-03-26 | 2 | 2024-11-15
Bridge File | Location | Region | Hwy | Crossing | Span/Culvert Details | Bridge Span or Culvert Lengths | Bridge/Culvert Total Length | Avg Bridge Width / Culvert Diameter
78643-2 | Near Kinuso | Peace | 33:14 | Jerry Creek | 1 x 3000 SWSP - 1 x 1800 Spray Lined SPCSP | 93 - 90 | 183 | 2.4
Bid Item Code | Description | Unit | Estimated Quantity | Unit Price (C-Estimate) | Total (C-Estimate) | Unit Price (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X100 | Mobilization (GCS 1.2.9) | lump sum | 1 | 580000 | 580000 | 570000 | 570000 | -
F750 | Traffic Accommodation for Bridge Construction (B.F. 78643) (HCS 7.1.12) (HCS 7.1.15) | lump sum | 1 | 100000 | 100000 | 37500 | 37500 | -
E612 | Fish Capture, Salvage, and Release (Special Provisions) | day | 8 | 1500 | 12000 | 55 | 440 | -
E612 | Total Suspended Solids (TSS) Testing (Special Provisions) | day | 20 | 1200 | 24000 | 55 | 1100 | -
X018 | Site Isolation and Water Accommodation (Special Provisions) | lump sum | 1 | 50000 | 50000 | 87500 | 87500 | -
F186 | Excavation - Structural (B.F. 78643) (BCS 1.6.1) | lump sum | 1 | 30000 | 30000 | 77500 | 77500 | -
F187 | Excavation - Channel (B.F. 78643) (BCS 1.6.1) | lump sum | 1 | 60000 | 60000 | 65000 | 65000 | -
F196 | Backfill - Non-Granular (B.F. 78643) (BCS 2.4) | lump sum | 1 | 30000 | 30000 | 100000 | 100000 | -
F018 | Existing Culvert Surface Preparation - Geopolymer Lining (Special Provisions) | lump sum | 1 | 10000 | 10000 | 100000 | 100000 | -
F022 | Geopolymer Culvert Lining (Special Provisions) | square metre | 701 | 2000 | 1402000 | 1750 | 1226750 | -
F027 | SWSP (3000 mm dia x 25.4 mm thickness) - Supply (Special Provisions) | metre | 93 | 9400 | 874200 | 15075 | 1401975 | -
F020 | SWSP (3000 mm dia x 25.4 mm thickness) - Install (Special Provisions) | metre | 93 | 25000 | 2325000 | 15075 | 1401975 | -
F021 | Grout Filling Voids for SWSP Installation (Special Provisions) | cubic metre | 20 | 10000 | 200000 | 1250 | 25000 | -
F715 | Substrate Holders - Steel (B.F. 78643) (BCS 18.7) | unit | 11 | 1500 | 16500 | 5000 | 55000 | -
F040 | Heavy Rock Riprap (Class 1) - (B.F. 78643) - Substrate (Special Provisions) | tonne | 140 | 160 | 22400 | 337.5 | 47250 | -
F040 | Heavy Rock Riprap (Class 2) - (B.F. 78643) (Special Provisions) | tonne | 2370 | 165 | 391050 | 187.5 | 444375 | -
F720 | Substrate Holders - Rock (B.F. 78643) (Special Provisions) (BCS 18.7) | unit | 23 | 1500 | 34500 | 1000 | 23000 | -
F492 | Roadway Work (B.F. 78643) (Special Provisions) (BCS 18.7) | lump sum | 1 | 60000 | 60000 | 175000 | 175000 | -
S805 | Strong Post W-Beam Guardrail - Supply and Install (HCS 5.25.5) (HCS 2.19.4) | metre | 21 | 500 | 10500 | 450 | 9450 | -
S811 | Impact Attenuator (NCHRP 350/MASH 2009 TL-3) - Supply and Install (Special Provisions) | unit | 4 | 6000 | 24000 | 10000 | 40000 | -
E052 | Willow Staking (Special Provisions) | unit | 920 | 20 | 18400 | 25 | 23000 | -
E020 | Brush Layering (Special Provisions) | metre | 159 | 200 | 31800 | 125 | 19875 | -
E505 | Erosion Control Soil Covering - Supply and Install (Type B) (HCS 6.5.6) | square metre | 600 | 10 | 6000 | 12.5 | 7500 | -
E020 | Erosion Control Barrier (Fiber Roll) (Special Provisions) | metre | 200 | 20 | 4000 | 20 | 4000 | -
E435 | Erosion Control Barrier (Silt Fence) (HCS 6.5.6) | metre | 200 | 20 | 4000 | 20 | 4000 | -
E052 | Tree Planting (Special Provisions) | unit | 200 | 50 | 10000 | 25 | 5000 | -
|  | Bridge File Modified Tender Value |  |  | 6330350 |  | 5952190 | -
|  | Total Tender Value |  |  |  |  | 6087190 | -
Item No | Description | Unit | Unit Price | Quantity (C-Estimate) | Total (C-Estimate) | Quantity (Low 3 Bids Avg) | Total (Low 3 Bids Avg) | Coefficient of Variation
X004 | Site Occupancy (GCS 1.2.41.9) | day | 1500 | 90 | 135000 | 90 | 135000 | -
Tender: 18144 ¦ Bridge File: 78643-2 ¦ Tender Opening Date: 2024-03-26